Contents

I.	General information	2

II.	Tender requirements	9

1.	Qualifications of proposed staff	9

1.1	Expert 1:	9

1.1.1	General qualifications	9

1.1.2	Experience in the region/knowledge of the country	9

1.1.3	Language skills:	9

1.2	Expert 2:	9

1.2.1	General qualifications	9

1.2.2	Experience in the region/knowledge of the country	10

1.2.3	Language skills:	10

2.	Quantitative requirements	10

III.	Outsourced processing of personal data	12

General information

Brief information on the project

Since 2015, GIZ Ghana has been developing Public-Private Partnership (PPP) projects with some of the Ghanaian private companies, funded through the develoPPP programme and the Special Initiative on Decent Work for a Just Transition. These projects are implemented by GIZ on behalf of the German Federal Ministry for Economic Cooperation and Development (BMZ).

The project will be implemented in the Northern Region by GIZ on behalf of BMZ in collaboration with Bunge Loders Croklaan (Bunge) B.V., a leading global producer and supplier of sustainable plant-based specialty oils and fats for the food manufacturing industry. It operates as the global B2B edible oils business of Bunge Limited. Bunge Loders Croklaan B.V. (Bunge) has over 50 years of experience in the shea industry and has its own processing facility in Ghana since 2019.

On behalf of GIZ and Bunge, many project activities will be conducted by the international, not-for-profit agri-agency foundation Agriterra. Agriterra works in emerging and developing economies and was founded by Dutch farmers’ organisations and cooperatives almost 25 years ago as an organization for international peer-to-peer agricultural cooperation.

In this dynamic, the project “Women Empowerment through the creation of independent women shea business cooperatives” was developed.

The objective of the project is to improve the livelihoods of shea collecting women and their communities in North Ghana. This shall be reached through various activities, one of the main activities being the creation and official registration of independent women business cooperatives in six communities. The officially registered business cooperatives will enable the women and their communities to establish direct selling relationships with customers, ensuring future stable, traceable, sustainable, and verifiable supply of shea to global markets. Setting an example with the shea nut value chain within the framework of the project, the cooperatives learn how to professionally organize themselves, develop a business mindset, and set up business plans for sustainable income-generating activities. Being equipped with these tools through various training measures, the independent women business cooperatives are capacitated to apply this knowledge to other income-generating activities and crops outside of the shea season whenever they see market opportunities. This might apply to improved productivity of producing and processing other crops the communities are already engaging with, such as soy, rice, beans etc.

The creation and official registration of the business cooperatives comes along with various training measures to capacitate the women to sustainably manage the cooperatives on their own. Agriterra’s local team in Ghana will conduct training measures on topics such as cooperative management, basic financial management, recordkeeping, youth engagement, marketing strategy, storage and pricing mechanisms, on aggregation, weighing and loading as well as on soft-skills such as literacy, communication, verbal negotiation- and discussion skills.

Besides the creation and official registration of the business cooperatives, the project will conduct further activities, which will add on the creation of cooperatives. This entails:

- Training measures on Good Agricultural Practices (GAP) to enhance the quality and quantity of shea nuts produced by the cooperatives members. High-quality shea nuts mean a better price paid by the global market, e.g. by Bunge, and as such an increased income. It may also prepare the cooperatives for potential value addition coming from possible future certifications;

- Training women to create their own energy-efficient processing cookstoves. As less wood is needed for the burning and heating process, the usage of the energy efficient processing cookstoves has a positive impact on the working conditions of the women as they are less exposed to smoke and a positive impact on the environment, contributing to the reduction of CO2 emissions;

- Digitalization: Introduction and training on the usage of an app such as FarmerLine, Softribe, agrocenta or any other suitable software to improve record keeping and cooperative data management. This allows digital member registration and enables the cooperative to access helpful data and information on crop prices etc. On top, it enables traceability for buyers and end-consumers. The introduction of digital tools improves the traceability of the shea nut supply, which will lead to a competitive advantage for the cooperatives and enable them to enter direct sourcing business relationships with global buyers;

- Introduction of Village-Saving-Loan-Associations (VSLAs) in two cooperatives to support financial inclusion opportunities. VSLAs sustainably enable the cooperatives to take independent decisions on savings and investment, such as financing critical farming inputs needed to increase productivity, crop yields and thus income. VSLAs serve the communities as credits and insurance, e.g. allowing individuals and families to financially cope with emergency situations;

- Distribution of consumables, tools and equipment: the distribution of shea tools and equipment such as shea rollers, gloves and tricycles will benefit the safety, health and working conditions of the women during the collection- and processing activities.

- Installation of six warehouses (one warehouse per community): allow the cooperatives to aggregate and safely store their harvest and protect the quality shea nuts and other crops from rain and thus from rotting.

Context

- In Ghana, 24.2% of the population lives below the poverty line. The national youth unemployment rate for young adults (aged 15-24) is 32.8% in the Savannah region and 34.7% in the Northeast. According to TreeAid, shea is a useful crop to fight poverty.

- Nearly 2 billion shea trees grow naturally on parklands in 21 African countries stretching from Senegal to South Sudan, while 16 million women living in rural communities individually collect fresh shea fruits and kernels for processing. Particularly in the rural areas of northern Ghana, the shea industry is traditionally dominated by women and represents a critical source of jobs and income to often poor and underserved communities. While shea trees provide a rare opportunity for women to earn their own income and become financially independent in an environment where women are often excluded from income-generating activities due to entrenched gender inequality, female rural shea farmers are the lowest earners in the shea value chain, with an annual income of about US$234 per capita. As many women are working individually or in unorganized groups without profound knowledge of the shea value chain, economic opportunities are left unexploited.

- Against this background, the project seeks to, through the creation of business cooperatives and related training measures, create new jobs, increase the income and improve the working conditions of the members of the newly created cooperatives. The latter including, amongst other aspects, improved occupational health and safety (OSH) conditions. The distribution of shea tools and equipment (rollers, gloves etc.) for example will benefit the safety, health and working conditions of the women during the collection- and processing activities. Gloves and rollers protect women shea collectors from snake or scorpion bites and allow them to stand upright while collecting nuts from the ground, meaning that women no longer must bend down for the nut collection. The provision of tricycles facilitates mobility and transportation as it reduced the need for the women to walk fast distances and carry heavy bags. The introduction of energy-efficient processing cookstoves reduces the exposure of the women to fire, as less wood is needed for the burning process, thus emitting less smoke.

- As the energy-efficient processing cookstoves, besides improving the working conditions of the women, have a positive effect on the environment by emitting less CO2, the project further aims at measuring the CO2 reduction that results from the project.

- Furthermore the project seeks to benefit the members of the newly created cooperatives to benefit from access to admin and digital traceability systems through the introduction of an digital app.

To facilitate the monitoring and evaluation of the project progress and impact, a contractor is solicitated to conduct a baseline survey.

Objective of the consultancy

Conduct a comprehensive baseline study to gather data on the (i) current situation, (ii) needs of the target population, (iii) existing gaps, (iv) key performance indicators (KPIs) and other key indicators (as per the table of key indicators) in order to provide valuable insights that guide the development of appropriate interventions to track progress towards achieving desired outcomes (output and impact) of the project.

The baseline study should ensure the measurability/ plausibility of data and guarantee proper setup of M&E system including relevant table of key figures,  theory of change, KPIs and if needed, set up for a tracer study (check criteria for tracer study and give recommendations).

The findings of the study will be used to finetune the project’s intervention logic (theory of change) and serve as a starting point for effectively monitoring and evaluating the impact of the project’s intervention.

Other key information related to the project

Below, are some key information to be considered by the contractor for a better outcome of the assignment.

Key Performance Indicators - KPIs

KPI 1: 2500 women (x youth, z people with disabilities) are successfully trained along the shea value chain.

- Overview on the training measures will be provided by project partners

KPI 2: 183 women are newly employed

- 183 new jobs will be created as 30 women from outside the shea industry are expected to join as cooperative members per cooperative, plus 3 new cooperative managers will be recruited to support the cooperatives in their management and execution. It is intended to support women to take up the role as business cooperative managers whenever possible.

KPI 3: 2.317 women benefit from improved working conditions along the shea value chain

- A detailed overview on the improved working condition is found in Chapter 3 of the project concept.

KPI 4: 2.317 women benefit from an income increase of 10%

- Increase in income due to a premium paid by Bunge for quality nuts and good cooperative management. Indirect impact on income increase could come as a result of income diversification through the creation of additional income streams.

- The baseline study shall determine the average current income level of women in the communities, consisting of income streams from a) shea, b) other streams of revenue. The baseline shall distinguish between the income revenue resulting from shea and the income streams resulting from other sources

- The baseline study shall determine which capacity building measures can aid the women to secure more streams of revenue outside the shea collection season

KPI 5: 2.500 members of the newly created cooperatives benefit from access to admin and digital traceability systems

- Through the introduction of a digital app

KPI 6: CO2 emissions are reduced by X% due to the use of 1500 energy-efficient processing cookstoves (250 per cooperative) that are provided

- Reduction of firewood use by 40%

- The baseline shall determine the X% reduction of CO2 emissions (in tons of CO2 emission) expected as a result of the 40% reduction of firewood use

For KPIs 1-5, the number of persons with disabilities and number of people defined as youthshall be defined with the baseline study.

Milestones:

- 6 independent women business cooperatives are officially registered

- 2,500 people are members of the 6 created cooperatives (500 members in cooperatives A-D each, 250 members in cooperatives E-F each)

- Village Saving Loan Associations (VSLAs) are installed in 2 communities

- 6 warehouses (1 per cooperative) are constructed.

Intervention zone

6 communities in the West Mamprusi area

Target population (Expected number for each target population and their distribution across project’s regions to be supplied by Private Partner Bunge)

6 cooperatives (direct) and their communities (indirect):

- Women smallholder farmers, especially youth, as members of the cooperatives

- Heads/management board of the cooperatives, including cooperative managers

- District Agricultural Extension Officers

None of the interventions in the framework of the project can be done without prior consent and support of local chiefs and community advocates

GIZ shall hire the contractor for the anticipated contract term, from 16.09.2024 to 29.11.2024.

The services described in Section 4 shall be provided until 29.11.2024.

The contractor shall provide the following work/service

- Partake in an inception meeting with GIZ, Bunge and Agriterra to discuss the objective and expected results of the assignment, target population, geographic scope, timeframe for the study and possible data sources.

- Elaborate implementation plan and share with GIZ, Bunge and Agriterra.

- Identify the target population and determine the sample size of the study based on information furnished by GIZ, Bunge and Agriterra. This should be representative of the general target population. Further determine biographic data of the target population of women, such as number of youth (people aged 15-35) and people with disabilities.

- Develop data collection tools(in line with GIZ P&R). These should be designed to answer the research questions identified in the objectives (What is the current situation? What are the needs of the target population? What are the gaps in the current situation? and What are the actual status of the KPIs?). The appropriate data collection methods (review of documents, surveys, interviews, focus group discussions, observation, or a combination of these) to be determined by the contractor. Data collection tools and methods selected should be convenable to collect both quantitative and qualitative data.

Actual situation:

Needs of target population:

  - Trainings

  - Equipment / materials to improve working conditions

KPIs & other key figures:

  - Definition

  - Baseline data

  - Data sources

  - Milestones

  - Targets

- Pre-test data collection tools and methods to detect and correct any errors or weaknesses in the data collection tools and/ or any logistical or practical issues that may arise during data collection. This should be conducted on a small sample of the real target population and in similar setting to the actual data collection.

- Organise data collection and entry. Elaborate and implement a data collection plan. Select and train data collectors on data collection tools and ethical consideration, and how to approach the target population and obtain informed consent.

- Put mechanisms in place to ensure the quality of data collected. Enter data collected into data entry tool developed. Identify and document best practices, success stories, and lessons learned as well.

- Organise data analysis. Elaborate and implement a data analysis plan. Ensure that data collected and entered are cleaned, coded, and checked for accuracy. Analyse data by using recommended statistical software for quantitative data and thematic analysis for qualitative data.

- Interpret the findings. The information gotten from the analysis should be used to identify the strengths and weaknesses of the current situation, identify the gaps that need to be addressed through the intervention and identify information related to each of the project’s KPI (definition, mode of calculation, mode of verification, baseline value, annual milestone, targets, data source, data collection cost, responsibility for data collection). The contractor’s attention must be drawn to the fact that, targets (general and disaggregation by gender, age and persons with disabilities) have been set for the project’s KPIs already. However, the contractor is permitted to confirm if these targets are realistic or not, and new targets if possible.

- Develop a comprehensive baseline report, including:

  - Executive summary

  - Methodology and limitations

  - Findings and results

  - Key performance indicators with actualised attributes (baseline values, milestones, targets, definitions, etc.)

  - Conclusions

  - Recommendations for project implementation and monitoring

In addition to the comprehensive report, a PowerPoint presentation should be developed.

- Present the baseline report. The report should be shared with the stakeholders, including the project team.

N.B. Please note that this ToR could be subjected to further adjustments in consultation with the consultant and the project partners during the inception meeting.

Period of assignment: from 16.09.2024 to 29.11.2024.

| Milestones/partial works | Date/location/responsibility | Criteria for acceptance |
| --- | --- | --- |
| Inception meeting is organised | 17.09.24/Accra/GIZ, Bunge and Agriterra | Availability of meeting minutes |
| Implementation plan is elaborated | 20.09.24/Accra/Contractor | Existence of inplementation plan |
| Target population and sample size are determined | 16.09.24/Accra/Contractor | Availability of estimate of target population and sample |
| Data collection tools are developed and pre-tested | 27.09.24/Accra/Contractor | Existence of approved data collection tools |
| Data collection and data entry are organised | 30.10.24/ Project implementation regions/Contractor in close agreement with GIZ, Bunge and Agriterra | Availability of raw data |
| Data analysis and data interpretation are conducted | 15.11.24/Accra/Contractor | Availability of findings |
| Final report is elaborated and presented to stakeholders GIZ, Bunge and Agriterra | 29.11.24/Accra/Contractor | Existence of approved report |

Tender requirements

## Qualifications of proposed staff

The tenderer is required to propose personnel for the positions specified here and described with respect to the areas of responsibility and qualifications on the basis of relevant CVs.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

Profile of contractor/ firm

- At least 10 years of experience in the domain of research and/or evaluation

- Proven experience in conducting baseline studies, especially for projects in the private sector

- Possess vast experience in project development and management

- Demonstrate ability to communicate effectively with various partners including government, civil society, the private sector, development partners and communities.

- Strong cross-cultural skills and ability to foster relationships with key stakeholders.

- Ability to work under pressure, effectively coordinate with others, and meet tight deadlines without compromising the quality of work

- Excellent analytical and writing skills

## Expert 1:

## General qualifications

Education:	University qualification (first degree/master’s) in research and/ or evaluation

Professional experience:	 10 years of professional experience in the domain of project managment, research and evaluation or similar fields. Also, experience in research design and data analysis is required.

## Experience in the region/knowledge of the country

5 years of working experience in the regions of Ghana

## Language skills:

Business fluency in C1

## Expert 2:

## General qualifications

Education:	University qualification (first degree/master’s) in research and/ or evaluation

Professional experience:	5 years of professional experience in the domain of research and evaluation, data analysis and report writing.

## Experience in the region/knowledge of the country

2 years experience in the regions of Ghana

## Language skills:

Business fluency in C1. Also local language in the Northern region of Ghana.

A team of 5 enumerators are to be recruited to support with data collection and entry.

## Quantitative requirements

Per-diem and overnight accommodation allowances are reimbursed as a lump sum up to the maximum amounts permissible under tax law for each country as set out in the country table in the circular from the German Federal Ministry of Finance on travel expense remuneration (download at https://www.bundesfinanzministerium.de).

All travel activities must be agreed in advance with the staff member responsible for the project.

Sustainability aspects for travel

GIZ would like to reduce greenhouse gas emissions (CO2 emissions) caused by travel. When preparing your tender, please incorporate options for reducing emissions, such as selecting the lowest-emission booking class (economy) and using means of transport, airlines and flight routes with a higher CO2 efficiency. For short distances, travel by train (second class) or e-mobility should be the preferred option.

If they cannot be avoided, CO2 emissions caused by air travel should be offset. GIZ specifies a budget for this, through which the carbon offsets can be settled against evidence.

The market for carbon credits is made up of a large number of providers, each with different claims as to their climate impact. The Development and Climate Alliance has published a list of standards. GIZ recommends using the standards specified there.

Specification of Inputs

| Fee days | Number of experts | Number of days per expert | Total | Comments |
| --- | --- | --- | --- | --- |
| Designation of TL | 1 | 20 | 20 | Project Team Lead |
| Designation of key expert 1 | 1 | 15 | 15 | Expert 1 |
| Travel expenses | Quantity | Number per expert | Total | Comments |
| Per-diem allowance in country of assignment | 2 | 5 | 10 | Lump-sum |
| Overnight accommodation | 2 | 5 | 10 | Against evidence |
| Transport | Quantity | Number per expert | Total | Comments |
| CO2 compensation for air travel |  |  |  | A fixed budget of EUR is earmarked for settling carbon offsets against evidence. |
| Other costs | Number | Price | Total | Comments |
| Flexible Enumeration | 5 Enumerators | 31 | 155 | Daily lump sum for 5 enumerators for up to 10 days. |
| Fuel | 11 | 100 | 1100 | Fuel for field work |

Calculate your financial bid exactly in line with the quantitative requirements of the specification of inputs above. There is no contractual right to use up the full days/travel or workshops or budgets. The number of days/travel/workshops and the budgets will be contractually agreed as maximum amounts. The regulations on pricing are contained in the price schedule.

- Conceptual

The tender should indicate how the services outlined in Section I.4 (Tasks) are to be provided. Reference should be made to the following criteria:

- 3.1 Strategy: interpretation of the objectives in the TOR, critical examination of outlined tasks and presentation of implementation strategy

- 3.2 Processes: Presentation of implementation plan (activities, milestones and schedule)

- 3.3 Project management: i) How to coordination with key partners, ii) presentation of personnel assignment plan and iii) Monitoring & Evaluation (collection of data and reporting)

# Requirements on the format of the tender

The CV submitted for each expert can have a maximum of four pages. The concept (if required) should not exceed five pages. If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered).

Outsourced processing of personal data

# The performance of the contract may be associated with the processing of personal data by the contractor, such as (but not limited to) names and contact information and who would alone define the nature of such data and how such processing would be carried out. In such cases, the contractor shall act as an independent DATA CONTROLLER and must alone comply with ALL applicable data protection obligations, including those stemming from regional and local laws. The contractor shall process personal data only when a given goal cannot be reasonably attained without such data. The data protection principles such as lawfulness, data minimization, accuracy, purpose limitation, storage limitation, transparency, integrity and confidentiality, and accountability, as well as the numerous rights of the data subject must be paid due attention. The GIZ is NOT in any way responsible for such processing.

# If the contractor is not subject to the GDPR and the applicable laws do not contain any explanation on the data protection principles and rights mentioned here, the definitions and meanings provided by the GDPR (Regulation (EU) 2016/679) should be considered.

Annexes

- Project concept and project plan

- Table of key Figures

- Theory of Change

- develoPPP for Jobs M&E manual with M&E definitions for KPIs

Increase of real income, i.e. adjusted for inflation.

This project refers to the youth definition by the African Union, according to which, persons aged between 15-35 are considered as youth.