| 6 cities damage assessment | Project number/ cost centre: 23.1821.0-001.00 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AI	Artificial Intelligence

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

CW	Calendar Week

DREAM	Digital Restoration Ecosystem for Accountable Management

GDPR	General Data Protection Regulation

HCD	Human Capacity Development

FK	Expert

FKT	Expert days

GIS	Geographical Information System

KZFK	Short-term expert

ML	Machine Learning

SUR 	Strengthening of Urban Resilience in the Areas of Supply Infrastructure and Housing

ToRs	Terms of reference

- Context

Description of the project

The new GIZ transitional aid project Strengthening of Urban Resilience in the Areas of Supply Infrastructure and Housing (SUR) focuses on the repair and rehabilitation of critical supply infrastructure and services as a contribution to municipal civil protection, as well as urban resilience and the rehabilitation, repair, and creation of municipal and private housing as a contribution to social resilience in Ukraine. The goal of the project is to strengthen municipal services of general interest systematically in selected regions. It thus fits into the Transitional Assistance field of action reconstruction of basic infrastructure and services.

The focus is, on the one hand, on immediate measures to restore the functionality of damaged or destroyed critical supply infrastructure in a robust, adaptive, and, if possible, future-proof manner. And thus, urban resilience, i.e. the ability of an urban system to react resiliently in the event of crises, while at the same time adapting, reshaping, and strengthening itself in terms of sustainable urban development. Where available, current damage analyses and existing planning principles are used to contribute to the medium- and long-term development of municipalities in the sense of a build-back-better approach. When selecting measures, care must be taken to ensure that they are modular, flexible, replicable, scalable, and can be implemented quickly in order to achieve economies of scale in procurement processes. Of particular importance is the consideration of local winter relief measures and aid offers from the international community.

On the other hand, the selected cities and municipalities, as well as private actors (owners, if possible, owner associations or neighbourhood cooperatives), are supported in the rehabilitation, repair, and creation of housing.

Background Information and Objective of this Assignment

Russia's ongoing invasion of Ukraine is leading to changing requirements in the development of conceptual and strategic approaches to the reconstruction of Ukrainian cities. This relates to building the capacity of city administrations in the areas of planning and management, the basic renovation of vacant buildings or the establishment of demonstration projects for the construction and integration of permanent housing into the urban fabric. In parallel, planning and reconstruction activities are being carried out in concrete terms to provide adequate housing for the resident population and internally displaced persons. In response to the current situation and as a necessary investment for the future, planning and physical reconstruction will be carried out under the aspect of "creating resilient cities in Ukraine".

The transitional assistance project Strengthening of Urban Resilience in the Areas of Supply Infrastructure and Housing (SUR) makes an important contribution to the implementation of a reform concept towards planning and building resilient cities and neighbourhoods. Due to the war situation, this remains a major challenge for all levels of government - national, regional and local - as planning concepts, housing situation, and the rehabilitation of social and technical infrastructure have to be thought of in parallel and interlinked.

Within the scope of its urban planning activities, as well as the repair and rehabilitation of critical supply infrastructure and services, SUR will utilize a support tool for rapid reconstruction. Additionally, SUR will primarily offer support services in form of HCD measures for city employees. To effectively carry out these activities, access to up-to-date information on the condition of residential buildings and social and technical infrastructure is a fundamental requirement.

Currently, information on the condition of or damage to buildings and social and technical urban infrastructure is only available through ground-based surveys. However, this information is mostly based on old paper maps, is usually not accurately geo-referenced, and usually only depicts damage visible from the ground. Obstacles to these damage assessment procedures are often safety aspects and the risk posed by unexploded ordnance and, in some cases, mines.

The main objective of the assignment is to improve access to accurate digital information on (war-related) damage to buildings and urban technical infrastructure. This information is essential input for key project activities and outputs, such as computer simulations on different resilience scenarios, urban and neighbourhood planning, and training materials. Furthermore, satellite photos evaluations shall provide important information on debris levels, recovery options, and potential hazards in the immediate vicinity of the damage sites.

- Tasks to be performed by the contractor

  - Tasks

The contractor is responsible for providing the following services:

Task 1. Identification and acquisition of suitable image material and GIS-Data, acquisition / renting of required technical resources

Task 2. Evaluation of satellite imagery and assessment/classification of damage. Data storage and data availability ensured for all stakeholders. Data representation and visualisation. Data enrichment and platform integrability. Capabilities for technical evolution. Preparation of documentation/training materials.

Task 3. Delivery of team trainings Guidance and monitoring of continuing damage assessment activities conducted by project staff and project partners.

Task 1. Identification and acquisition of suitable image material and GIS-Data, acquisition / renting of required technical resources

Task 2.2.1.1. Project group participants identification;

Task 2.2.2.2. Satellite images, are available, and quality is assessed for 290 sq.km.;

Task 2.2.1.3. Required technical resources specified and requested (server computing power)

Task 2.2.1.4. Required technical resources specified and requested (85 % of required server cloud storage is available)

As part of this task, the contractor must procure the satellite images required for the damage assessments. The reference area is the city of Balakliya, Kupiansk, Lozova, Merefa, Chuhuiv (Kharkiv region), Chornomorsk (Odesa region) and its surroundings. The approximate area of satellite imagery to cover these cities and their surroundings within these images is 290 km2.

Image data of urban areas can only be obtained from satellite images. Drone flights over urban areas must be ruled out for safety reasons.

The imagery to be procured shall meet the following criteria:

  - it must allow an exact damage assessment via a before - after comparison. Pre-war and current images for one and the same area must therefore be obtained in comparable resolution and quality;

  - A resolution of the satellite images of 19 - 49 cm/pixel is expected;

  - Satellite images must be rectified and transformed to the valid geo-reference system.

Anticipated number of expert days for completion: Team leader – 2 FKT; Key expert 1 – 0 FKT; Key expert 2 – 3 FKT.

Task 2. Evaluation of satellite imagery and assessment/classification of damage. Data storage and data availability ensured for all stakeholders. Data representation and visualisation. Data enrichment and platform integrability. Capabilities for technical evolution. Preparation of documentation/training materials.

Task 2.2.2.1. Required technical resources specified and requested (15 % of required server cloud storage is available)

Task 2.2.2.2. Damage assessment finalized;

Task 2.2.2.3. Data storage and data availability ensured for all stakeholders

Task 2.2.2.4. Project results are uploaded to the urban cadastre or other digital tool, or transferred to the responsible representatives of the executive committees of the city councils;

Task 2.2.2.5. Documentation of the project results finalized and user guide preparation

Evaluation of satellite imagery and assessment/classification of damage.

In this task, the acquired satellite images are analysed using advanced Machine Learning (ML) and/or Artificial Intelligence (AI) techniques to assess the extent of damage to buildings. The analysis should be conducted following the requirements:

  - each visible building is assigned one of the classifications in accordance with the requirements of regulatory legal acts of Ukraine and technical regulations;

  - each visible building is assigned one of four classifications:

- completely destroyed;

- largely destroyed;

- partly destroyed;

- completely undamaged;

  - an identified building should be easily available (navigated) on the online interactive map view interface;

  - estimated level of destruction of critical infrastructure using overlay of the infrastructure GIS layer and the satellite images information based on 1 km2 grid;

  - for each building in destruction category 1 and 2, a calculation of the amount of debris is made (mixed building debris; reinforced concrete, bricks, plaster and breeze blocks; wood, plastics and various bulky items; other debris) enabling debris management and urban recycling.

All building damages are visualised per quadrant (1 km2) in the satellite images (e.g. as GIS application) and presented in tabular form. In case of damages to urban infrastructure, these are described textually and georeferenced with the corresponding GIS layer. In addition, for all damaged buildings, ownership is referenced using cadastral information.

Depending on the assessment methodology and tools, server computing power and server cloud storage space are provided and administered on a server system.

Anticipated number of expert days for completion: Team leader – 44 FKT; Key expert 1 – 51 FKT; Key expert 2 – 45 FKT.

Data storage and data availability ensured for all stakeholders

Make sure GIS data and tools developed or used during the project will remain available after its completion.

Anticipated number of expert days for completion:  Team leader – 9 FKT; Key expert 1 – 4 FKT; Key expert 2 – 14 FKT.

Data representation and visualisation

It is expected that the assessment analysis will be easily accessible by users via UI to ensure digitalization goals of the program:

- Data should be available in an online digital view, accessible through a web-based interface;

- Enable users to navigate through the city map, providing a way to explore different buildings and their corresponding damage assessments;

- Display contextual data of the destroyed buildings (e.g. calculations of area of destruction, time for reconstruction etc.);

- Ensure that the algorithms for calculations are flexible and can be improved over time to reflect the most accurate and up-to-date information;

- Enable the generation of data reports based on the assessment results and selected object layers;Ensure capability for real-time updates to reflect the latest assessment information as new data becomes available.

Data enrichment and platform integrability. Capabilities for technical evolution. Preparation of documentation/training materials

This task focuses on enhancing the data and ensuring the integrity of the platform through integration with various data sources and compatibility with other systems. The following capabilities should be in place:

- Ensure that the view of the buildings and city landscapes on the map can be enriched with additional data sources such as address registers, city cadastral layers, and city plans;

- The proposed solution should have capabilities for seamless integration with official government data sources (e.g. such as Unified State Register of Addresses, urban cadastre, ecosystem DREAM etc.);

- Ensure that the results of the assessment can be recognized and utilised by other commonly used GIS systems;

- Ensure building data can be enhanced and extended with additional information by stakeholders within the time;Implement a mechanism to maintain the integrity and accuracy of the data throughout the assessment (e.g. edit building information).

This task focuses on ensuring the platform's capabilities for feature extension and efficiency enhancements to handle various operational demands in future. This include the following criteria:

- Maintain the consistency of assessments across different data sets and time periods to ensure reliability;

- Implement objective assessment criteria to minimize subjective bias and errors in the evaluation process;Make sure GIS data and tools developed or used during the project will remain available after its completion;

- Ensure the system is scalable to handle a growing amount of data, supporting increasing volumes of imagery, assessment results, and enriched data;

- Implement efficient and reliable data storage solutions to securely store all collected and processed data;

- Ensure that changes in assessment methodologies or data processing techniques can be seamlessly integrated and applied to existing data sets;

- Enable concurrent use of the data by different users, ensuring that multiple users can access, analyse, and interact with the data simultaneously without performance degradation.

In parallel with the damage evaluation, documentation of the most important technical steps, a consideration of the expected margin of error, and instructions on how to use the data shall be prepared.

The scope of the documentation must comply with the usual standards of the industry. Information about technical secrets or critical technologies does not have to be documented.

Anticipated number of expert days for completion:  Team leader – 26 FKT; Key expert 1 – 28 FKT; Key expert 2 – 33 FKT.

Task 3. Delivery of team trainings. Guidance and monitoring of continuing damage assessment activities conducted by project staff and project partners

Task 2.2.3.1. Trainings conducted;

Task 2.2.3.2. Technical support measures finalized

Training for the use of the evaluations and the image material as well as the generation of own reports will be carried out by the contractor in the scope of 15 working days of online training for 5 project employees over a period of 2 months. Each working day consist of 8 working hours.

In parallel to the execution of the trainings and during the follow-up of the damage assessments by project staff and project partners, the continuous validation or correction of obtained damage data is carried out. In the event of errors and anomalies in the generation of results, corrective action is taken, and appropriate follow-up training (online) is provided.

Anticipated number of expert days for completion:  Team leader – 19 FKT; Key expert 1 – 17 FKT; Key expert 2 – 15 FKT.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| Task 1. Identification and acquisition of suitable image material and GIS-Data, acquisition / renting of required technical resources |  |
| Kick-off meeting, meeting minutes, technical report of performed works / Task 2.2.1.1. Project group participants identification; Task 2.2.2.2. Satellite images, are available, and quality is assessed for 290 sq.km.; Task 2.2.1.3. Required technical resources specified and requested (server computing power) Task 2.2.1.4. Required technical resources specified and requested (server cloud storage) | CW 46 / 2024, Contractor, Cities representatives |
| Task 2. Evaluation of satellite imagery and assessment/classification of damage. Data storage and data availability ensured for all stakeholders. Data representation and visualisation. Data enrichment and platform integrability. Capabilities for technical evolution. Preparation of documentation/training materials |  |
| Task 2.2.2.1. Required technical resources specified and requested (15 % of required server cloud storage is available) Task 2.2.2.2. Damage assessment finalized; Task 2.2.2.3. Data storage and data availability ensured for all stakeholders | CW 06 / 2025, Contractor |
| Task 2.2.2.4. Project results are uploaded to the urban cadastre or other digital tool, or transferred to the responsible representatives of the executive committees of the city councils; Task 2.2.2.5. Documentation of the project results finalized and user guide preparation | CW 13 / 2025, Contractor |
| Task 3. Delivery of team trainings Guidance and monitoring of continuing damage assessment activities conducted by project staff and project partners |  |
| Task 2.2.3.1. Trainings conducted; Task 2.2.3.2. Technical support measures finalized | CW 18 / 2025, Contractor |

The contract duration is from 08.11.2024 till 30.05.2025.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| 2.2.1: Task 1. Identification and acquisition of suitable image material and GIS-Data, acquisition / renting of technical resources |  |  |
| Kick-off meeting, meeting minutes, technical report of performed works Task 2.2.1.1. Project group participants identification; Task 2.2.2.2. Satellite images, are available, and quality is assessed for 290 sq.km.; Task 2.2.1.3. Required technical resources specified and requested (server computing power) Task 2.2.1.4. Required technical resources specified and requested (85 % of required server cloud storage is available) | Submission of the report of the performed works by e-mail. The report should be submitted in two languages - English and Ukrainian (tabular form), in pdf format, up to 10 A4 pages, portrait orientation, with relevant illustrations | CW 46 / 2024 |
| 2.2.2. Task 2. Evaluation of satellite imagery and assessment/classification of damage. Data storage and data availability ensured for all stakeholders. Data representation and visualisation. Data enrichment and platform integrability. Capabilities for technical evolution. Preparation of documentation/training materials |  |  |
| Technical report of performed works and demo presentation Task 2.2.2.1. Required technical resources specified and requested (15 % of required server cloud storage is available) Task 2.2.2.2. Damage assessment finalized; Task 2.2.2.3. Data storage and data availability ensured for all stakeholders | Submission of the report of the performed works and demo presentation by e-mail. The report should be submitted in two languages - English and Ukrainian (tabular form), in pdf format, up to 10 A4 pages, portrait orientation, with relevant illustrations. The Demo presentation must be provided (using filetransfer.giz.de) in video format up to 20 minutes long and conducted at the meeting with SUR | CW 06 / 2025 |
| technical report of performed works and User guide Task 2.2.2.4. Project results are uploaded to the urban cadastre or other digital tool, or transferred to the responsible representatives of the executive committees of the city councils; Task 2.2.2.5. Documentation of the project results finalized and user guide preparation | Submission of the report of the performed works and the User guide by e-mail. The report should be submitted in two languages - English and Ukrainian (tabular form), in pdf format, up to 10 A4 pages, portrait orientation, with relevant illustrations. The User guide should be submitted in two languages - English and Ukrainian (tabular form), in pdf format, up to 25 A4 pages, portrait orientation, with relevant illustrations | CW 13 / 2025 |
| 2.2.3. Task 3. Delivery of team trainings. Guidance and monitoring of continuing damage assessment activities conducted by project staff and project partners |  |  |
| Final technical report of performed works / Task 2.2.3.1. Trainings conducted; Task 2.2.3.2. Technical support measures finalized | Submission of the final report of the performed works by e-mail. The report should be submitted in two languages - English and Ukrainian (tabular form), in pdf format, up to 10 A4 pages, portrait orientation, with relevant with relevant photos / illustrations, presentation of the results of damage assessment to the executive committees of the Balakliya, Kupiansk, Lozova, Merefa, Chuhuiv, Chornomorsk City Councils and SUR The Contractor should send the scanned copies of confirming documents (invoices and other if available) of payments (expenditures) for Item 1 (Acquisition of satellite images for specified locations 290 km2 with 0.19-0.49 m/px resolution), Item 2 (Server computing power), Item 3 (Server cloud storage) by e-mail. | CW 18 / 2025 |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided.

## Project management of the contractor (1.6)

Details about backstopping The tenderer is required to describe its backstopping concept (1.6.3). The following services are part of the standard backstopping package, which (like ancillary personnel costs) must be factored into the fee schedules of the staff listed in the tender in accordance with Section 3.3.1 of the GIZ AVB:

- Service-delivery control

- Managing adaptations to changing conditions

- Ensuring the flow of information between the tenderer and GIZ

- Assuming personnel responsibility for the contractor’s experts

- Process-oriented steering for implementation of the commission

- Securing the administrative conclusion of the project

4. Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

## Team leader

Tasks of the team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local and international short-term experts

- Regular reporting in accordance with deadlines

Qualifications of the team leader

- Education/training (2.1.1): 10 points for master degree in Computer Science or any other relevant technical field; 0 points - lower level of education or education in a non-technical field;

- Language (2.1.2): 10 points for B2-level language proficiency in English; 5 points for B1 level language proficiency in English, less then B1 - 0 points;

- General professional experience (2.1.3): 10 points for more than 15 years of professional experience in the IT/GIS sector; 5 points for 10-15 years of professional experience in the IT/GIS sector; 0 points - irrelevant experience or less than 10 years of professional experience in the IT/GIS sector;

- Specific professional experience (2.1.4): 10 points for more than 5 years in data analytics/AI/ML; 6 points for 3-5 years in data analytics/AI/ML; 0 points - irrelevant experience or less than 3 years of experience in data analytics/AI/ML;

- Leadership/management experience (2.1.5): 10 points for more than 10 years of management/leadership experience as project team leader or manager in a company; 5 points for 5-10 years of management/leadership experience as project team leader or manager in a company; 0 points – less than 5 years of management/leadership experience as project team leader or manager in a company;

## Key expert 1

Tasks of key expert 1

- Lead the overall execution of damage assessment activities;

- Ensure the project adheres to technical standards and methodologies;

- Evaluate satellite imagery;

- Oversee damage assessment activities;

- Support and backstopping of damage assessment activities.

Qualifications of key expert 1

- Education/training (2.2.1): 10 points for master degree in Computer Science or any other relevant technical field; 0 points for lower level of education or education in a non-technical field;

- Language (2.2.2): 10 points for B1-level language proficiency in English; 5 points for A2 level language proficiency in English, less then A2 - 0 points;

- General professional experience (2.2.3): 10 points for more than 5 years of professional experience in the IT/GIS or any other relevant technical field sector; 5 points for 3-5 years of professional experience in the IT/GIS or any other relevant technical field sector; 0 points - irrelevant experience or less than 3 years of professional experience in the IT/GIS sector;

- Specific professional experience (2.2.4): 10 points for more than 5 years in computer-based/image-based pattern recognition and more than 5 years of technical support and training; 5 points for 3-5 years in computer-based/image-based pattern recognition and 3-5 years of technical support and training; 0 points - irrelevant experience or less than 3 years in computer-based/image-based pattern recognition or less than 3 years of technical support and training;

- Leadership/management experience (2.2.5): 10 points for more than 2 years of management/leadership experience as project team leader or manager in a company; 5 points for 1-2 years of management/leadership experience as project team leader or manager in a company; 0 points - less than 1 year of management/leadership experience as project team leader or manager in a company.

## Key expert 2

Tasks of key expert 2

- Provide technical assistance for the evaluation of satellite images;

- Data visualisation, data storing activities;

- Generate detailed reports based on the damage assessment execution;

- Ensure data integration into the specified GIS system;

- Support and backstopping of damage assessment activities.

Qualifications of key expert 2

- Education/training (2.3.1): 10 points for master degree in Computer Science or any other relevant technical field; 0 points for lower level of education or education in a non-technical field;

- Language (2.3.2): 10 points for B1-level language proficiency in English; 5 points for A2 level language proficiency in English, less then A2 - 0 points;

- General professional experience (2.3.3): 10 points for more than 5 years of professional experience in the IT/GIS or any other relevant technical field sector; 5 points for 3-5 years of professional experience in the IT/GIS or any other relevant technical field sector; 0 points - irrelevant experience or less than 3 years of professional experience in the IT/GIS sector;

- Specific professional experience (2.3.4): 10 points for more than 5 years in computer-based/image-based pattern recognition and more than 5 years of technical support and training; 5 points for 3-5 years in computer-based/image-based pattern recognition and 3-5 years of technical support and training; 0 points - irrelevant experience or less than 3 years in computer-based/image-based pattern recognition or less than 3 years of technical support and training.

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills;

- Initiative and flexibility;

- Communication skills;

- Socio-cultural skills;

- Efficient, partner- and client-focused working methods;

- Interdisciplinary thinking.

# Costing requirements

## Assignment of personnel and travel expenses

Travels are not foreseen by the Contract.

Specification of inputs

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| 1. Designation of TL | Expert | 1 | 100 |  |
| 2. Key Expert 1 | Expert | 1 | 100 |  |
| 3. Key expert 2 | Expert | 1 | 110 |  |
| Other costs | Unit of measurement | Quantity |  | Comments (if any) |
| 4. Item 1 - Acquisition of satellite images for specified locations 290 km2 with 0.19-0.49 m/px resolution | service | 1 |  | Reimbursement against evidence: the Contractor must provide the invoice from actual service provider, no additional costs are to be reimbursed. |
| 5. Item 2 - Server computing power | service | 1 |  | Reimbursement against evidence: the Contractor must provide the invoice from actual service provider, no additional costs are to be reimbursed. |
| 6. Item 3 - Server cloud storage | service | 1 |  | Reimbursement against evidence: the Contractor must provide the invoice from actual service provider, no additional costs are to be reimbursed. |

## There is no contractual obligations to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the commercial bid.

Anticipated payment schedule:

In consideration of service completed, the Contractor shall be paid in the following instalments:

| Instalment # | Anticipated payment date | Payment of up to % from total contract value | Deliverables and reporting |
| --- | --- | --- | --- |
| 1. Advance payment | 15.11.2024 / CW 46, 2024 | 100 % for purchase Item 1, 100 % for purchase Item 2, 85 % for purchase Item 3 for tasks 2.2.1.1, 2.2.1.2, 2.2.1.3, 2.2.1.4 performing, but not more than 40 % of contract value |  |
| 2. Interim payment | 21.02.2024 / CW 08, 2025 | 15 % for purchase Item 3 55 % FKT of Team Leader, 55 % FKT of Key expert 1, 55 % FKT of Key expert 2 | Acc. to cl. 2.2 (tasks 2.2.2.1, 2.2.2.2, 2.2.2.3), item 3 (Technical report of performed works and demo presentation) |
| 3. Interim payment | 11.04.2025 / CW 15, 2025 | 25 % FKT of Team Leader, 25 % FKT of Key expert 1, 30 % FKT of Key expert 2 | Acc. to cl. 2.2 (tasks 2.2.2.4, 2.2.2.5) (technical report of performed works and User) |
| 4. Final payment | 16.05.2025 / CW 20, 2025 | 20 % FKT of Team Leader), 20 % FKT of Key expert 1, 15 % FKT of Key expert 2 | Acc. to cl. 2.2 (tasks 2.2.3.1, 2.2.3.2) (Final technical report of performed works) |

  - Financial proposal

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, incl. VAT.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid the advance payment in the amount of 40% of the contract amount, all further payments are post payment upon performance in the agreed instalments and presentation of invoices for the procurement of items 1, 2, 3;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the payments except advance payment shall be done exclusively for the actually performed works/services (“up to”), on the ground of reports and invoices for items 1, 2, 3 accepted by GIZ;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done on the ground of the scanned invoices and acts of acceptance submitted in digital form within 15 days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment.

The Contractor must procure the satellite images in accordance with the requirements specified in Chapter 2 of this ToR, pay for server cloud storage, server computing power and provide scanned copies of confirming documents (invoices and other if available) for these expenditures to the e-mail of the GIZ representative.

  - Requirements to the submission of the financial reporting documents

- Invoices, acts of acceptance and timesheets, etc. shall be scanned as one PDF document (up to 4 mb) and send as an attachment to the e-mail of the GIZ Project Representatives (the e-mail shall be provided additionally) together with other financial supporting documents as and if stipulated by the Contract; the technical documents (reporting/ deliverables) can be submitted either in the same or in a separate e-mail;

- The e-mail body/ text from the Contractor should also contain the following:

- List of the attached documents incl. title of the document, number, date of issue, amount UAH;

- Confirmation, that the services/ works/ goods specified in the attached documents were provided/ delivered/ supplied in full;

- Full name, position, contact details, full name of the organization.

- Confirmation, that the original documents (invoices, 2 copies of acts of acceptance, other financial supporting documents) will be kept by the Contractor and submitted later as soon as the security situation permits upon the request of GIZ. The deadline and the address for the delivery of documents will be agreed between GIZ and the Contractor via e-mail.

- Each invoice and act of acceptance shall contain the Project Number and the contract number.

- By submitting the Invoice the Contractor should indicate (in the invoice or in the e-mail) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

Timesheet standard template can be found here https://www.giz.de/en/worldwide/63065.html

- Other Provisions

  - General

The Contract will be signed by the Parties as a soft copy version by sending to each other by electronic means signed and scanned copies of the Contract and annexes. Such Contract shall have full legal force as the hard copies of it. The hard copies will be submitted as soon as the security situation in Ukraine stabilizes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine published on the link  Закупівлі - giz.de (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor: _________

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, a citizen of the Russian Federation, except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation.

GIZ reserves the right to verify this information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- CVs of all experts with relevant work experience, qualifications (education, certificates).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English.

The complete technical bid must not exceed 25 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 5 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English.

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise, the bid will be disqualified.

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Commercial bid must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

    - Documents for tenderer’s eligibility confirmation

| The tenderer is obliged to conform to the following eligibility requirements: | The tenderer must provide the following document to confirm the compliance with eligibility requirements: |
| --- | --- |
| Average annual turnover for the last financial year (2023) is at least 1,000,000.00 UAH | Scan copy of turnover list |
| Average number of permanent employees for the last year (2023) (at least 5 employees) | Scan copy of staff list |
| Experience in implementing projects in the field of destruction and damage assessment (in 2020-2024 years) | At least 1 recommendation letter or letter of appropriation regarding successful completion of works related to damage assessment or letter of cooperation in the field of damage assessment |

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU;

- not be in the process of termination;

- not be registered on uncontrolled territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, a citizen of the Russian Federation, except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation.

GIZ reserves the right to verify this information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.