| ENTER THE TITLE OF THE SERVICE HERE B-FIT (Women in Apiculture) | Project number/ cost centre: 19.4933.8-005.00 |
| --- | --- |

0.	List of abbreviations	2

1.	Context	3

2.	Concept	6

Technical-methodological concept	6

Project management of the contractor (1.6)	7

3.	Personnel concept	7

Team leader	7

Short-term expert pool with minimum 4, maximum 5 members	8

4.	Costing requirements	9

Assignment of personnel and travel expenses	9

Sustainability aspects for travel	9

Workshops and training	10

5.	Inputs of GIZ or other actors	10

6.	Requirements on the format of the tender	11

7.	Annexes	11

# List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General Terms and Conditions of Contract for supplying services and work

FBO	Farmer Based Organizations

FK	Expert

FKT	Expert days

GHS	Ghana Cedis

HACCP	Hazard Analysis Critical Control Points

KZFK	Short-term expert

OHS	Occupational Health and Safety

SMEs	Small and mediums Size Enterprises

ToRs	Terms of reference

# Context

Introduction

The following section explains how the Terms of Reference fit into the context of the project and country including a brief description of the beneficiaries.

The project is part of BMZ's Special Initiative “Decent Work for a Just Transition” under the brand Invest for Jobs, which is being implemented in eight African countries. The core objective of Invest for Jobs is to create decent jobs and improve working conditions. The project has three main outs and as given blow.

- Output 1 Business/Investment: Conditions have improved for investments by African and European enterprises.

- Output 2 Ghanaian SME: The capacities of small and medium-sized enterprises with growth potential have improved.

- Output 3 Cluster Focus: The business ecosystem has been strengthened in selected sectors and locations.

The aim of the bilateral GIZ project of the Special Initiative “Decent Work for a Just Transition” in Ghana is to promote the growth of companies that will generate employment. To this end, measures are being implemented to improve the conditions for investments by European companies in Ghana, to increase the capacity of Ghanaian SMEs and to improve the entrepreneurial ecosystem for the processing of agricultural products and in the automotive sector.

These Terms of Reference relate to Output 2 and the contractor is expected to contribute to achieving the objectives specified for that output. Please see Section 2 for more

Problem Analysis

Apiculture in Ghana

Apiculture, or beekeeping, has a rich history in Ghana, deeply intertwined with the country's cultural and agricultural practices. Traditionally, it was practised on a small scale using indigenous methods such as hollowing out tree trunks to create hives.

Over time, this evolved with the introduction of modern beekeeping techniques and equipment, significantly enhancing honey production. Ghana’s climate, characterised by its tropical weather and diverse flora, is highly conducive to apiculture. Vast forested areas and savannah regions provide a rich and varied source of nectar and pollen for bees, enabling honey production in Ghana to cater not only to domestic consumption but also to hold potential for export, contributing to the national economy.

Apiculture has the potential to significantly contribute to Ghana's economy through proper management and investment, generating income for rural households, reducing poverty, and creating employment opportunities. Bees play a crucial role in pollination, essential for the productivity of various crops, enhancing agricultural yields and promoting food security. Sustainable beekeeping practices aid in the conservation of biodiversity, as bees are vital for maintaining the balance of ecosystems, and their preservation helps protect various plant species. Ghanaian honey, known for its high quality, presents an opportunity to tap into international markets, increasing foreign exchange earnings.

However, the apiculture industry in Ghana faces constraints such as the widespread use of pesticides and weedicides, which pose a significant threat to bee populations, leading to colony collapse and reduced honey production. Many beekeepers rely on traditional methods due to limited access to modern beekeeping equipment and techniques, which hampers productivity, and the quality of honey produced. There is also a general lack of knowledge and expertise in modern apiculture practices among beekeepers, with inadequate training programs and extension services limiting growth potential. Changing weather patterns and deforestation adversely affect bee habitats, with unpredictable weather conditions disrupting nectar flow and bee foraging behaviour, impacting honey production. Poor infrastructure and limited access to markets constrain beekeepers' ability to sell their products at competitive prices, affecting the profitability and sustainability of their operations.

Northern Ghana confronts complex socio-economic hardships stemming from a confluence of factors. Encompassing Northern, Savanna, Upper East, North-East, and Upper West Regions, Northern Ghana grapples with high illiteracy, elevated child pregnancy rates, increased school dropouts, and pervasive poverty.

Central to these challenges is the region's reliance on a single annual harvest, leading to a mere four to five months of agricultural activity followed by a prolonged dry season. This cycle significantly curtails economic opportunities, perpetuating poverty and unemployment. It disrupts education, contributing to heightened dropout rates and limiting avenues for skill development. Moreover, health and social issues, notably child pregnancies and restricted access to healthcare during the prolonged dry season, compound the region's struggles.

The repercussions extend beyond the Northern territories, impacting the socio-economic stability of adjacent regions. These challenges collectively undermine sustainable livelihoods, hinder socio-economic growth, and perpetuate vulnerability across Northern Ghana.

Addressing these interwoven challenges demands holistic strategies that foster year-round economic activities, ensure consistent access to education, enhance healthcare provisions, and promote sustainable livelihoods. Collaborative and targeted interventions are essential to break the cyclical nature of these issues and pave the way for enduring socio-economic development in Northern Ghana. Hence, the need for this collaboration aimed at creating sustainable jobs through apiculture production.

2.0 Tasks to be performed by the contractor

In this assignment, GIZ is seeking to hire the services of competent consultancy firm to train and build the capacity of 200 women beekeepers in the Upper East and Upper West Regions.  The beneficiaries of the project would be put into clusters and given additional training in alternative livelihood training.

GIZ-Ghana seeks to engage the services of a consultancy firm with the requisite technical and professional know-how in building the strength of beekeepers and cooperatives in the upper east and Upper West Region.

The contractor is responsible for providing the following services:

- Facilitate the selection of 200 project beneficiaries (Set pre-determined selection criteria).

- Collect baseline date from all project beneficiaries and provide a short report to GIZ

- Facilitate the formation, strengthening and formalization of apiculture clusters/FBOs

- Review and adapt training manuals (Business management and entrepreneurship, food safety, OSH, Organic and Social protection)

- Business Management and Entrepreneurial training.

- Occupational health and safety training in honey production and processing

- Food safety, organic certification and HACCP training for 200 project beneficiaries,

- Promotion of social protection measures (awareness creation and registration)

- Facilitate market access (Facilitate market linkage, training in basic negotiation skills, market prospecting).

- Develop a comprehensive sustainability plan for the project.

In addition to the reports required by GIZ in accordance with the AVB, the contractor submits the following reports:

  - Inception report

  - Contributions to reports to GIZ’s commissioning party

  - Brief quarterly or half-yearly reports on the implementation status of the project (5-7 pages)

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Deadline/place/person responsible |
| --- | --- |
| Brief Inception Report -presenting approach to tasks. -Identifying what resources will or may be required. | 10.10.2024 |
| Set eligibility and selection criteria for project beneficiaries to be shared by email to GIZ. | 17.10.2024 |
| Work with the partner for the selection and mobilization of project beneficiaries. | 24.11.2024 |
| Review and adapt training manuals and materials on business management and entrepreneurial training, food safety, organic, OSH, social protection measures. | 20.01.2025 |
| Baseline data collection | 12.02.2025 |
| Provides training in, group dynamics, communication, reporting and gross margin analysis training. | 20.01.2025 |
| Business Management and Entrepreneurial training. | 27.02.2025 |
| Provide technical training in food safety, Organic certification and HACCP. | 03.03.2025 |
| Provide training in OSH and Social Protection Measures. | 10.03.2025 |
| Facilitate the drafting and adaption of group constitution and registration of cooperatives with the department of cooperatives. | 20.03.2025 |
| Provide a draft report on the project | 16.04.2025 |
| Develop a sustainability with for the project | 16.04.2025 |
| Submit a draft news article to GIZ for review and publication | 16.05.2025 |
| Submit final project report | 30.05.2025 |

Period of assignment: from 30.09.2024 until 30.05.2025.

NB: Please note that any tenderer who wins the bid would submit the following:

- Tax Clearance Certificate

- SSNNIT Clearance Certificate

- Business Registration Certificate

- VAT Registration Certificate

# 3. Concept

In the tender, the tenderer is required to show how the objectives defined in Chapter 3 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 3 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 3 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation.

## Project management of the contractor (1.6)

The tenderer is required to explain its approach for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the tender; the plan includes information on assignment dates (duration and expert days) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

# 4. Personnel concept

The tenderer is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 7.0), the range of tasks involved and the required qualifications.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team leader

Tasks of the team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local short-term experts

- Regular reporting in accordance with deadlines

Qualifications of the team leader

- Education/training (2.1.1): university degree (Master) in Agriculture, Agricultural Economics, Agribusiness, Economics, Agricultural Extension, Total Quality Management and other related programmes

- Language (2.1.2): C1-level language proficiency in English, B2-level language proficiency in 2 local languages (e.g., Twi, Fante, Ahanta and Nzema)

- General professional experience (2.1.3): 12 years of professional experience in the field of Agriculture and Project Management

- Specific professional experience (2.1.4): 8 years of relevant professional experience in project monitoring and coaching

- Leadership/management experience (2.1.5): 5 years of management/leadership experience as project team leader or manager in a company

- Regional experience (2.1.6): 7 years of experience in projects in a West African country (region), of which 5 years in Ghana

- Development cooperation (DC) experience (2.1.7): 3 years of experience in DC projects

## Short-term expert pool with minimum 4, maximum 5 members

For the technical assessment, an average of the qualifications of all specified members of the expert pool is calculated. Please send a CV for each pool member (see below Chapter 7 Requirements on the format of the bid) for the assessment.

Tasks of the short-term expert pool

- Participation in the inception meeting and other meetings with GIZ

- Contributes to defining pre-determine set selection criteria and the design, developing, delivering training programmes.

- Work with the team leader to develop training manuals

- Support the team leader with training and coaching of project beneficiaries at the production site

- Support with the design and organization of training workshops

- Attend and participate in team meetings and TOT training events

- Work cohesively with the team leader and other members to achieve project milestones.

- Complete administrative tasks, collect the necessary receipt and invoices to ensure proper adequate funds retirement

- Collect relevant M&E and knowledge management data to be shared with GIZ

- Contributions to documentation of activities with photos, short videos, articles to feed GIZ communication activities

- Support the team leader with regular reporting in accordance with deadlines

Qualifications of the short-term expert pool

- Education/training (2.6.1): 4 experts with university qualification (Master) in Agriculture, Agribusiness, Agricultural Economics, Agricultural Extension, Food Science, Accounting, Total Quality Management and other related fields.

- Language (2.6.2): C1-level language proficiency in English, B2-level language proficiency in 2 local languages (e.g., Twi, Fante, Ahanta and Nzema)

- General professional experience (2.6.3): 4 experts with 5 years of professional experience in the agribusiness sector and promotion of non-traditional agriculture

- Specific professional experience (2.6.4): 3 experts with 5 years of professional experience in agribusiness SME coaching and promotion of OHS and social protection measures. 1 expert with 3 years of professional experience in accounting and finance

- Regional experience (2.6.5): 4 experts with 5 years of experience in agribusiness project management in West African countries, 4 experts with 3 years of experience in Ghana

- Development cooperation (DC) experience (2.6.6): 2 experts with 3 years of experience in DC

- Other professional experience (2.6.7): 3 experts with 5 years’ experience in food safety and quality management

The tenderer must provide a clear overview of all proposed short-term experts and their individual qualifications.

# Costing requirements

## Assignment of personnel and travel expenses

Per-diem and overnight accommodation allowances are reimbursed as a lump sum up to the maximum amounts permissible under tax law for each country as set out in the country table in the circular from the German Federal Ministry of Finance on travel expense remuneration (downloadable at https://www.bundesfinanzministerium.de).

Accommodation costs which exceed this up to a reasonable amount and the cost of flights and other main forms of transport can be reimbursed against evidence

## Sustainability aspects for travel

GIZ would like to reduce greenhouse gas emissions (CO2 emissions) caused by travel. When preparing your tender, please incorporate options for reducing emissions, such as selecting the lowest-emission booking class (economy) and using means of transport, airlines and flight routes with a higher CO2 efficiency. For short distances, travel by train (second class) or e-mobility should be the preferred option.

If they cannot be avoided, CO2 emissions caused by air travel should be offset. GIZ specifies a budget for this, through which the carbon offsets can be settled against evidence.

There are many different providers in the market for emissions certificates, and they have different climate impact ambitions. The Development and Climate Alliance (German only) has published a list of standards (German only). GIZ recommends using the standards specified there.

Specification of inputs

| Fee days | Number of experts | Number of days per expert | Total | Comments |
| --- | --- | --- | --- | --- |
| Team Leader | 1 | 75 | 75 |  |
| Short-term expert pool | 4 | 61 | 244 |  |
| Travel expenses | Number | Price (GHS) | Total (GHS) | Comments |
| Per-diem allowance |  |  |  | Lump-sum |
| Overnight allowance |  |  |  | Lump-sum |
| Transport | Number | Price (GHS) | Total (GHS) | Comments |
| Travel Expenses |  |  |  |  |
| Other costs | Number | Price (GHS) | Total (GHS) | Comments |
| Workshops |  |  |  | The budget contains the following costs: Training Materials/ conference packages/room. Against evidence |
| Other costs |  |  |  | The budget contains the following costs: financial assistance for the registration of cooperative with department of cooperative. Against evidence |

## Workshops and training

Please describe in your concept how you implement GIZ’s minimum standards for sustainable event management (see annexes to the terms of reference).

- The contractor implements the following workshops:

- Four training workshops would be organized with a minimum of participants of 40 and maximum of 50 participants.

- Training would be conducted using the farmer business school model.

- Training duration would be five days per workshop including 1-day onsite training.

- Training modules would encompass, Business management and entrepreneurship, OHS, food safety, HACCP, Access to market, group formation and strengthening, packaging and branding, social protection measures.

- The selected consultant would work with the partner to select 200 beneficiaries for training.

- The tenderer is required to book and pay the venues / conference packages

- Travel expenses of the participants (SMEs) will be covered by themselves

P+R Rule 566 on sustainable event management.

Please describe in your concept how you implement GIZ’s minimum standards for sustainable event management (see annexes to the terms of reference).

The contractor implements the following workshops/study trips/training courses:

- Four days classroom training

- 1-day onsite training

# Inputs of GIZ or other actors

GIZ and/or other actors are expected to make the following available:

- Organize regular online jour fixe with the partner to discuss the progress work and the way forward

- The partner would work with the consultant to select the venue for the workshop

- GIZ will be work with the partner to publish at least one article on the national media

- GIZ will provide funding for the key activities in the TOR

# Requirements on the format of the tender

The structure of the tender must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The tender must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete tender must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application. The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs can also be submitted in English (language).

Please calculate your financial tender based exactly on the parameters specified in Chapter 5 Quantitative requirements. The contractor is not contractually entitled to use up the days, trips, workshops or budgets in full. The number of days, trips and workshops and the budgets will be contractually agreed as maximum limits. The specifications for pricing are defined in the price schedule.

# Annexes

Minimum standards for sustainable event management at GIZ