| Snails for Nutrition, Agriculture and Labour/Empowering Women Entrepreneurs in Greenhouse Snail Production | Project number/ cost centre: 19.4933.8-005.00 |
| --- | --- |

0.	List of abbreviations	2

1.	Context	3

2.	Tasks to be performed by the contractor	4

3.	Concept	5

Technical-methodological concept	5

Project management of the contractor (1.6)	6

4.	Personnel concept	6

Team leader	6

Short-term expert pool with minimum 4, maximum 5 members	7

5.	Costing requirements	8

Sustainability aspects for travel	8

Workshops and training	9

6.	Inputs of GIZ or other actors	9

7.	Requirements on the format of the tender	10

8.	Annexes	10

# List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General Terms and Conditions of Contract for supplying services and work

FBO	Farmer Based Organizations

FK	Expert

FKT	Expert days

GHS	Ghana Cedis

HACCP	Hazard Analysis Critical Control Points

KZFK	Short-term expert

OHS	Occupational Health and Safety

SMEs	Small and mediums Size Enterprises

ToRs	Terms of reference

# Context

Introduction

The following section explains how the Terms of Reference fit into the context of the project and country including a brief description of the beneficiaries.

The project is part of BMZ's Special Initiative “Decent Work for a Just Transition” under the brand Invest for Jobs, which is being implemented in eight African countries. The core objective of Invest for Jobs is to create decent jobs and improve working conditions. The project has three main outs and as given blow.

- Output 1 Business/Investment: Conditions have improved for investments by African and European enterprises.

- Output 2 Ghanaian SME: The capacities of small and medium-sized enterprises with growth potential have improved.

- Output 3 Cluster Focus: The business ecosystem has been strengthened in selected sectors and locations.

The aim of the bilateral GIZ project of the Special Initiative “Decent Work for a Just Transition” in Ghana is to promote the growth of companies that will generate employment. To this end, measures are being implemented to improve the conditions for investments by European companies in Ghana, to increase the capacity of Ghanaian SMEs and to improve the entrepreneurial ecosystem for the processing of agricultural products and in the automotive sector.

These Terms of Reference relate to Output 2 and the contractor is expected to contribute to achieving the objectives specified for that output. Please see Section 2 for more information.

Problem Analysis

In Ghana, the state of employment, income levels, and working conditions for women and youth demand focused attention in terms of development policy. While there has been some progress in recent years, persistent gender disparities continue to exist, particularly in economic empowerment and women's access to entrepreneurial opportunities. The issue of youth unemployment / underemployment is also escalating, necessitating immediate action.

Women, especially those in rural areas, face limited employment opportunities and often find themselves confined to traditional roles as homemakers. This perpetuates economic dependency and restricts their ability to make meaningful contributions to their family's well-being. The depth of opportunities for women to engage in income-generating activities poses a significant obstacle to poverty reduction efforts and sustainable economic development.

Additionally, many educated youths, unable to pursue higher education, find themselves unemployed or underemployed, contributing to the issue of youth unemployment. Moreover, Ghana's agriculture sector, including snail farming, holds substantial job creation and income generation potential. In Ghana, the state of employment, income levels, and working conditions for women and youth demands attention from a development-policy perspective.

Literature has also shown that snail production also known as heliciculture has the potential to create sustainable employment opportunities across the different segments of the population, contributing to local economic development, poverty reduction, and improving livelihoods in both rural and urban areas. Effective support through training, access to market, infrastructure development can further enhance the role of snail farming in job creation within communities, hence this intervention.

# Tasks to be performed by the contractor

In this assignment, GIZ seeks to train and build the capacity of 180 snail farmers made up of 60 women entrepreneurs and 120 farm hands in greenhouse snail production techniques and put them into snail production cooperatives. The beneficiaries of the project would be trained in greenhouse snail production, and they would be allotted with greenhouses for snail production and processing.

GIZ Ghana seeks to engage the services of a consultancy firm with the requisite technical and professional know-how in building the strength of snail farmers and cooperatives in the Mpohor District.

The contractor is responsible for providing the following services:

- Facilitate the selection of project beneficiaries (Set predetermined criteria for selecting project beneficiaries)

- Facilitate the formation, strengthening and formalization of snail production clusters/FBOs

- TOT training for 60 women entrepreneurs and capacity building for 120 farm hands.

- Review and adapt training manuals (business management and entrepreneurship, food safety, organic certification, occupational health and safety and social protection)

- Business management and entrepreneurial training to 160 snail farmers.

- Occupational health and safety Training (OHS) in snail production and processing

- Conduct training for 180 snail farmers on food safety, organic certification and HACCP, promotion of social protection measures.

- Access to market (facilitate market linkage, negotiations and capacity building on market prospecting, branding and packaging)

- Facilitate the registration of interested farmers unto social protection schemes, such as health insurance and pension schemes.

In addition to the reports required by GIZ in accordance with the AVB, the contractor submits the following reports:

  - Inception report

  - Contributions to reports to GIZ’s commissioning party

  - Brief quarterly reports on the implementation status of the project (5-7 pages)

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Deadline/place/person responsible |
| --- | --- |
| Brief Inception Report - presenting approach to tasks - identifying what resources will or may be required | 03.10.2024 |
| Set eligibility and selection criteria for project beneficiaries to be shared by email with GIZ | 10.10.2024 |
| Work with the partner on the selection and mobilization of project beneficiaries | 17.10.2024 |
| Review and adapt training manuals and materials on business management and entrepreneurial training, food safety, organic certification, OHS, social protection, HACCP | 30.10.2024 |
| Provide training in group dynamics, communication, reporting and gross margin analysis | 20.01.2025 |
| Business Management and Entrepreneurial training | 27.01.2025 |
| Provide technical training in food safety and organic certification and HACCP | 10.02.2025 |
| Provide training in OHS and promote social protection among project beneficiaries | 17.02.2025 |
| Access to market (facilitate market linkage, negotiations and capacity building on market prospecting, branding and packaging) | 24.02.2025 |
| Facilitate the drafting and adaption of group constitution and registration of cooperatives with the department of cooperatives | 31.03.2025 |
| Provide a draft report on the project | 17.04.2025 |
| Submit a draft news article to GIZ for review and publication | 16.05.2025 |
| Submit final project report | 30.05.2025 |

Period of assignment: from 30.09.2024 until 30.05.2025.

NB: Please note that any tenderer who wins the bid would submit the following:

- Tax Clearance Certificate

- SSNNIT Clearance Certificate

- Business Registration Certificate

- VAT Registration Certificate

# Concept

In the tender, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation.

## Project management of the contractor (1.6)

The tenderer is required to explain its approach for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the tender; the plan includes information on assignment dates (duration and expert days) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

# Personnel concept

The tenderer is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 7), the range of tasks involved and the required qualifications.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team leader

Tasks of the team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local short-term experts

- Regular reporting in accordance with deadlines

Qualifications of the team leader

- Education/training (2.1.1): university degree (Master) in Agriculture, Agricultural Economics, Agribusiness, Economics, Agricultural Extension, Total Quality Management and other related programmes

- Language (2.1.2): C1-level language proficiency in English, B2-level language proficiency in 2 local languages (e.g., Twi, Fante, Ahanta and Nzema)

- General professional experience (2.1.3): 12 years of professional experience in the field of Agriculture and Project Management

- Specific professional experience (2.1.4): 8 years of relevant professional experience in project monitoring and coaching

- Leadership/management experience (2.1.5): 5 years of management/leadership experience as project team leader or manager in a company

- Regional experience (2.1.6): 7 years of experience in projects in a West African country (region), of which 5 years in Ghana

- Development cooperation (DC) experience (2.1.7): 3 years of experience in DC projects

## Short-term expert pool with minimum 4, maximum 5 members

For the technical assessment, an average of the qualifications of all specified members of the expert pool is calculated. Please send a CV for each pool member (see below Chapter 7 Requirements on the format of the bid) for the assessment.

Tasks of the short-term expert pool

- Participation in the inception meeting and other meetings with GIZ

- Contributes to defining pre-determine set selection criteria and the design, developing, delivering training programmes.

- Work with the team leader to develop training manuals

- Support the team leader with training and coaching of project beneficiaries at the production site

- Support with the design and organization of training workshops

- Attend and participate in team meetings and TOT training events

- Work cohesively with the team leader and other members to achieve project milestones.

- Complete administrative tasks, collect the necessary receipt and invoices to ensure proper adequate funds retirement

- Collect relevant M&E and knowledge management data to be shared with GIZ

- Contributions to documentation of activities with photos, short videos, articles to feed GIZ communication activities

- Support the team leader with regular reporting in accordance with deadlines

Qualifications of the short-term expert pool

- Education/training (2.6.1): 4 experts with university qualification (Master) in Agriculture, Agribusiness, Agricultural Economics, Agricultural Extension, Food Science, Accounting, Total Quality Management and other related fields.

- Language (2.6.2): C1-level language proficiency in English, B2-level language proficiency in 2 local languages (e.g., Twi, Fante, Ahanta and Nzema)

- General professional experience (2.6.3): 4 experts with 5 years of professional experience in the agribusiness sector and promotion of non-traditional agriculture

- Specific professional experience (2.6.4): 3 experts with 5 years of professional experience in agribusiness SME coaching and promotion of OHS and social protection measures. 1 expert with 3 years of professional experience in accounting and finance

- Regional experience (2.6.5): 4 experts with 5 years of experience in agribusiness project management in West African countries, 4 experts with 3 years of experience in Ghana

- Development cooperation (DC) experience (2.6.6): 2 experts with 3 years of experience in DC

- Other professional experience (2.6.7): 3 experts with 5 years’ experience in food safety and quality management

The tenderer must provide a clear overview of all proposed short-term experts and their individual qualifications.

# Costing requirements

## Sustainability aspects for travel

GIZ would like to reduce greenhouse gas emissions (CO2 emissions) caused by travel. When preparing your tender, please incorporate options for reducing emissions, such as selecting the lowest-emission booking class (economy) and using means of transport, airlines and flight routes with a higher CO2 efficiency. For short distances, travel by train (second class) or e-mobility should be the preferred option.

If they cannot be avoided, CO2 emissions caused by air travel should be offset. GIZ specifies a budget for this, through which the carbon offsets can be settled against evidence.

There are many different providers in the market for emissions certificates, and they have different climate impact ambitions. The Development and Climate Alliance (German only) has published a list of standards (German only). GIZ recommends using the standards specified there.

Specification of inputs:

| Fee days | Number of experts | Number of days per expert | Total | Comments |
| --- | --- | --- | --- | --- |
| Team leader | 1 | 65 | 65 |  |
| Short-term expert pool | 4 | 55 | 220 |  |
| Travel expenses | Number | Price (GHS) | Total (GHS) | Comments |
| Per-diem allowance |  |  |  | Lump-sum |
| Overnight allowance |  |  |  | Lumpsum |
| Transport | Number | Price (GHS) | Total (GHS) | Comments |
| Travel Expenses |  |  |  | Four trips per each of the five consultants |
| Other costs | Number | Price (GHS) | Total (GHS) | Comments |
| Workshops |  |  |  | The budget contains the following costs: training materials / conference packages / room. Against evidence |
| Other costs |  |  |  | The budget contains the following costs: financial assistance for the registration of cooperative with department of cooperative. Against evidence |

## Workshops and training

Please describe in your concept how you implement GIZ’s minimum standards for sustainable event management (see annexes to the terms of reference).

The contractor implements the following workshops:

- Five training workshops would be organized with a minimum of participants of 40 and maximum of 50 participants.

- Training would be conducted using the farmer business school model

- Training duration would be five days per workshop including 4-days in a classroom and 1-day onsite training

- Training modules would encompass, Business management and entrepreneurship, Occupational health and safety, food safety, HACCP, Access to market, group formation and strengthening, packaging and branding, social protection measures.

- The selected consultants would work with the partner to select 60 beneficiaries for training and the 60 beneficiaries would also bring two farm hands of their choice for the training

- The tenderer is required to book and pay the venues / conference packages

- Travel expenses of the participants (SMEs) will be covered by themselves

P+R Rule 566 on sustainable event management

Please describe in your concept how you implement GIZ’s minimum standards for sustainable event management (see annexes to the terms of reference).

# Inputs of GIZ or other actors

GIZ and/or other actors are expected to make the following available:

- Organize regular online jour fixe with the partner to discuss the progress work and the way forward

- The partner would work with the consultant to select the venue for the workshop

- GIZ will work with the partner to publish at least one article on the national media

- GIZ will provide funding for the key activities in the ToRs

# Requirements on the format of the tender

The structure of the tender must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The tender must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete tender must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application. The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs can also be submitted in English (language).

Please calculate your financial tender based exactly on the parameters specified in Chapter 5 Quantitative requirements. The contractor is not contractually entitled to use up the days, trips, workshops or budgets in full. The number of days, trips and workshops and the budgets will be contractually agreed as maximum limits. The specifications for pricing are defined in the price schedule.

# Annexes

Minimum standards for sustainable event management at GIZ