| CONSULTANCY FOR THE "SME PRODUCT CERTIFICATION PROJECT" OF THE SPECIAL INITIATIVE "DECENT WORK FOR A JUST TRANSITION" (INVEST FOR JOBS) | Project number/ cost centre: 19.4933.8-005.00 |
| --- | --- |

0.	List of abbreviations	2

1.	Context	3

2.	Tasks to be performed by the contractor	3

3.	Concept	5

Technical-methodological concept	5

Project management of the contractor (1.6)	5

4.	Personnel concept	6

Team Leader	6

Short-term expert pool with 5 members	7

5.	Costing requirements	7

Assignment of personnel and travel expenses	7

Sustainability aspects for travel	8

Workshops and training	9

6.	Inputs of GIZ or other actors	9

7.	Requirements on the format of the tender	9

8.	Annexes	10

# List of abbreviations

AVB	General Terms and Conditions of Contract for supplying services and work

FDA                     Foods and Drugs Authority

GSA                    Ghana Standards Authority

OSH                    Occupational Safety and Health

ToRs	Terms of reference

# Context

The Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH is a provider of international cooperation services for sustainable development and international education work, dedicated to building a future worth living around the world. As part of the Ghana-German cooperation, GIZ has been involved in supporting a wide range of sectors for over 30 years. As agreed between the Governments of Germany and Ghana, GIZ is boosting Ghana's potential by focusing its projects on three priority areas: Responsibility for our planet - climate and energy, Training and sustainable growth for decent jobs as well as Peaceful and inclusive societies. In addition, nearly all the projects in Ghana involve the private sector.

GIZ has been commissioned by the German Federal Ministry for Economic Cooperation and Development (BMZ) to implement the Special Initiative "Decent Work for a Just Transition", which operates under the brand ‘Invest for Jobs’. The objective is to promote job creation and growth of enterprises in Ghana. Invest for Jobs works in three areas of intervention: ‘Business & Invest’, ‘Cluster approach’ and ‘Ghanaian SME (Mittelstand)’. Under the ‘Business & Invest’, it promotes sustainable investments from German and European companies and investors; the ‘Cluster approach’ aims to increase the economic attractiveness of business locations and industries; intervenes to support industrial parks, improves export opportunities and addresses various obstacles to investment. The ‘Ghanaian SME (Mittelstand)’ promotes the SME sector, by improving the business environment and enhancing competitiveness, by promoting advisory and (innovative) financial services for SME and boosting cooperation between German and African companies.

Under its second component, Ghanaian SME (African Mittelstand), GIZ intends to implement the “SME Product Certification Project” which supports beneficiary SMEs with the certification of their products by Foods and Drugs Authority (FDA) and Ghana Standards Authority (GSA), increases their readiness for further certifications (e.g., HACCP, ISO), and provides trainings and consulting on quality management, standardization, packaging, branding, marketing, Occupational Safety and Health (OSH) and social protection. The objectives of this project are to improve access to markets for the beneficiary SMEs and to increase the trust level of consumers and buyers in terms of product quality and safety, thereby creating decent jobs and improving working conditions.

# Tasks to be performed by the contractor

The contractor is responsible for providing the following services:

- Participation in the inception meeting and preparation of inception report with further specification of the methodology to be deployed to deliver the activities

- Organisation of online application process and selection of participating SMEs:

    - 60 SMEs in three geographical clusters

- Cluster 1: Northern Ghana (Northern, Savannah, Upper West, North East, Upper East regions)

- Cluster 2: Ashanti, Ahafo, Bono and Bono East regions

- Cluster 3: Western and Central regions

    - Based on selection criteria and scoring system which have to be developed in advance, in cooperation with GIZ

    - SMEs with a focus on eco-friendly production or a proven interest in eco-friendly product and process innovation with the potential for job creation and sustainable growth are given priority

    - 50% or more of the SMEs should be women-led (women in key management positions) and / or women-owned

    - Targeted sectors are manufacturing in agro-processing, textile & fashion, and cosmetics

    - Beneficiaries must be ready to pay their travel expenses to attend the classroom trainings and to make required investments into improvements of their processes and facilities to acquire product certifications

    - Establishing contacts with business organisations and other actors to spread the call for applications

    - Final selection of SMEs will be done with the GIZ project team

- Developing methodology and contents for trainings, in-factory consulting, continuous guidance and support for the certification

- Trainings in Tamale, Kumasi, Takoradi + 2 more cities, depending on locations of selected enterprises (e.g. Sunyani, Wa). Training duration is 3 days in each location. Topics should include an introduction to GSA and FDA certification processes, quality management, standardization, packaging, branding and marketing. Session on Occupational Safety and Health (OSH) and social protection will be delivered by a GIZ expert (this is not part of the consultancy). Each SME sends 2 staff members for participation in these trainings

- In-factory consulting on the above-mentioned topics and any other topics that are relevant for the specific enterprise: each enterprise is visited at least twice by a consultant

- Continuous technical guidance and support, including online training sessions, coaching (via video call, phone and email) for the SMEs in preparation for and during the certification process as well as assistance for the payment of fees for product certification with FDA and GSA

- Coordination and facilitation of activities between SMEs and product certification bodies (GSA, GDA or any other relevant bodies)

- Documentation of activities with photos, short videos, articles to feed GIZ communication activities

- The contractor is responsible for selecting, preparing, training and steering experts assigned to perform the advisory tasks

- The contractor provides equipment and supplies (consumables) and assumes the associated operating and administrative costs

- The contractor manages costs and expenditures, accounting processes and invoicing in line with the requirements of GIZ

- The contractor reports regularly to GIZ in accordance with the current AVB of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Deadline/place/person responsible |
| --- | --- |
| Inception meeting | 18.11.2024 in Accra, GIZ office |
| Inception report | 25.11.2024 |
| Start of application process | 14.12.2024 |
| Finalization of training programs | 15.12.2024 |
| Finalization of methodology for in-factory consulting & continuous guidance and support | 15.12.2024 |
| Finalization of beneficiary selection | 15.12.2024 |
| Organization of training venues | 29.12.2024 |
| Completion of trainings | 21.02.2025 in 5 cities |
| Completion of in-factory consulting & continuous guidance and support for product certification | 17.10.2025 in the SMEs & via video call, phone and email |
| Completion of product certifications | 17.10.2025 |
| Final report | 28.10.2025 |
| Quarterly report | Quarterly |

Period of assignment: from 01.11.2024 until 31.10.2025.

# Concept

In the tender, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps.

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation.

## Project management of the contractor (1.6)

The tenderer is required to explain its approach for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the tender; the plan includes information on assignment dates (duration and expert days) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

The tenderer is required to describe its backstopping concept. The following services are part of the standard backstopping package, which (like ancillary personnel costs) must be factored into the fee schedules of the staff listed in the tender in accordance with Section 3.3.1 of the GIZ AVB:

- Service-delivery control

- Managing adaptations to changing conditions

- Ensuring the flow of information between the tenderer and GIZ

- Assuming personnel responsibility for the contractor’s experts

- Process-oriented steering for implementation of the commission

- Securing the administrative conclusion of the project

# Personnel concept

The tenderer is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 7), the range of tasks involved and the required qualifications.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team Leader

Tasks of the team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines): oversees the application process and selection, the development of training programs as well as methodology for in-factory consulting & continuous guidance and support

- Leading the inception meeting and other meetings with GIZ

- Leading the provision of trainings in 5 locations

- Provision of in-factory consulting & continuous guidance and support to the selected companies

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting short-term experts

- Documentation of activities with photos, short videos, articles with other experts to feed GIZ communication activities

- Regular reporting in accordance with deadlines

Qualifications of the team leader

- Education/training (2.1.1): university degree (Master) in Quality Management, Economics, Agribusiness, Agricultural Engineering or related fields

- Language (2.1.2): C1-level language proficiency in English, B2-level language proficiency in 2 local languages (e.g., Twi, Fante, Nzema, Dagbani)

- General professional experience (2.1.3): 8 years of professional experience in the agribusiness sector

- Specific professional experience (2.1.4): 5 years of professional experience in supporting agribusiness and textile enterprises, with a focus on quality management, standardization, product certification & marketing and packaging

- Leadership/management experience (2.1.5): 3 years of management/leadership experience as project team leader or manager in a company

- Regional experience (2.1.6): 5 years of experience in projects in West Africa, of which 3 years in projects in Ghana

- Development cooperation (DC) experience (2.1.7): 3 years of experience in DC projects

## Short-term expert pool with 5 members

For the technical assessment, an average of the qualifications of all specified members of the expert pool is calculated. Please send a CV for each pool member (see below Chapter 7 Requirements on the format of the bid) for the assessment.

Tasks of the short-term expert pool

- Participation in the inception meeting and other meetings with GIZ

- Contributions to the application process and selection, the development of training programs as well as methodology for in-factory consulting & continuous guidance and support

- Provision of trainings in 5 locations

- Provision of in-factory consulting & continuous guidance and support to the selected companies. To reduce travelling time and costs, it is expected that members are based in the regions where the companies are (Northern, Savannah, Upper West, North East, Upper East, Ashanti, Ahafo, Bono, Bono East, Western, Central)

- Regular exchange and coordination with Team Leader and all members of the expert pool

- Contributions to documentation of activities with photos, short videos, articles to feed GIZ communication activities

- Supporting the Team Leader with regular reporting in accordance with deadlines

Qualifications of the short-term expert pool

- Education/training (2.6.1): 5 experts with university qualification in Quality Management, Economics, Agribusiness, Agricultural Engineering or related fields

- Language (2.6.2): 5 experts with C1-level language proficiency in English, B2-level language proficiency in 2 local languages (e.g., Twi, Fante, Nzema, Dagbani)

- General professional experience (2.6.3): 5 experts with 5 years of professional experience in the agribusiness sector

- Specific professional experience (2.6.4): 5 experts with 3 years of professional experience in supporting agribusiness and textile enterprises, with a focus on quality management, standardization, product certification & marketing and packaging

- Regional experience (2.6.5): 5 experts with 3 years of experience in projects in West Africa, of which 2 years in projects in Ghana

- Development cooperation (DC) experience (2.6.6): 5 experts with 2 years of experience in DC

The tenderer must provide a clear overview of all proposed short-term experts and their individual qualifications.

# Costing requirements

## Assignment of personnel and travel expenses

All business travel must be agreed in advance by the officer responsible for the project.

## Sustainability aspects for travel

GIZ would like to reduce greenhouse gas emissions (CO2 emissions) caused by travel. When preparing your tender, please incorporate options for reducing emissions, such as selecting the lowest-emission booking class (economy) and using means of transport, airlines and flight routes with a higher CO2 efficiency. For short distances, travel by train (second class) or e-mobility should be the preferred option.

If they cannot be avoided, CO2 emissions caused by air travel should be offset. GIZ specifies a budget for this, through which the carbon offsets can be settled against evidence.

There are many different providers in the market for emissions certificates, and they have different climate impact ambitions. The Development and Climate Alliance (German only) has published a list of standards (German only). GIZ recommends using the standards specified there.

Specification of inputs

| Fee days | Number of experts | Number of days per expert | Total | Comments |
| --- | --- | --- | --- | --- |
| Team Leader | 1 | 65 | 65 |  |
| Short-term expert pool | 5 | 40 | 200 |  |
| Travel expenses | Number | Price (GHS) | Total (GHS) | Comments |
| Per-diem allowance |  |  |  | Lump-sum |
| Overnight allowance |  |  |  | Against evidence |
| Transport | Number | Price (GHS) | Total (GHS) | Comments |
| Travel Expenses |  |  |  |  |
| Other costs | Number | Price (GHS) | Total (GHS) | Comments |
| Workshops | 5 | 45,000 | 225,000 | The budget contains the following costs: conference rooms / conference packages. Against evidence |
| Other costs | 60 | 5,000 | 300,000 | The budget contains the following costs: financial assistance for the payment of fees for product certification with FDA and GSA. Against evidence |

## Workshops and training

Please describe in your concept how you implement GIZ’s minimum standards for sustainable event management (see annexes to the terms of reference).

The contractor implements the following workshops:

- Trainings in Tamale, Kumasi, Takoradi + 2 more cities, depending on locations of selected enterprises (e.g. Sunyani, Wa)

- Training duration is 3 days in each location

- Topics should include an introduction to GSA and FDA certification processes, quality management, standardization, packaging, branding and marketing

- Session on Occupational Safety and Health (OSH) and social protection will be delivered by a GIZ expert (this is not part of the consultancy)

- Each SME sends 2 staff members for participation in these trainings

- The tenderer is required to book and pay the venues / conference packages

- Travel expenses of the participants (SMEs) will be covered by themselves

# Inputs of GIZ or other actors

GIZ is expected to make the following available:

- Organization of regular online meetings to discuss the progress of the project

- GIZ will spread the call for application on GIZ social media handles

- GIZ will be involved in the final selection of beneficiaries

- GIZ will provide the training sessions on Occupational Safety and Health (OSH) and social protection

# Requirements on the format of the tender

The structure of the tender must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The tender must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English language.

The complete tender must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application. The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs should be submitted in English language.

Please calculate your financial tender based exactly on the parameters specified in Chapter 5 Quantitative requirements. The contractor is not contractually entitled to use up the days, trips, workshops or budgets in full. The number of days, trips and workshops and the budgets will be contractually agreed as maximum limits. The specifications for pricing are defined in the price schedule.

# Annexes

- Minimum standards for sustainable event management at GIZ