| To Provide Baseline and Group Dynamics/Cooperative Business School for youth and women Under the Regenerative Jobs in Northern Ghana Project (Regen Jobs) | Project number/ cost centre: 19.4933.8-007.00 |
| --- | --- |

0.	List of abbreviations	2

1.	Context	3

2.	Tasks to be performed by the contractor	3

3.	Concept	4

Technical-methodological concept	5

Project management of the contractor (1.6)	5

Further requirements (1.7)	6

4.	Personnel concept	6

Team leader	6

Key expert 1, 2 and 3	7

5.	Costing requirements	8

Assignment of personnel and travel expenses	8

Workshops and training	13

6.	Inputs of GIZ or other actors	13

7.	Requirements on the format of the tender	13

8.	Option	14

Type and scope	14

Requirements	15

Quantitative requirements for the optional services	15

Requirements on the format of the tender for the option	17

9.	Outsourced processing of personal data	17

10.	Annexes	18

# List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General Terms and Conditions of Contract for supplying services and work

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

# Context

Due to the constant growth of Africa’s population, the continent needs 20 million new jobs annually. This goal is only achievable in cooperation with the private sector. In order to realize employment-related investments with companies, the Special Initiative “Decent Work for a Just Transition” (Invest for Jobs), commissioned by the German Federal Ministry for Economic Cooperation and Development (BMZ), works with African countries that are committed to reforms; and supports them to create more and better jobs and therefore providing future prospects for the local population.

The Special Initiative in Ghana works in three components: ‘Business & Invest’, ‘Cluster Approach’ and ‘Ghanaian SME (Mittelstand)’. Under the ‘Business & Invest’, the programme promotes sustainable investments from German and European companies and investors; the ‘Cluster approach’ aims to increase the economic attractiveness of business locations and industries; support industrial parks, improve export opportunities and address various obstacles to investment. The ‘Ghanaian SME (Mittelstand)’ promotes the SME sector, by improving the business environment and enhancing competitiveness, by promoting advisory and (innovative) financial services for SME and boosting cooperation between German and African companies.

Under its Component 1, Business and Invest, GIZ is collaborating with public and private partners to implement the Regenerative Jobs in Northern Ghana (Regen Jobs) Project.

In the northern part of Ghana, about 97.9 percent of households are engaged in crop farming such as maize, rice, sorghum, soybeans, cowpea, cassava, yam, cotton and vegetables, with few households engaging in poultry, livestock and pig rearing. Agricultural production is therefore the main activity in the northern sector of Ghana and is practiced mainly on seasonal and subsistence level. The Gross Domestic Product of the country has recorded an annual growth rate of about 4 to 8 percent within the past decade. Agricultural growth has been the major driver of poverty reduction. The agriculture sector is the largest source of employment for the people of northern Ghana and is dominated by smallholder farmers. The challenges in the agriculture sector include human resource and managerial skills, natural resource management, technology development and food insecurity. Food security is a phenomenon resulting from multiple causes which are food availability, food accessibility, food utilization and food stability. About 5% of Ghanaian populace are food insecure. Additionally, about 2 million Ghanaian people are vulnerable to become food insecure. Growth in the agricultural sector has been more rapid as compared to that of the non-agricultural sectors in recent years, expanding by an average annual rate of 5.5%, compared to 5.2% for the economy as a whole.

Agricultural growth however, depends mainly on rainfall patterns and land expansion. Even though agriculture is heavily dependent on rainfall, northern Ghana has unpredictable and erratic rainfall pattern. The adoption of modern agricultural technologies and cultural practices such as irrigation, fertilizer application, use of resistant varieties, good planting and harvesting times and above all, adoption of sustainable production practices like regenerative agriculture might be the panacea to increased agricultural production and improved food security and livelihoods among farmers in northern Ghana. However, the use of these modern practices is hindered by financial constraints as these farmers are smallholder farmers with limited financial support. Commercial banks, private partners and micro finance institutions are often not ready to support the smallholder farmers adopt and apply these technologies as a result of lack of collaterals. Challenges in the agriculture sector are not only limited to cultivation, but also postharvest losses, storage and marketing problems. The major cause of food insecurity in northern Ghana is therefore, attributable to the use of outmoded farming practices and postharvest losses. The objective of this project is to promote food security in Northern Ghana and increase agricultural contribution to Ghana’s economic growth in general whilst creating sustainable new decent jobs.

The overall project objective is to improve the employment situation and working conditions of 1200 people in the maize, sorghum and soy value chains (at least 50% youth, 40% females) through the promotion and development of the chains in the Northern regions and to provide micro-entrepreneurship opportunities to the people of Ghana as a means of sustainable employment-promoting growth whiles building economic resilience in the Northern regions of Ghana.

To achieve this, the following two key activities will be implemented:

•	Set-up of Farm Service Centers (Spray and Farm labour Service Providers).

•	Provide occupational health and safety trainings and support for targeted beneficiaries.

•	Conduct baseline and Provide Cooperative Business School training as well as Health Insurance provision advocacy for targeted beneficiaries.

Farmers/beneficiaries sensitized/trained – data collected and stored must adhere to the Data Protection Policy and discussed with GIZ

# Tasks to be performed by the contractor

The contractor is responsible for providing the following services:

- Group Dynamics/Cooperative Business School Training

- Provide Group Dynamics Training to new 1200 smallholder farmers, who will be formed into vibrant cooperative associations with efficient and effective leadership.

- Provide Enterprise Development Training to new 1200 beneficiaries.

- Develop Group communication plan for the newly formed cooperatives.

- Implement / Rollout the developed action plan of the new farmer cooperatives.

- Develop a Sustainability plan for the newly formed Cooperatives.

- Registration of all the new farmer groups into co-operatives under the DAs Co-operative Department

- Provide Farmer Business School trainings in grains for smallholder farmers.

- Conduct a Training of Trainers in Farmer/Cooperative Business School for at least 40 members of the Producer Associations.

- Baseline Survey

- Baseline values for setting project benchmarks to assess performance monitoring.

- Establish baseline data situation for at least 1200 farmers on the following;

- Bio-data of the beneficiary with a gender focus

- Farm size

- Yield per (kg) acre for the past three years

- Cost per acre for the past three years

- Income per acre for the past three years

- Ownership or land tenure system

- Work force size (permanent or casual)

- Access to resources (land, credit, information etc)

- Affiliation with any financial institution (including awareness)

- Source of inputs (improved variety or normal seed planting)

- Access to any health insurance or pension scheme and status (active or inactive) since the last 3 years etc

c. Help refine and align project targets

1. Develop a tracking mechanism for measuring indicators.

  - 2. Information needs, knowledge gaps on agronomic practices (production, harvesting, post-harvesting) as well as communication capacities of the target groups.

  - 3. Information on the number of people benefiting from social and economic safeguards program such as NHIS, Pensions, PPEs and loans from financial institutions.

  - 4. Information on stakeholder's perception on district assembly basic service delivery as well as status of land tenure of cocoa production in project locations.

In addition to the reports required by GIZ in accordance with the AVB, the contractor submits the following reports:

- Inception and main reports in softcopy.

- Report on group dynamics activities including the training of members and executives of Cooperatives.

- Report on Enterprise Development Activities.

- Member support/benefit circle.

- Word version of training guidelines/materials used for training.

- Implementation status of Group communication plan.

- Implementation status of Group code of conduct/norms.

- Report on the community trainings and coaching.

- Implementation status of sustainability plan for the groups.

- A baseline survey report.

- Soft copy of training attendance sheets and high -resolution pictures.

- Signed consent forms.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Deadline/place/person responsible |
| --- | --- |
| Brief Inception meeting | 15.10.2024, Accra |
| Present detailed time schedule(s) for the implementation of the trainings | 15.10.2024, Accra |
| Train targeted beneficiaries as part of technical short-term courses | 22.10.2024 – 30.07.2025, project locations |
| Submit regular progress updates | 22.01.2025, 22.04.2025, Accra |
| Submit Final report including participants lists, monitoring tables, group and individual pictures as well as consent forms | 30.07.2025 |

Period of assignment: from 15.10.2024 until 30.07.2025.

# Concept

In the tender, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation.

## Project management of the contractor (1.6)

The tenderer is required to explain its approach for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the tender; the plan includes information on assignment dates (duration and expert months) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

The tenderer is required to describe its backstopping concept. The following services are part of the standard backstopping package, which (like ancillary personnel costs) must be factored into the fee schedules of the staff listed in the tender in accordance with Section 3.3.1 of the GIZ AVB:

- Service-delivery control

- Managing adaptations to changing conditions

- Ensuring the flow of information between the tenderer and GIZ

- Assuming personnel responsibility for the contractor’s experts

- Process-oriented steering for implementation of the commission

- Securing the administrative conclusion of the project

# Personnel concept

The tenderer is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 7), the range of tasks involved and the required qualifications.

The below specified qualifications represent the requirements to reach the maximum number of points.

## Team leader

Tasks of the team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local and international short-term experts

- Regular reporting in accordance with deadlines

Qualifications of the team leader

- Education/training (2.1.1): university degree in Business Administration, Agribusiness, Social Science, Rural Sociology, Education, Development management or related fields.

- Language (2.1.2): C1-level language proficiency in English Language

- General professional experience (2.1.3): At least 5 years’ experience in community work and enterprise development or any group activities involving farmers and other community-based groups in the Agribusiness sector.

- Specific professional experience (2.1.4): At least 3 years’ experience in working with International Organisation

- Leadership/management experience (2.1.5): 5 years of management/leadership experience as project team leader or manager in a company

- Development cooperation (DC) experience (2.1.7): 5 years of experience in DC projects

## Key expert 1

Tasks of key expert 1

- Delivery of training as described above but primarily responsible for the baseline data collection and analysis.

Qualifications of key expert 1

- Education/training (2.2.1): At least tertiary education in Business Administration, Economics, Agribusiness and community development or related fields.

- Language (2.2.2): B2 -level language proficiency in English language.

- General professional experience (2.2.3): At least 3 years of professional experience in Business Administration, Agribusiness, Enterprise/community development or related fields.

- Specific professional experience (2.2.4): At least 2 years’ experience in working with an international organisation.

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Socio-cultural skills

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

## Key expert 2

Tasks of key expert 2

- Delivery of training as described above but primarily responsible for the Group Dynamics/Cooperative Business School as well as data collection.

Qualifications of key expert 2

- Education/training (2.2.1): At least tertiary degree in Business Administration, Agribusiness and community development or related fields.

- Language (2.2.2): B2 -level language proficiency in English language.

- General professional experience (2.2.3): At least 3 years professional experience in Business Administration, Agribusiness, Enterprise/community development or related fields.

- Specific professional experience (2.2.4): At least 2 years’ experience in working with an international organisation.

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Socio-cultural skills

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

## Key expert 3

Tasks of key expert 3

- Delivery of training as described above but also primarily responsible for the Group Dynamics/Cooperative Business School training as well as data collection.

Qualifications of key expert 3

- Education/training (2.2.1): At least tertiary education in Business Administration, Agribusiness and community development or related fields.

- Language (2.2.2): B2 -level language proficiency in English language.

- General professional experience (2.2.3): At least 3 years professional experience in Business Administration, Agribusiness, Enterprise/community development or related fields.

- Specific professional experience (2.2.4): At least 2 years’ experience in working with an international organisation.

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Socio-cultural skills

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

# Costing requirements

## Assignment of personnel and travel expenses

Per-diem and overnight accommodation allowances are reimbursed as a lump sum up to the maximum amounts permissible under tax law for each country as set out in the country table in the circular from the German Federal Ministry of Finance on travel expense remuneration (downloadable at https://www.bundesfinanzministerium.de).

Accommodation costs which exceed this up to a reasonable amount and the cost of flights and other main forms of transport can be reimbursed against evidence

All business travel must be agreed in advance by the officer responsible for the project.

## Sustainability aspects for travel

GIZ would like to reduce greenhouse gas emissions (CO2 emissions) caused by travel. When preparing your tender, please incorporate options for reducing emissions, such as selecting the lowest-emission booking class (economy) and using means of transport, airlines and flight routes with a higher CO2 efficiency. For short distances, travel by train (second class) or e-mobility should be the preferred option.

If they cannot be avoided, CO2 emissions caused by air travel should be offset. GIZ specifies a budget for this, through which the carbon offsets can be settled against evidence.

There are many different providers in the market for emissions certificates, and they have different climate impact ambitions. The Development and Climate Alliance (German only) has published a list of standards (German only). GIZ recommends using the standards specified there.

Specification of inputs

| Fee days | Number of experts | Number of days per expert | Total | Comments |
| --- | --- | --- | --- | --- |
| Designation of TL | 1 | 10 | 10 | This explains the remuneration of the Team Leader who is a level 3 expert |
| Designation of key experts | 3 | 15 | 45 | This explains the remuneration of the key experts who are level 2 experts |
| Travel expenses | Quantity | Number per expert | Total | Comments |
| Per-diem allowance in country of assignment | 4 | 15 days for 3 experts and 10 days for 1 | 55 | Daily per-diem per expert per number of days |
| Overnight allowance in country of assignment | 4 | 9 for TL and 41 in total for key experts | 50 | Overnight allowance to pay accommodation per night |
| Transport | Quantity | Number per expert | Total | Comments |
| Travel expenses (car) - Car rental and fuel | 4 | 1 | 4 | Travel within the country of assignment, transfer to/from airport etc. |
| Other costs | Number | Price | Total | Comments |
| Workshops | 15 | 1200 | 18000 | The budget contains the following costs : hiring of venues, workshop/training materials and refreshment. |

## Workshops and training

Please describe in your concept how you implement GIZ’s minimum standards for sustainable event management (see annexes to the terms of reference).

The contractor implements the following workshops/study trips/training courses:

- Training on Group Dynamics/ Cooperation/Farmer Business School

- Baseline survey

# Inputs of GIZ or other actors

GIZ and/or other actors are expected to make the following available:

- Logistics for workshops/trainings: To be organized by contractor

# Requirements on the format of the tender

The structure of the tender must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The tender must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete tender must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application. The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs can also be submitted in English (language).

Please calculate your financial tender based exactly on the parameters specified in Chapter 5 Quantitative requirements. The contractor is not contractually entitled to use up the days, trips, workshops or budgets in full. The number of days, trips and workshops and the budgets will be contractually agreed as maximum limits. The specifications for pricing are defined in the price schedule.

# Outsourced processing of personal data

The data protection and information security provisions set out in the most recent GIZ AVB (section 1.10 Data Protection) apply.

NB: Survey software used must adhere to the Data Protection Policy (software must be hosted by an European Country).