| To Provide Group Dynamics Training, Baseline Data and Farm Mapping Under the Sustainable Pineapple for Export Resilience (SuPER) Project | Project number/ cost centre: 19.4933.8-007.00 |
| --- | --- |

0.	List of abbreviations	2

1.	Context	3

2.	Tasks to be performed by the contractor	4

3.	Concept	8

Technical-methodological concept	8

Other specific requirements	8

Project management of the contractor	8

4.	Personnel concept	9

Team leader	10

Expert 1

Short-term expert pool with minimum ..., maximum ... members

5.	Costing requirements	11

Assignment of personnel	11

Travel	11

Workshops, training	11

Other costs	11

Flexible remuneration item

6.	Inputs of GIZ or other actors

7.	Requirements on the format of the bid	12

8.	Option	12

9.	Annexes	12

# List of abbreviations

AVB	General Terms and Conditions of Contract (AVB) for supplying services and work 2018

ToRs	Terms of reference

BMZ	Federal Ministry for Economic Cooperation and Development

GIZ	Deutsche Gesellschaft für Internationale Zusammenarbeit GmbH

SME	Small and Medium-sized Enterprises (Mittelstand)

PPE	Personal Protective Equipment

CoFIE                 Cocoa Jobs for Organic Integration and Improved Rural Economy

GoG	Government of Ghana

ITC	International Trade Center

GHS	Ghana Cedis

USD                    United States Dollars

# Context

Due to the constant growth of Africa’s population, the continent needs 20 million new jobs annually. This goal is only achievable in cooperation with the private sector. In order to realize employment-related investments with companies, the Special Initiative on Training and Job Creation (Invest for Jobs), commissioned by the German Federal Ministry for Economic Cooperation and Development (BMZ), works with African countries that are committed to reforms; and supports them to create more and better jobs and therefore providing future prospects for the local population.

The Special Initiative in Ghana works in three components: ‘Business & Invest’, ‘Cluster Approach’ and ‘Ghanaian SME (Mittelstand)’. Under the ‘Business & Invest’, the programme promotes sustainable investments from German and European companies and investors; the ‘Cluster approach’ aims to increase the economic attractiveness of business locations and industries; support industrial parks, improve export opportunities and address various obstacles to investment. The ‘Ghanaian SME (Mittelstand)’ promotes the SME sector, by improving the business environment and enhancing competitiveness, by promoting advisory and (innovative) financial services for SME and boosting cooperation between German and African companies.

Under its Component 1, Business and Invest, GIZ is collaborating with public and private partners to implement the Sustainable Pineapple for Export Resilience (SuPER) Project.

As is evident in business, opportunities always signify the need to modify strategy and invest. To meet the increasing demand from our local and foreign partners, there is the need to expand production. As has been the model, they combine the produce from their own farms and the produce from the out-grower scheme.

To meet the demand, the project seeks to expand their fields with an additional 30 acres of land. The main challenge would be to ensure the standards of produce from the new farms meet international standards and are compliant with the new EU Due Diligence Law.

Considering the expansion and the inclusion of more farmland acreage, it would also become necessary to improve on the traceability model that currently exist to ensure it is robust. This will ensure that, partners, primarily off-takers, have the necessary assurances regarding the products.

The project will be measured against the following success indicators (Key Performance Indicators):

- No. of Jobs: 70

- No. of people to be trained.: 300 (until end of this project)

- No. of people with improved working conditions: 300 (until end of this project)

- No. of people with improved livelihoods: 300 (until end of this project)

# Tasks to be performed by the contractor

With this assignment, GIZ and partners seek to prepare and strengthen pineapple producers as MightyCrops Limited, and other smallholder farmers in its catchment area aimed at securing the international market relationships that have been built and secured by MightyCrops, by so doing, securing the many jobs created and creating new green decent jobs as well.

Therefore, GIZ-Ghana seeks to engage a consultancy firm with the required professional knowledge and experience.

- Objective of Consultancy Assignment

The objective is to:

- Review/adapt manuals and curriculum on general business models, marketing models and farmer/cooperative business school from relevant organizations to context of the project for the identified groups.

- Sensitize 300 beneficiaries and support them to form vibrant cooperative associations with efficient and effective leadership to produce firstly organic, then conventional pineapple.

- Map the current pineapple farms of the private partner.

- Baseline Survey

- Baseline values for setting project benchmarks to assess performance monitoring

- Establish baseline data situation for at least 1500 farmers on the following;

- Bio-data of the beneficiary with a gender focus

- Farm size

- Yield per (kg) acre for the past three years

- Cost per acre for the past three years

- Income per acre for the past three years

- Ownership or land tenure system

- Work force size (permanent or casual)

- Access to resources (land, credit, information etc)

- Affiliation with any financial institution (including awareness)

- Source of inputs (improved variety or normal seed planting)

- Access to any health insurance scheme and status (active or inactive) since the last 3 years etc

This baseline should be done for all pineapple farms within a 5km radius of the private partner.

- Survey software used must adhere to the Data Protection Policy (software must be hosted by an European Country).

- Group Dynamics Training

The consultant shall provide the following output as evidence of work undertaken both in hard and      soft copies:

- An inception report

- Report on group dynamics activities including the training of members and executives of Cooperatives

- Report on Enterprise Development Activities

- Member support/benefit circle

- Word version of training guidelines/materials used for training

- Group communication plan developed

- Group code of conduct/norms developed

- Cooperatives and Enterprises established and registered in project beneficiary district

- Report on the community trainings and coaching

- Suitability plan for the Cooperatives and Enterprises

- Farm Mapping

  - Map the farm area of the private partner and all potential farmlands registered to their estate.

  - Map all farms within a 10km radius of the farm of the private partner producing pineapple.

This mapping exercise shall follow a typical farm profiling data collection. Template for data collection shall be developed by all parties concerned

Certain milestones, as laid out in the table below, are to be achieved by certain dates during the contract term, and at locations:

| Milestone | Deadline/place/person responsible |
| --- | --- |
| Brief Inception meeting | 15.10.2024, Accra |
| Present detailed time schedule(s) for the implementation of the trainings | 25.10.2024, Accra |
| Undertake main activities of the consultancy | 26.10.2024 – 30.06.2025, project locations |
| Submit Progress Reports | 28.02.2025, Accra |
| Submit Final report including participants lists, monitoring tables, group and individual pictures as well as consent forms | 30.07.2025, Accra |

| Duration of Assignment | 15.10.2024 – 30.07.2025 |
| --- | --- |
| Geographic coverage | Central Region |

# Concept

In the bid, the bidder is required to show how the objectives defined in Chapter 2 are to be achieved, if applicable under consideration of further specific method-related requirements (technical-methodological concept). In addition, the bidder must describe the project management system for service provision.

## Technical-methodological concept

Strategy: The bidder is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1). Following this, the bidder presents and justifies the strategy with which it intends to provide the services for which it is responsible (see Chapter 2).

The bidder is required to present the actors relevant for the services for which it is responsible and describe the cooperation with them.

The bidder is required to present and explain its approach to steering the measures with the project partners and its contribution to the results-based monitoring system.

The bidder is required to describe the key processes for the services for which it is responsible and create a schedule that describes how the services according to Chapter 2 are to be provided. In particular, the bidder is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors in accordance with Chapter 2.

The bidder is required to describe its contribution to knowledge management for the partner and GIZ and promote scaling-up effects (learning and innovation).

The bidder shall clearly indicate:

- Geographic area, where training will take place / where contractor is located

- Trade area(s)

- Number of trainers available

- Preliminary indication when the training is supposed to happen (morning/midday/evening and number of training days per week/month).

## Project management of the contractor

The bidder is required to explain its approach for coordination with the GIZ project.

- The contractor is responsible for selecting, preparing, training and steering the experts assigned to perform training.

- The contractor makes available equipment and supplies (consumables) and assumes the associated operating and administrative costs.

- The contractor manages costs and expenditures, accounting processes and invoicing in line with the requirements of GIZ.

The contractor reports regularly to GIZ in accordance with the AVB of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH.

In addition to the reports required by GIZ in accordance with AVB, the contractor submits the following reports/outputs as evidence of work:

- Detailed time schedule(s) for the implementation of the tasks i. e. timeline required.

- Participants Lists of the trainees (validated via signatures/thumbprints): Monitoring / data selection and storage must adhere to the Data Protection Policy and discussed with GIZ.

- Monthly progress reports/updates within the training period, in close collaboration with GIZ and project partners

- Group and individual pictures of the workshops / beneficiaries with signed consent forms by each person for which data or pictures are taken. A template will be provided by GIZ.

- Final training report

Beyond the aspects mentioned above, the technical proposal shall include:

- Institutional profile

- Registration certificate

- Understanding of assignment, proposed methodology and work plan to approach the assignment.

- Details must include among others.

  - Duration of training per person/group

  - Training plan / content incorporating all stated modules.

  - Capacity to offer training (trainers, list of tools and equipment)

  - Modalities to ensure job/order matching of at least 50% of trained beneficiaries.

- In case the contractor has capacities to train more than the assigned persons, this should be indicated (although the financial proposal shall be based on assigned number)

The bidder is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the bid; the plan includes information on assignment dates (duration and expert days) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

# Personnel concept

The bidder is required to provide personnel/trainers who are suited to filling the positions described, on the basis of their CVs (see Chapter 6), the range of tasks involved and the required qualifications.

The below specified qualifications represent the requirements to reach the maximum number of points.

## Team leader

Tasks of the team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project.

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local and international short-term experts.

- Regular reporting in accordance with deadlines

Qualifications of the team leader

- Education/training (2.1.1): (Master’s) degree in Business Administration, Agribusiness, Social Science, Rural Sociology, Education, Development management or related fields.

- Language (2.1.2): Good business language skills in report writing and communication skills in English and good knowledge of local languages (Twi, Fante, Bono etc.)

- General professional experience (2.1.3): At least 7 years’ experience in community work and enterprise development or any group activities involving farmers and other community-based groups.

## Team Members (4)

Tasks of institutional staff / trainers

- Delivery of training as described above.

Qualifications of institutional staff / trainers

- Education/training (2.2.1): At least bachelor's degree in business administration, Agribusiness and community development or related fields

- Language (2.2.2): Good skills in English and good knowledge of local languages (Twi, Fante, Bono etc.)

- General professional experience (2.2.3): At least 4 years of post-graduate professional experience in Business Administration, Agribusiness, Enterprise/community development or related fields.

- At least 1 expert with specialty in ArcGIS and Geo-spatial Mapping

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Sociocultural competence

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

The bidder must provide a clear overview of all proposed short-term experts and their individual qualifications.

Data protection

The contractor agrees and cooperates on the following: Personal data will be processed on behalf of the client, represented by GIZ. Therefore, an agreement on "Outsourcing of data processing (AuV)" will be concluded with the contractor in accordance with the General Data Protection Regulation (GDPR) of the European Union (EU). For this purpose, the technical and organisational measures (TOM) for compliance with the data protection requirements must be outlined prior to conclusion of the contract. If the contractor has already been audited by GIZ in the past, an update in accordance with GDPR must nevertheless be sent. After a positive check, the contract is concluded with the AuV attachment. The AuV is attached as part of these tender documents. The bidder is required to submit the TOM along with the technical proposal. The TOM that must be outlined are specified in the document “Outsourcing of data processing” on page 8 and 9. The TOM will not be assessed during the evaluation of the technical proposal; however, it is mandatory to submit them. Failure to do so can result in your bid being excluded from the tender procedure.

# Costing requirements

## Assignment of personnel

## Assignment of personnel and travel expenses

Accommodation costs which exceed this up to a reasonable amount and the cost of flights and other main forms of transport can be reimbursed against evidence

All business travel must be agreed in advance by the officer responsible for the project.

## Sustainability aspects for travel

GIZ would like to reduce greenhouse gas emissions (CO2 emissions) caused by travel. When preparing your tender, please incorporate options for reducing emissions, such as selecting the lowest-emission booking class (economy) and using means of transport, airlines and flight routes with a higher CO2 efficiency. For short distances, travel by train (second class) or e-mobility should be the preferred option.

If they cannot be avoided, CO2 emissions caused by air travel should be offset. GIZ specifies a budget for this, through which the carbon offsets can be settled against evidence.

There are many different providers in the market for emissions certificates, and they have different climate impact ambitions. The Development and Climate Alliance (German only) has published a list of standards (German only). GIZ recommends using the standards specified there.

Specification of inputs

| Fee days | Number of experts | Number of days per expert | Total | Comments |
| --- | --- | --- | --- | --- |
| Designation of TL | 1 | 25 | 25 |  |
| Designation of key expert | 4 | 40 | 160 |  |
| Travel expenses | Quantity | Number per expert | Total | Comments |
| Per-diem allowance in country of assignment | 1 | 5 | 5 |  |
| Transport | Quantity | Number per expert | Total | Comments |
| CO2 compensation for air travel |  |  |  | A fixed budget of EUR is earmarked for settling carbon offsets against evidence. |
| Travel expenses (train, car) Car Rental | 1 | 5 | 5 | Travel within the country and city of assignment for 20 days |
| Fuel for Car | 1 | 5 | 5 | Fuel for car within the period of transport. |
| Other costs | Number | Price | Total | Comments |
| Workshop (Food, Tnt) | 300 | 30 | 9000 | Food and tnt for participants. |
| Hall Rental | 15 | 90 | 1350 | For trainings |

| Milestones/partial works | Estimated expert days for orientation | Deadline/place/person responsible |
| --- | --- | --- |
| Inception and Document Preparation | 10 | Dominase/ Consultant |
| Implementation and Training | 25 | Dominase/ Consultant |
| Reporting and Closing | 5 | Accra/ Consultant |

## Travel

The bidder is required to calculate the travel by the specified experts and the experts it has proposed based on the places of performance stipulated in Chapter 2 and list the expenses separately by daily allowance, accommodation expenses, flight costs and other travel expenses.

## Workshops, training

The contractor implements the following workshops/study trips/training courses:

- Workshops/trainings to 4850 persons over a period of 5 months constitutes the main task of the assignment, as described above.

## Other costs

Apart from the professional stated above, the financial proposal shall include all costs required in a detailed breakdown, such as

- Cost and list of any tools and materials/consumables required to aid training.

- Travel costs, if applicable

Costs for Coordination / Contacting beneficiaries etc.

# Requirements on the format of the bid

The structure of the bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) is to be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). It must be legible (font size 11 or larger) and clearly formulated. The bid is drawn up in English (language).

The complete bid shall not exceed 10 pages (excluding CVs).

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application. The CVs shall not exceed 4 pages. The CVs must clearly show the position and job the proposed person held in the reference project and for how long. The CVs can also be submitted in English (language).

If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment.

Please calculate your price bid based exactly on the aforementioned costing requirements. In the contract the contractor has no claim to fully exhaust the days/travel/workshops/ budgets. The number of days/travel/workshops and the budget amount shall be agreed in the contract as ‘up to’ amounts. The specifications for pricing are defined in the price schedule.

# Option

After the tasks put out to tender have been completed, important elements of these tasks can be continued or extended within the framework of a follow-on assignment, e.g. in terms of type and scope. The option is exercised in the form of an extension to the contract based on the already offered individual rates.

# Annexes

not applicable