| To Provide Capacity Building training for Youth and Women and provide auxiliary services for janitors and waste collectors for placement in public, private and commercial entities under the Ghana Goes Green Initiative in the Ashanti Region of Ghana. | Project number/ cost centre: 19.4933.8-007.00 |
| --- | --- |

0.	List of abbreviations	2

1.	Context	3

2.	Tasks to be performed by the contractor	4

3.	Concept	5

Technical-methodological concept	5

Other specific requirements	6

Project management of the contractor	6

4.	Personnel concept	7

Team leader	7

Expert 1

Short-term expert pool with minimum ..., maximum ... members

5.	Costing requirements	8

Assignment of personnel	8

Travel	8

Workshops, training	10

Other costs	10

Flexible remuneration item

6.	Inputs of GIZ or other actors

7.	Requirements on the format of the bid	10

8.	Option	10

9.	Annexes	11

# List of abbreviations

AVB	General Terms and Conditions of Contract (AVB) for supplying services and work 2018

ToRs	Terms of reference

BMZ	Federal Ministry for Economic Cooperation and Development

GIZ	Deutsche Gesellschaft für Internationale Zusammenarbeit GmbH

SME	Small and Medium-sized Enterprises (Mittelstand)

PPE	Personal Protective Equipment

GoG	Government of Ghana

ITC	International Trade Center

GHS	Ghana Cedis

USD                    United States Dollars

# Context

Due to the constant growth of Africa’s population, the continent needs 20 million new jobs annually. This goal is only achievable in cooperation with the private sector. In order to realize employment-related investments with companies, the Special Initiative on Training and Job Creation (Invest for Jobs), commissioned by the German Federal Ministry for Economic Cooperation and Development (BMZ), works with African countries that are committed to reforms; and supports them to create more and better jobs and therefore providing future prospects for the local population.

The Special Initiative in Ghana works in three components: ‘Business & Invest’, ‘Cluster Approach’ and ‘Ghanaian SME (Mittelstand)’. Under the ‘Business & Invest’, the programme promotes sustainable investments from German and European companies and investors; the ‘Cluster approach’ aims to increase the economic attractiveness of business locations and industries; support industrial parks, improve export opportunities and address various obstacles to investment. The ‘Ghanaian SME (Mittelstand)’ promotes the SME sector, by improving the business environment and enhancing competitiveness, by promoting advisory and (innovative) financial services for SME and boosting cooperation between German and African companies.

Under its Component 1, Business and Invest, GIZ is collaborating with public and private partners to implement the Ghana Goes Green Initiative.

The Ghana Goes Green Initiative is an umbrella initiative that is looking at several projects under circular economy and environmental sustainability. The Initiative is focused on Plastic pollution mediation and recovery projects, paper recycling, wastewater treatments, textile recycling amongst others. The Initiative is broken down into 4 milestones; Plastic Recycling; Paper Recycling, Textile Recycling and Wastewater treatment.

Plastic pollution is a problem that has been with us for ages. This is even more prevalent in the cities and towns. Over the years, several attempts have been made by governments and several other actors to address this challenge with very little or no impact made. The focus of this project is to not see it as a problem in its entirety, but also as a valuable resource. It is in this notion that we fashion out this project, to accrue every possible value in this resource, and by so doing, create jobs, improve livelihoods, and improve the skills of the actors in this space.

The concept here is to train plastic collectors and aggregators to have a better understanding of the value chain. This project also seeks to train and empower house keepers, janitors and cleaners in public, private and corporate organizations to have the technical know how to segregate plastics and potentially paper from the waste stream, contributing to environmental sustainability whiles making some money as well.

The project, therefore, aims at contributing to improving the plastic value chain of collectors, and aggregators and empowering janitors and housekeepers to include plastic segregation in their day-to-day duties in public, private and corporate institutions, creating jobs for about 100 people, providing trainings for about 600 individuals, and improving the incomes and working conditions of some 300 existing and new workers in the sector.

To achieve this, the following key activities will be implemented:

- Organize waste pickers in selected project locations into cooperatives and improve working conditions,

- Develop a training manual for the purpose of training skilled janitors and housekeepers.

- Provide occupational health and safety trainings and support for targeted beneficiaries.

- Promote health insurance and pension scheme activities among collectors.

- Create and strengthen linkages between collectors, aggregators, and final off takers.

- Connect training beneficiaries to decent jobs in the public, private and corporate institutions, using the skill acquired to influence waste segregation and plastic recycling.

# Tasks to be performed by the contractor.

With this assignment, GIZ and partners seek to prepare, strengthen, and improve the working conditions of actors along the plastic waste resource value chain to improve the quantity and quality of plastics collected in Ghana for processing, among others.

Therefore, GIZ-Ghana seeks to engage a consultancy firm or consortium of organisations with the required professional knowledge and experience.

- Objective of Consultancy Assignment

The objective is to:

- Review/adapt manuals and curriculum on group dynamics/business models, accounting/marketing models and occupational health and safety from relevant organizations to the context of the project for the identified groups.

- Conduct the training and provide other advisory services to the identified groups.

- Beneficiaries trained – data collected and stored must adhere to the Data Protection Policy and discussed with GIZ.

- Connect beneficiaries to job openings in the areas in which they have been trained.

- Outputs

- Capacity Building for Identified Beneficiaries.

The contractor shall;

- pre-assess training needs of the identified groups,

- develop curriculums for the specific trainings identified in objective 2 and facilitate the trainings for the target group.

- these trainings should be targeted at improving efficiency, improving working conditions, financial inclusion amongst others.

- Promote health insurance and or pension scheme among targeted beneficiaries.

- Liaise with partners to supply Personal Protective Equipment to collectors, and individuals at aggregation/sorting and processing centres. (Overalls, Hand Gloves, Reflective Jackets, Safety Boots, Googles, Nose Masks)

- Matchmake project beneficiaries to public, private and corporate institutions for job opportunities.

Certain milestones, as laid out in the table below, are to be achieved by certain dates during the contract term, and at locations:

| Milestone | Deadline/place/person responsible |
| --- | --- |
| Brief Inception meeting | 15.10.2024, Accra |
| Present detailed time schedule(s) for the implementation of the trainings and others | 20.10.2024, Kumasi |
| Develop and Adapt Training Manuals | 21.10.2024 - 30.11.2024 |
| Train targeted beneficiaries | 01.12.2024 – 25.05.2025 |
| Compile training reports | 25.05.2025 - 25.06.2025 |
| Submit Final report including participants lists, monitoring tables, group and individual pictures as well as consent forms | 30.07.2025 |

| Duration of Assignment | 15.10.2024 – 30.07.2025 |
| --- | --- |
| Geographic coverage | Kumasi, Ghana |
| Training Capacity | At least 300 |

# Concept

In the bid, the bidder is required to show how the objectives defined in Chapter 2 are to be achieved, if applicable under consideration of further specific method-related requirements (technical-methodological concept). In addition, the bidder must describe the project management system for service provision.

## Technical-methodological concept

Strategy: The bidder is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1). Following this, the bidder presents and justifies the strategy with which it intends to provide the services for which it is responsible (see Chapter 2).

The bidder is required to present the actors relevant for the services for which it is responsible and describe the cooperation with them.

The bidder is required to present and explain its approach to steering the measures with the project partners and its contribution to the results-based monitoring system.

The bidder is required to describe the key processes for the services for which it is responsible and create a schedule that describes how the services according to Chapter 2 are to be provided. In particular, the bidder is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors in accordance with Chapter 2.

The bidder is required to describe its contribution to knowledge management for the partner and GIZ and promote scaling-up effects (learning and innovation).

The bidder shall clearly indicate:

- Geographic area, where training will take place / where contractor is located

- Trade area(s)

- Number of trainers available

- Preliminary indication when the training is supposed to happen (morning/midday/evening and number of training days per week/month).

## Project management of the contractor

The bidder is required to explain its approach for coordination with the GIZ project.

- The contractor is responsible for selecting, preparing, training and steering the experts assigned to perform training.

- The contractor makes available equipment and supplies (consumables) and assumes the associated operating and administrative costs.

- The contractor manages costs and expenditures, accounting processes and invoicing in line with the requirements of GIZ.

The contractor reports regularly to GIZ in accordance with the AVB of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH.

In addition to the reports required by GIZ in accordance with AVB, the contractor submits the following reports/outputs as evidence of work:

- Detailed time schedule(s) for the implementation of the tasks i. e. timeline required.

- Participants Lists of the trainees (validated via signatures/thumbprints): Monitoring / data selection and storage must adhere to the Data Protection Policy and discussed with GIZ.

- Monthly progress reports/updates within the training period, in close collaboration with GIZ and project partners

- Group and individual pictures of the workshops / beneficiaries with signed consent forms by each person for which data or pictures are taken. A template will be provided by GIZ.

- Final training report

Beyond the aspects mentioned above, the technical proposal shall include:

- Institutional profile

- Registration certificate

- Understanding of assignment, proposed methodology and work plan to approach the assignment.

- Details must include among others.

  - Duration of training per person/group

  - Training plan / content incorporating all stated modules.

  - Capacity to offer training (trainers, list of tools and equipment)

  - Modalities to ensure job/order matching of at least 50% of trained beneficiaries.

- In case the contractor has capacities to train more than the assigned persons, this should be indicated (although the financial proposal shall be based on assigned number)

The bidder is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the bid; the plan includes information on assignment dates (duration and expert days) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

# Personnel concept

The bidder is required to provide personnel/trainers who are suited to filling the positions described, on the basis of their CVs (see Chapter 6), the range of tasks involved and the required qualifications.

The below specified qualifications represent the requirements to reach the maximum number of points.

## Team leader

Tasks of the team leader

- Overall responsibility for the consultancy (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project.

- Personnel management, particularly identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local and international short-term experts.

- Regular reporting in accordance with deadlines

Qualifications of the team leader

- Education/training (2.1.1): (Master’s) degree in Environmental Science, Business Administration, Social Science, Rural Sociology, Education, Development management or related fields.

- Language (2.1.2): Good business language skills in report writing and communication skills in English and good knowledge of local languages (Twi, Ga, Fante, Ewe, Bono etc.)

- General professional experience (2.1.3): At least 5 years’ experience in waste management, community work and enterprise development or any group activities involving waste pickers and other community-based groups.

## Team Members (4)

Tasks of institutional staff / trainers

- Delivery of training as described above.

Qualifications of institutional staff / trainers

- Education/training (2.2.1): At least Bachelor’s Degree in Environmental Science, Business Administration, and community development or related fields

- Language (2.2.2): Good skills in English and good knowledge of local languages (Ga, Twi, Fante, Ewe, Bono etc.)

- General professional experience (2.2.3): At least 3 years of post-graduate professional experience in Environmental Science, Business Administration, Enterprise/community development or related fields.

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Sociocultural competence

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

The bidder must provide a clear overview of all proposed short-term experts and their individual qualifications.

# Costing requirements

## Assignment of personnel

## Assignment of personnel and travel expenses

Accommodation costs which exceed this up to a reasonable amount and the cost of flights and other main forms of transport can be reimbursed against evidence

All business travel must be agreed in advance by the officer responsible for the project.

## Sustainability aspects for travel

GIZ would like to reduce greenhouse gas emissions (CO2 emissions) caused by travel. When preparing your tender, please incorporate options for reducing emissions, such as selecting the lowest-emission booking class (economy) and using means of transport, airlines and flight routes with a higher CO2 efficiency. For short distances, travel by train (second class) or e-mobility should be the preferred option.

If they cannot be avoided, CO2 emissions caused by air travel should be offset. GIZ specifies a budget for this, through which the carbon offsets can be settled against evidence.

There are many different providers in the market for emissions certificates, and they have different climate impact ambitions. The Development and Climate Alliance (German only) has published a list of standards (German only). GIZ recommends using the standards specified there.

Specification of inputs

| Fee days | Number of experts | Number of days per expert | Total | Comments |
| --- | --- | --- | --- | --- |
| Designation of TL | 1 | 60 | 60 |  |
| Designation of key expert | 4 | 70 | 280 |  |
| Travel expenses | Quantity | Number per expert | Total | Comments |
| Per-diem allowance in country of assignment | 1 | 5 | 5 |  |
| Transport | Quantity | Number per expert | Total | Comments |
| CO2 compensation for air travel |  |  |  | A fixed budget of EUR is earmarked for settling carbon offsets against evidence. |
| Travel expenses (train, car) Car Rental | 1 | 5 | 5 | Travel within the country and city of assignment for 40 days |
| Fuel for Car | 1 | 5 | 5 | Fuel for car within the period of transport. |
| Other costs | Number | Price | Total | Comments |
| Workshop (Food,Hall and Tnt) | 15 | 1000 | 15000 | Food, hall and Tnt ( 100 participants per session with each participant been present for 5 days) |
| Procurement (PPEs) | 1 | 10000 | 10000 | For trainings |

| Milestones/partial works | Estimated expert days for orientation | Deadline/place/person responsible |
| --- | --- | --- |
| Inception and Document Preparation | 15 | Dominase/ Consultant |
| Implementation and Training | 40 | Dominase/ Consultant |
| Reporting and Closing | 15 | Accra/ Consultant |

## Travel

The bidder is required to calculate the travel by the specified experts and the experts it has proposed based on the places of performance stipulated in Chapter 2 and list the expenses separately by daily allowance, accommodation expenses, flight costs and other travel expenses.

## Workshops, training

The contractor implements the following workshops/study trips/training courses:

- Workshops/trainings to 400 persons over a period of 4 weeks constitutes the main task of the assignment, as described above.

## Other costs

Apart from the professional stated above, the financial proposal shall include all costs required in a detailed breakdown, such as

- Cost and list of any tools and materials/consumables required to aid training.

- Travel costs, if applicable

Costs for Coordination / Contacting beneficiaries etc.

# Requirements on the format of the bid

The structure of the bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) is to be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). It must be legible (font size 11 or larger) and clearly formulated. The bid is drawn up in English (language).

The complete bid shall not exceed 10 pages (excluding CVs).

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application. The CVs shall not exceed 4 pages. The CVs must clearly show the position and job the proposed person held in the reference project and for how long. The CVs can also be submitted in English (language).

If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment.

Please calculate your price bid based exactly on the aforementioned costing requirements. In the contract the contractor has no claim to fully exhaust the days/travel/workshops/ budgets. The number of days/travel/workshops and the budget amount shall be agreed in the contract as ‘up to’ amounts. The specifications for pricing are defined in the price schedule.

# Option

After the tasks put out to tender have been completed, important elements of these tasks can be continued or extended within the framework of a follow-on assignment, e.g. in terms of type and scope. The option is exercised in the form of an extension to the contract based on the already offered individual rates.

# Annexes

# The open tender is open for applicants applying either as an Individual entity or in a Consortium of several entities. Applicants must fulfil the following conditions to be eligible:

# When applying as an individual entity: An individual applicant must be a separate legal entity registered in Ghana. The exact type of legal form must be disclosed in the application form. An individual applicant must be duly registered and operating under all licenses required for a given line of business in Ghana. An individual applicant must have been operating for a minimum of 3 years (since April 2018).

# When applying as a Consortium of several entities: The consortium must nominate one lead applicant amongst its entities. The responsibilities of the lead applicant are:

  - Responsible for the quality and truth of information provided via the offer.

  - In case of a successful application, the lead applicant will be the one signing the Contract Agreement. Hence the lead applicant must be the main stakeholder, who will implement the project and be responsible for the full execution of the project.

  - The Lead applicant must have been operating for a minimum of 3 years (since April 2018).

  - All applicants of the consortium must each be a separate legal entity registered in Ghana. The exact type of legal form must be attached to the application form. At least one member of the applying consortium must be duly registered and operating under all licenses required for the given line of business in Ghana.