| Women Empowerment in Manufacturing (WEM) Project | Project number/ cost centre: 18.2197.4-010.00 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

- Context

The objective of the EU-BMZ co-funded GIZ programme “EU4Business: Small and medium sized enterprises (SME) Recovery, Competitiveness and Internationalization / Utilization and Implementation of the Association Agreement between European Union (EU) and Ukraine in the field of trade” (hereafter “EU4Business Programme”) is to enhance Ukrainian SME’s competitiveness and to facilitate their access to the EU´s internal market. A special emphasis is put on strengthening the capacities of Ukrainian SMEs to comply with the EU-Ukraine Deep and Comprehensive Free Trade Agreement (DCFTA).

The EU4Business Programme pursues a multi-level, multi-actor approach, intervening on different levels and with different organizations. On the macro level Ukrainian ministries (e.g., Ministry of Economy of Ukraine, Ministry of Digital Transformation) and state entities such as the EEPO are being supported. On the meso-level, SME clusters with export potential are strengthened in their capacities, as are business intermediate organizations (BIOs) and other Ukrainian export-oriented institutions and business support organizations, with whom the EU4Business Programme closely cooperates.

On the micro level, the EU4Business Programme supports SMEs via two types of assistance – financial support combined with advisory support. It supports business continuity of micro businesses hit worst by the crisis, supports the providers of basic supplies by micro and small firms and stimulates economic recovery (via SME with growth potential) in the medium term

Current situation

Ukraine has been actively working towards more robust integration with the EU, especially in economic sectors such as manufacturing, to foster knowledge sharing and cross-border cooperation. Recent milestones, such as Ukraine being granted EU candidate status on June 23, 2022, and the decision to start accession negotiations on December 14, 2023, have made international collaboration more critical than ever. This momentum opens up significant opportunities for Ukrainian women-led manufacturing SMEs to integrate into the European market, adopt best practices, particularly in best practices in digitalization and green transition, and strengthen their operational resilience.

A unique challenge faced by many women entrepreneurs in manufacturing is that their male partners have been mobilized to the army, leaving them with greater responsibility in both family life and business operations. This shift means that women must not only manage their businesses but also delve deeper into the technical, operational, and strategic aspects of manufacturing—areas traditionally dominated by men. As a result, there is an urgent need to empower these women with the skills, knowledge, and support to overcome these new challenges and continue leading their businesses effectively.

In the short term, connecting Ukrainian women entrepreneurs with their European counterparts allows them to share valuable knowledge, understand market needs, and effectively manage risks. In the long term, fostering these partnerships and promoting digital adoption will enhance the resilience of Ukraine’s manufacturing sector, contributing to the broader goal of sustainable economic recovery.

Despite progress, the level of export and internationalization among Ukrainian women-led manufacturing SMEs remains relatively low. The war has introduced new challenges, including disrupted supply chains, damaged infrastructure, and the relocation of businesses. Additionally, with many male partners serving in the military, women are now taking on larger roles within their companies, often without sufficient training or technical knowledge in areas such as production processes and international trade.

The WEM Project is designed to provide Ukrainian women-led manufacturing SMEs with:

Navigating International Markets: Export Skills for Women Entrepreneurs.

Digital Transformation & AI Integration in Manufacturing: Training on digital tools, data analytics, and AI to optimize production, cut costs, and enhance decision-making.

Capacity Building in Green Technologies: Training in sustainable manufacturing practices to not just reduce environmental impact but also to pave the way for significant operational efficiency improvements and future growth.

Lean Manufacturing Processes: training focused on streamlining production processes to increase efficiency and reduce waste.

Virtual exchange with EU Counterparts: facilitating connections between Ukrainian and European businesses to foster knowledge sharing and collaboration.

- Tasks to be performed by the contractor

The contractor is responsible for providing the following services:

2.1 Tasks

2.1.1 Working Package 1: Open call and SMEs Selection

| Implementation period | 11.11.2024 – 11.12.2024 |
| --- | --- |
| Place of provision | anticipated: Ukraine |
| Number of SMEs covered | Up to 15, not less than 10 Ukrainian Women-lead SMEs in Manufacturing |

2.1.1.1 The Contractor shall conduct a selection process of SMEs for participation in the project via an open call, focusing on women-led SMEs in manufacturing sectors with officially employed not less than 10 people and with separate manufacturing space. The goal is to select up to 15 SMEs not less than 10. The contractor shall develop to GIZ a list of questions to be used for interviews and selection criteria aimed at the selection of the participants of the project; the Contractor shall conduct interviews (online) to select up to 15 participants but not less than 10 for the project. The Contractor also is free to use different additional instruments for selection (e.g. motivation letter, essay, questionnaire, etc). The Contractor, in close cooperation with GIZ, shall shortlisted out of 15 shortlisted and will develop a list of finalists. The application form for the selection process, the interview questionnaires, the open call announcement, and the final list of at least 10 SMEs must be approved by GIZ.

2.1.1.2 The Contractor shall analyse all selected SMEs (not less than 10). Based on the interviews and due diligence results, the Contractor shall develop profiles presentations in Ukrainian and English languages for selected women-led SMEs (up to 2 pages each in PDF format ) with an SME profile and an analysis of the needs and development potential of the selected SMEs and submit it to GIZ.

2.1.2. Working Package 2: Development and conduction of the training courses

| Implementation period | 12.12.2024 – 04.02.2025 |
| --- | --- |
| Place of provision | anticipated: Ukraine |
| Number of SMEs covered | Up to 15, not less than 10 Ukrainian Women-lead SMEs in Manufacturing |

2.1.2.1. The Contractor shall develop and approve an online training course program with GIZ Project Staff representatives, which shall include, but not be limited to, the following topics. The course duration should not be less than 20 hours (2 hours per each activity within the Module)

| Module 1. | Navigating International Markets: Export Skills for Women Entrepreneurs Objective: Equip Ukrainian women-led manufacturing SMEs with the knowledge and skills needed to successfully navigate international markets, particularly the EU, by understanding export requirements, market access, and building business relationships Activities (could be modified): - Training in export readiness, EU requirements - Training in EU Market Access & Matchmaking - Workshops on International Networking and Cross-Cultural Business Communication |
| --- | --- |
| Module 2. | Digital Transformation & AI Integration in Manufacturing Objective: Equip women-led manufacturing SMEs with the tools and knowledge to integrate advanced digital technologies and AI into their production processes. Activities (could be modified): - Workshop on using AI to optimize manufacturing operations, improve production efficiency, and reduce waste. - Training in digital tools that enhance productivity, supply chain management, and process automation. |
| Module 3. | Sustainable Manufacturing Practices Objective: Build the capacity of women-led manufacturing SMEs to adopt sustainable, green technologies that reduce environmental impact and improve operational efficiency. Activities (could be modified): - Training program on implementing eco-friendly manufacturing technologies and processes, focusing on resource efficiency and waste reduction. - Workshop on circular economy models and sustainable product design. - Consulting services to support adopting green certification programs and environmentally responsible manufacturing practices. - Best practices from EU countries on sustainable manufacturing innovations |
| Module 4. | Lean Processes & Operational Efficiency in Manufacturing Objective: Streamline manufacturing operations through lean processes, increasing productivity, reducing waste, and enhancing efficiency. Activities (could be modified): - Practical workshops on lean manufacturing principles, focusing on minimizing waste and maximizing value creation. - Tools and strategies to implement continuous improvement processes across manufacturing lines. - SMEs diagnostic and action plan development. |

2.1.2.2. The Contractor shall conduct an online training course following the developed and approved by GIZ representatives.

2.1.3. Working Package 3: Virtual exchange with EU Counterparts: facilitating connections between Ukrainian and European businesses to foster knowledge sharing and collaboration

| Implementation period | 12.12.2024 – 25.02.2025 |
| --- | --- |
| Place of provision | anticipated: Ukraine |
| Number of SMEs covered | Up to 15, not less than 10 Ukrainian Women-lead SMEs in Manufacturing |

2.1.3.1. The Contractor will identify relevant SMEs and institutional organizations from EU, finalize the list of selected EU based SMEs in collaboration with GIZ Project Staff, and facilitate the virtual exchange of knowledge and partnership-building between these companies and Ukrainian SMEs.

2.1.3.2. The Contractor will organize online exchange sessions with EU companies, focusing on sharing technological advancements in manufacturing. Topics may include Digital Transformation & AI Integration, Green Technology & Sustainable Manufacturing Practices, and Lean Processes & Operational Efficiency.

2.1.4. Working Package 4:  Mentorship and road map development: leveraging knowledge for Digital, Green, and Lean Transformations, Entering the EU market/export.

| Implementation period | 05.02.2025 – 31.03.2025 |
| --- | --- |
| Place of provision | anticipated: Ukraine |
| Number of SMEs covered | Up to 15, not less than 10 Ukrainian Women-lead SMEs in Manufacturing |

2.1.4.1. The Contractor shall facilitate 4 mentorship sessions (up to 2 hours each) for each participating in the project SME. During these sessions, the mentor in close cooperation with SME will identify industry-specific features and trends, analyze relevant information, and collaboratively develop a Road map.

2.1.4.2. The Contractor, in collaboration with the mentors, has to create a comprehensive template for the Road map and assist each SME in populating it with essential information regarding their business operations.

2.1.4.3. The Contractor shall coordinate with mentors to design and layout the Road map, ensuring it incorporates branding elements and a visually appealing format.

2.1.4.4. The Contractor shall prepare and submit an initial report to GIZ detailing the outcomes and effectiveness of the services rendered under this work package.

2.1.5. Working Package 5:

The Contractor has to develop of a Communication plan and agree it with the GIZ. This plan should include a list of resources for publications and a timeline of publications (not less than 5 publications - 1 program announcement, 1 open call announcement, 2 publications during the training course, 1 post-training publication on the results (success stories) according to GIZ PR guidelines aimed at informing the social media users about the Program conducted, provide photo and/or video content according to GIZ PR guidelines. The topics of the publications are to be determined in cooperation with GIZ. The plan should follow all GIZ requirements for PR materials and their distribution.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| Working Package 1: Open call and SMEs Selection (in acc. to item 2.1.1 of the ToR) | 11.12.2024 / Ukraine / Team leader |
| Working Package 2: Development and conduction of the training course (in acc. to item 2.1.2. of the ToR) | 04.02.2025 / Ukraine / Team leader |
| Working Package 3: Establishing contacts with EU partners to share experiences and introduce innovations (in acc. to item 2.1.3. of the ToR) | 25.02.2025/ Ukraine / Team leader |
| Working Package 4: Mentorship and Roadmap Development: Leveraging Knowledge for Digital, Green, and Lean Transformations (in acc. to item 2.1.4. of the ToR) | 31.03.2025/ Ukraine / Team leader |
| Working Package 5: develop of a communication plan | 10.04.2025/ Ukraine / Team leader |

The contract's duration is from 11.11.2024 till 30.04.2025.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| 1. Interim narrative report on completed activities (Working Package 1 and 2) in acc. to paragraphs 2.1.1. and 2.1.2. of clause 2.1 of the present ToR. | Word file up to 15 pages according to GIZ template pages in English (font Arial, size 11, single-line spacing) with photos and relevant attachments added | 04.02.2025 |
| 2. Final narrative report on completed activities (Working Package 1,2,3,4) in acc. to paragraph 2.1.1, 2.1.2., 2.1.3., 2.1.4.of clause 2.1 of the present ToR | Word file up to 15 pages according to GIZ template pages in English (font Arial, size 11, single-line spacing) with photos and relevant attachments added | 31.03.2025 |
| 3. Communication plan (agree it with the GIZ) and report according to GIZ PR guidelines. (Working Package 5) in acc. to paragraph 2.1.5. of clause 2.1 of the present ToR | Excel file up to 2 pages according to GIZ template pages in English (font Arial, size 11, single-line spacing) | 10.04.2025 |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2.1 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2.1 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2.1 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2.1 (Tasks to be performed) (1.4.2).

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation.

## Project management of the contractor (1.6)

The tenderer is required to explain its approach for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2.1 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the tender; the plan includes information on assignment dates (duration and expert months) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

- Personnel concept (proposed staff)

The tenderer is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

The tenderer is required to gather a project team of up to 6 team members, including team leader, 4 key experts and PR expert.

## Team leader

Tasks of the team leader

- Lead the implementation of activities within the framework of the WEM project. Prepare technical materials and develop the detailed project concept, implementation plan, and agenda.

- Coordinate and maintain communication with GIZ, project partners, stakeholders, and others involved.

- Manage the project team, including planning, steering assignments, and identifying needs.

- Organize selection process of SMEs for participation in the project.

- Develop profile presentations in Ukrainian and English languages for selected women-led SMEs (up to 2 pages each in PDF format ) with an SME profile and an analysis of the needs and development potential of the selected SMEs and submit it to GIZ.

- Conduct training sessions and workshops on export readiness, EU requirements, market access, international networking, and cross-cultural business communication.

- Work with SMEs to develop roadmaps for implementing new knowledge for sustainable transformation, ensuring their alignment with EU market requirements.

- Provide mentorship to SMEs to guide them through the sustainable transformation process, focusing on applying the knowledge gained from the modules and exchange sessions with EU companies in real-world scenarios.

- Ensure regular and comprehensive reporting, adhering to project deadlines and GIZ requirements.

- Facilitate collaboration between Ukrainian SMEs and EU counterparts to enhance knowledge sharing and partnership opportunities.

Qualifications of the team leader

- Education/training (2.1.1): university degree Master’s or equivalent degree in International Affairs, Economics, Finance, Economic Development, or other subject related to the assignment.

- Language (2.1.2): C1-level language proficiency in English and Ukrainian.

- General professional experience (2.1.3): 10 years of professional experience in the trade, manufacturing and matchmaking sector

- Specific professional experience (2.1.4): more than 10 years in implementing projects or coordinating work in projects related to manufacturing and consulting SMEs

- Leadership/management experience (2.1.5): more than 10 years of management/leadership experience as project team leader or manager in a company

- Regional experience (2.1.6): 10 years of experience in projects in Ukraine, of which 2 years in projects in EU.

- Development cooperation (DC) experience (2.1.7): 10 years of experience in DC projects

- Other (2.1.8): 5 years of proven experience in conducting educational activities for business sustainable development.

## Key Expert 1

Tasks of Key Expert 1

- Prepare the technical materials and detailed project concept/ agenda, implementation plan, schedule, etc.

- Prepare and implement activities within the framework of this assignment.

- Develop and conduct the module “Digital Transformation & AI Integration in Manufacturing”

- Conduct tailored mentorship to help manufacturing SMEs develop digital transformation strategies that align with their specific production needs.

- Communication with GIZ project team.

Qualifications of Key Expert 1

- Education/training (2.2.1): Master university degree or equivalent in Industrial Engineering, Manufacturing, Digital Transformation, Data Science, Artificial Intelligence, or other subject related to the assignment.

- Language (2.2.2): B2-level language proficiency in English and C1-level in Ukrainian.

- General professional experience (2.2.3): more than 10 years of professional experience in industrial engineering, manufacturing, digital transformation or data science sector

- Specific professional experience (2.2.4): more than 10 years in digital transformation and AI integration within manufacturing, including developing strategies and implementing industry best practices.

- Leadership/management experience (2.2.5): not applicable

- Regional experience (2.2.6): 10 years of experience in projects in Ukraine and European countries

- Development cooperation (DC) experience (2.2.7): 3 years of experience in DC projects

## Key Expert 2

Tasks of Key Expert 2

- Prepare the technical materials and detailed project concept/ agenda.

- Prepare and implement activities within the framework of this assignment.

- Develop and conduct the module “Sustainable Manufacturing Practices”.

- Provide personalized mentorship to manufacturing SMEs, guiding them in developing and implementing sustainable manufacturing transformations.

- Assist SMEs in identifying actionable steps and strategies for integrating sustainable practices into their business models.

- Communication with GIZ project team.

Qualifications of Key Expert 2

- Education/training (2.3.1): university Master's degree or equivalent in Industrial Engineering, Manufacturing, Sustainable Development, Industrial Ecology, Resource Management, or Business Administration with a focus on sustainability or other subject related to the assignment.

- Language (2.3.2): B2-level language proficiency in English and C1-level in Ukrainian.

- General professional experience (2.3.3): more than 10 years of professional experience in industrial engineering, manufacturing, industrial ecology, resource management, or business administration

- Specific professional experience (2.3.4): more than 10 years in green transformation within manufacturing, including developing strategies and implementing industry best practices.

- Leadership/management experience (2.3.5): not applicable

- Regional experience (2.3.6): 10 years of experience in projects in Ukraine and European countries

- Development cooperation (DC) experience (2.3.7): 3 years of experience in DC projects

## Key Expert 3

Tasks of Key Expert 3

- Design and implement activities within this assignment's framework, focusing on lean manufacturing principles.

- Develop and conduct the “Lean Processes & Operational Efficiency in Manufacturing” module emphasizing waste reduction and value maximization.

- Facilitate practical workshops that teach participants how to apply lean manufacturing principles in their operations.

- Provide personalized mentorship to manufacturing SMEs, guiding them in identifying inefficiencies and developing actionable strategies for lean transformation.

- Assist SMEs in conducting diagnostic assessments to evaluate their current manufacturing processes and create tailored action plans for improvement.

- Communicate regularly with the GIZ project team to ensure alignment and progress on project objectives.

Qualifications of Key Expert 3

- Education/training (2.4.1): University Master’s degree or equivalent in Business Administration, Industrial Engineering, Manufacturing, Operations Management, or a related field.

- Language (2.4.2): B2-level language proficiency in English and C1-level in Ukrainian

- General professional experience (2.4.3): more than 10 years of professional experience in manufacturing, industrial engineering, or operations management.

- Specific professional experience (2.4.4): more than 10 years of experience in implementing lean manufacturing principles, developing efficiency strategies, and driving operational improvements

- Leadership/management experience (2.4.5): not applicable

- Regional experience (2.4.6): 10 years of experience in projects in European countries

- Development cooperation (DC) experience (2.4.7): 3 years of experience in DC projects

## Key Expert 4

Tasks of Key Expert 4

- Prepare and implement activities within the framework of Working Package 3.

- Identify relevant EU-based SMEs, finalize the list of selected EU companies in collaboration with GIZ Project Staff, and facilitate virtual knowledge exchange and partnership-building between these companies and Ukrainian SMEs.

- Organize and conduct virtual exchange with EU Counterparts, focusing on sharing advancements in manufacturing technologies. Topics include Digital Transformation & AI Integration in Manufacturing, Green Technology & Sustainable Manufacturing Practices, Lean Processes & Operational Efficiency, and Export promotion.

- Support the Team Leader in the overall coordination of project activities, contributing to the development of technical materials, reports, and project documentation.

- Collaborate with the GIZ project team to ensure alignment on goals, project timelines, and deliverables.

- Provide insights and recommendations to improve the effectiveness of the project’s training and exchange components, helping to align them with EU market access and capacity-building objectives.

Qualifications of Key Expert 4

- Education/training (2.5.1): university degree Master’s or equivalent degree in International Affairs, Economics, Finance, Economic Development, or other subject related to the assignment.

- Language (2.5.2): C1-level language proficiency in English and Ukrainian

- General professional experience (2.5.3): more than 10 years of professional experience in the trade, manufacturing and matchmaking sector

- Specific professional experience (2.5.4): more than 10 years in conducting international study visits, matchmaking with EU-based SMEs, entities, and EU accession

- Leadership/management experience (2.5.5): not applicable

- Regional experience (2.5.6): 10 years of experience in projects in European countries

- Development cooperation (DC) experience (2.5.7): 3 years of experience in DC projects

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Socio-cultural skills

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

PR Expert (Key Expert 5)

Tasks of PR Expert

- Develop and execute communication plan to enhance the visibility of the WEM Project and its mission of empowering women-led manufacturing SMEs.

- Manage the project’s public relations efforts, including crafting press releases, news articles, newsletters, and social media content highlighting key activities, achievements, and success stories.

- Coordinate communications with GIZ, project partners, stakeholders, and participating SMEs, ensuring timely updates and a consistent narrative.

- Create content for marketing materials such as press releases, success stories, and profiles of women-led SMEs, showcasing their potential and achievements.

- Oversee the development of communication materials in both Ukrainian and English, including translating key documents when necessary.

- Ensure alignment with EU communication standards and practices, especially concerning sustainable development and the promotion of women’s entrepreneurship.

Qualifications of PR Expert

- Education/training (2.6.1): A university degree (Master’s or equivalent) in Communications, Public Relations, Journalism, Marketing, or a related field.

- Language (2.6.2): C1-level fluency in both Ukrainian and English is required, with strong written and verbal communication skills

- General professional experience (2.6.3): more than 10 years of professional experience in public relations, media, or communication roles.

- Specific professional experience (2.6.4): more than 10 years experience in developing and implementing PR strategies for projects focused on entrepreneurship, women’s empowerment, or manufacturing.

- Regional experience (2.6.5): 3 years of experience in projects on international development projects, especially with GIZ or other EU-funded initiatives

# Costing requirements

## Assignment of personnel and travel expenses

Travels are not foreseen. All activities will be online.

## Sustainability aspects for travel and travel regulations

If applicable on ground of these Terms of Reference the following travel regulations are to be observed. See Annex 1 to these Terms of Reference.

Specification of inputs

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| Designation of TL | Expert-days | 1 | 60 |  |
| Designation of key expert 1 | Expert-days | 1 | 30 |  |
| Designation of key expert 2 | Expert-days | 1 | 30 |  |
| Designation of key expert 3 | Expert-days | 1 | 30 |  |
| Designation of key expert 4 | Expert-days | 1 | 30 |  |
| Designation of PR expert (key expert 5) | Expert-days | 1 | 20 |  |

## There is no contractual right to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

# Inputs of GIZ or other actors

Not Applicable

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the commercial bid.

Anticipated payment schedule:

The payments are to be done after the completion of each work package.

In consideration of services completed, the Contractor shall be paid in the following instalments:

| Instalment # | Anticipated payment date | Payment of up to % from total contract value | Deliverables and reporting | Project Number and % of costs split (if applicable) |
| --- | --- | --- | --- | --- |
| 1 Interim payment | 24.02.2025 | 43 % | Acc. to deliverables 1 of clause 2.2 | 18.2197.4-010.00 |
| 2. Final payment | 25.04.2025 | 57 % | Acc. to deliverables 2, 3 of clause 2.2 | 18.2197.4-010.00 |

  - Financial proposal

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, but excl. VAT

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of reports accepted by GIZ;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done on the ground of the scanned invoices and acts of acceptance submitted in digital form within 7-10 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Invoices, acts of acceptance and timesheets, etc.shall be scanned as one PDF document (up to 4 mb) and send as an attachment to the e-mail of the GIZ Project Representatives (the e-mail shall be provided additionally) together with other financial supporting documents as and if stipulated by the Contract; the technical documents (reporting/ deliverables) can be submitted either in the same or in a separate e-mail;

- The e-mail body/ text from the Contractor should also contain the following:

- List of the attached documents incl. title of the document, number, date of issue, amount UAH;

- Confirmation, that the services/ works/ goods specified in the attached documents were provided/ delivered/ supplied in full;

- Full name, position, contact details, full name of the organization.

- Confirmation, that the original documents (invoices, 2 copies of acts of acceptance, other financial supporting documents) will be kept by the Contractor and submitted later as soon as the security situation permits upon the request of GIZ. The deadline and the address for the delivery of documents will be agreed between GIZ and the Contractor via e-mail.

- Each invoice and act of acceptance shall contain the Project Number 18.2197.4-010.00

- By submitting the Invoice the Contractor should indicate (in the invoice or in the e-mail) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

- In case the Contracts is a VAT Payer at the moment of the Invoice issuing, the VAT exemption clause shall be applicable and the Contractor should also submit the Tax Invoice to GIZ as soon as that is available.

Timesheet standard template can be found here https://www.giz.de/en/worldwide/63065.html

- Other Provisions

  - General

The Contract will be signed by the Parties as a soft copy version by sending to each other by electronic means signed and scanned copies of the Contract and annexes. Such Contract shall have full legal force as the hard copies of it. The hard copies will be submitted as soon as the security situation in Ukraine stabilizes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine and Supplements to General Terms of contract governing Contracts with Appraisers/Firms of Consultants (local) published on the link  Закупівлі - giz.de (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor _______ (indicate name/-s, surname/-s, phone/-s, e-mail/-s)

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU;

- not be in the process of termination;

- not be registarted on temporary occupaied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, a citizen of the Russian Federation, except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation.

GIZ reserves the right to verify this information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

The given procurement of services/ works upon the Contract shall be carried out at the funds of the funds of the Project of International Technical Assistance (Project ITA), PN: 2018.2197.4 ENI/2020/418-940, Project title “Utilization and Implementation of the Association Agreement between European Union (EU) and Ukraine in the field of trade / EU4Business: Small and medium sized enterprises (SME) Competitiveness and Internationalisation”, registered by the by Directorate for Coordination of International Technical Assistance to the Cabinet of Ministers of Ukraine (Registration Card of the ITA Project (program) No. 4545-10 dated 11.03.2024) and complies with the category (type) of Services specified in the Procurement Plan of the Project as services for organizing project events: conferences, seminars, round tables, exhibitions, forums, etc.; services for organizing personnel and partner trips (tickets, accommodation, transportation, and other logistical services) available at address of the Governmental Portal: https://www.kmu.gov.ua/diyalnist/mizhnarodna-dopomoga/pereliki-zareyestrovanih-proektiv-z-planami-zakupivel

The above-mentioned ITA project is implemented within the Framework Agreement between the Government of Ukraine and the Government of the Federal Republic of Germany on Counselling and Technical Cooperation dated 29/05/1996 and Framework Agreement between the Government of Ukraine and the Commission of European Communities ratified by the Law of Ukraine № 360-VI of 03.09.2008.

The given procurement of services/ works upon the Contract shall be determined free from VAT under provisions of cl.197.11 Art. 197 of the Tax Code of Ukraine. Operations for providing services under this Agreement are subject to VAT exemption.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, then the Contractor must notify GIZ of such VAT registration in writing or in electronic form by means of submission of an e-mail with copy of the Excerpt from VAT Registration Registry to the GIZ’s e-mail address indicated in the details of the Contract. The Contractor must submit the mentioned notification to the GIZ not later than 1 calendar day following the day of VAT registration.

At the same time the Parties agreed that the purchase of Services after the VAT registration of the Contractor shall be exempt from VAT in accordance with the abovementioned.

# Outsourced processing of personal data

The performance of the contract may involve the processing of personal data by the contractor, such as (but not limited to) names and contact details, where the nature of such data and the way such processing is carried out shall be solely determined by the contractor. In such cases, the contractor shall act as an independent data controller and shall be solely responsible for complying with all applicable data protection obligations, including those arising from regional and local laws. The contractor shall only process personal data if a specific objective cannot reasonably be achieved without such data. Data protection principles such as lawfulness, data minimisation, accuracy, purpose limitation, storage limitation, transparency, integrity and confidentiality and accountability, as well as the numerous rights of the data subject, must be duly taken into account.

The data transfer rules of the GDPR must be considered whenever personal data is transferred from the EU to a third country. GIZ is in no way responsible for such processing. If the contractor carries out the instructions of a GIZ partner regarding such processing, the partner is the data controller, and the data processing must be carried out in accordance with the instructions of the partner and the laws and standards to which it is subject. If the contractor is not subject to the GDPR and the applicable laws do not contain an explanation of the data protection principles and rights mentioned here, the definitions and meanings provided by the GDPR (Regulation (EU) 2016/679) may be helpful. GIZ is available to assist the Contractor as needed.

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- tentative work plan;

- personnel (team) concept

- CVs of all experts with relevant work experience, qualifications (education, certificates).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English (language).

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise, the bid will be disqualified.

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Commercial bid must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

    - Documents for tenderer’s eligibility confirmation

| The tenderer is obliged to conform to the following eligibility requirements: | The tenderer must provide the following document to confirm the compliance with eligibility requirements: |
| --- | --- |
| Successfully implemented at least 2 (two) projects focused on capacity-building and/or export readiness for Ukrainian SMEs. | Self-declaration of eligibility The Tenderer must provide at least 2 (two) letters of recommendation from previous clients or partners, attesting to the successful execution of similar projects (In Annexes to Self-Declaration of eligibility). |
| Successfully implemented at least 2 (two) projects involving international matchmaking between SMEs and potential business partners, investors, or international markets. | Self-declaration of eligibility The Tenderer must provide at least 2 (two) letters of recommendation from previous clients or partners, attesting to the successful execution of similar projects (In Annexes to Self-Declaration of eligibility). |
| Annual turnover has been more than 50, 000 EUR/ 2,300.000 (two million three hundred thousand UAH) on average over the last three financial years. | Self-declaration of eligibility |
| At least 2 (two) employees in average over the last 10 years | Self-declaration of eligibility |

- Annexes

- Annex 1 – Communication guidelines.

- Annex 2 - Communication and Visibility Plan.