| ProjectPro for SMEs that are working in critical infrastructure, focuses on rebuilding, energy efficiency, manufactory and food processing | Project number/ cost centre: 18.2197.4-010.00 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

- Context

The GIZ programme “EU4Business: SME Recovery, Competitiveness, and Internationalisation” aims to support the recovery and growth of Ukrainian SMEs by enhancing their competitiveness and facilitating their access to the EU market.

Small and medium-sized enterprises (SMEs), especially those that are working in critical infrastructure, focuses on rebuilding, manufactory, energy efficiency and food processing are the backbone of Ukraine’s economy, accounting for a significant portion of employment and economic activity. With the ongoing war and post-crisis recovery efforts, the role of SMEs is even more critical. They are key drivers of innovation, economic resilience, and community-level growth.

Despite the critical role SMEs play, many faces significant difficulties in accessing finance due to a lack of awareness of available funding opportunities, complex application processes, and stringent international standards they struggle to meet. Many SMEs lack experience in writing competitive grant proposals and managing project budgets that align with EU requirements. Financial illiteracy and limited access to capital further compound these challenges, making it difficult for them to secure loans or attract investors. Without proper training in project cycle management (PCM), they are unable to plan, execute, and report on projects efficiently, which is critical for gaining funder trust. Training and consultations will empower SMEs with the skills and knowledge needed to overcome these barriers, allowing them to access essential financing and manage projects successfully.

In light of the ongoing challenges, the programme will launch the ProjectPro for SMEs. This initiative will provide essential training and consultations to help Ukrainian SMEs navigate project cycle management (PCM) and Access to Finance, ultimately increasing their capacity to secure EU funding and implement successful projects.

Mastering project cycle management is crucial for Ukrainian SMEs to thrive in a competitive, international market. It equips them with essential skills to plan, manage, implement and present projects efficiently, ensuring better resource allocation, timely execution, and successful outcomes. Learning PCM also improves their ability to prepare grant applications, which can unlock EU funding opportunities, supporting growth and expansion in sectors vital for Ukraine’s recovery and long-term development.

Project Objective

Main objective of the ProjectPro is to empower Ukrainian small and medium-sized enterprises (SMEs) operating in critical sectors, such as infrastructure, energy efficiency, food processing, manufactory and rebuilding efforts with the necessary skills and tools to enhance their project management capabilities. By equipping them with project cycle management (PCM) knowledge, the initiative aims to improve their ability to design, plan, and execute strategic projects that align with EU funding requirements. This, in turn, will increase their competitiveness, facilitate their access to international markets, attract financial recourses (grants, vouchers, loans) and support Ukraine’s broader economic recovery and development goals.

About the SMEs that will be targeted by the Programme

- The Programme proposed in response to this tender should aim to support up to 50 SMEs that are working in critical infrastructure, focuses on rebuilding, energy efficiency, manufactory and food processing

- The target SMEs should have 5 to 249 employees and fall into one of the following categories.

- Companies from all regions under government control in Ukraine may be considered.

- It is important to note that the proposed Programme should consider the specific needs and challenges of each targeted SME and provide tailored support accordingly.

Project Outcomes

Up to 50 Ukrainian SMEs will acquire essential project cycle management (PCM) skills, enabling them to effectively develop and submit high-quality grant applications.

Up to 50 SMEs will receive in-depth consultations and will develop improve capability to design, plan, and execute projects aligned with EU standards.

Submission of not less 8 and up to 16 high-quality grant applications for funding and available calls for proposals, thereby increasing competitiveness of the SMEs and their capacity to grow and innovate within the EU market.

Not less 8 and up to 16 SMEs will train their presentation skills and present their projects on the final online pitching event

- Tasks to be performed by the contractor

2.1 Work package 1. Identification of Ukrainian SMEs that are working in critical

infrastructure, focuses on rebuilding, energy efficiency, manufactory and food processing

2.1.1 The Contractor shall develop the project team that will work on the goals and tasks set out in the TOR with clear identification of roles and responsibilities

2.1.2 Contractor shall conduct a comprehensive Open Call campaign to attract SMEs from all over Ukraine to apply for participation in the Programme.

Contractor must develop and present Application Form and evaluation criteria (subject for approval with GIZ)

The eligibility criteria for SMEs are as follows:

- The company is registered entity in Ukraine and under Ukrainian law. At least 51% of the company's beneficiaries are Ukrainian citizens.  The company is qualified as a small or medium-sized enterprise (SME) according to the Ukrainian law.

- The company has been actively operating in Ukraine for at least 2 years.

- The company operates in critical infrastructure, focuses on rebuilding, energy efficiency

and food processing.

- The company, it's owner's and final beneficiaries are not in EU and Ukrainian sanction lists.

- The company is not located and does not operate in the temporarily occupied territories of Ukraine; does not operate or has its subsidiaries in the Russian Federation and/or Belarus; does not operate in the countries on the sanction lists.

- The priority will be given to SMEs which operates in Ukrainian cities with a population less than 250 000 inhabitants.

- The company is not in the process of termination or bankruptcy, is not bankrupt, and has no tax debts; is not a defendant in lawsuits and enforcement proceedings related to corruption offenses

- The company have not received support from EU4Business since February 1, 2022

- SMEs cannot apply if their activity is related to the production of weapons, military ammunition and dual-purpose products, coke and refined petroleum products, alcoholic beverages, mainly by fermentation, beer, and wine as well as production of distilled alcoholic beverages, tobacco products, medicine, pharmaceutical products, gambling industry, pesticides.

2.1.3 Received application form should be evaluated by 3 independent experts engaged by the Contractor according to the evaluation criteria approved by GIZ.

2.1.4 Based on the independent evaluation Contractor will also develop the final list of 50 winners (+ *reserve list up to 10 SMEs). Subject for approval with GIZ.

2.1.5. Organize set of PR & Communication activities to ensure spread the information throughout relevant channels and attracting SMEs to provide applications according to GIZ templates.

2.2 Work package 2. Development and facilitation training course on Project Cycle Management and Access to Finance for Ukrainian SMEs

2.2.1 Develop training course including modules and individual consultations for up to 50 SMEs.

2.2.2 Develop and facilitate training modules online (6 modules up to 2 hours each) for 2 groups of up to 25 participants each. Training modules should include agenda, content and learning materials (workbook, templates etc.).

Trainings must include the following topics:

- Introduction to Project Cycle Management (PCM)

- Project Planning & Proposal Writing

- Financial Management & Budgeting for Projects

- Project Implementation & Monitoring

- Access to Finance for SMEs (overview of available funding opportunities for SMEs, focusing on EU grants and other financial assistance programs and How SMEs Can Become Bankable for Financial Institutions and Grant Programs)

- Other relevant topics

Topics and schedule of the modules are subject to further approval by GIZ.

2.2.3 Conduct and facilitate up to 50 Individual Consultations according to previously scheduled with GIZ.

As a result of the consultations, it is expected that up to 50 SMEs will develop a tailor-made project proposal and project budget according to their needs. Focus areas include project objectives, alignment with funders’ priorities, budget finalization, and risk assessment).The Contractor needs to provide a roster/list of individual consultants per thematic area with sector specific knowledge. The Contractor shall undertake best endeavours to find suitably qualified and experienced consultant(s) as per the topics for consultancy demanded and justified by SMEs in their application forms, within a reasonable period of time.

Evaluators that will be engaged in assessing of the applications and project team members could not be considered as potential consultants under providing individual consultations

For indicative purposes:

Tentative number of man-hours used by each consultant on individual consultation is estimated in 8 hours (1 working days).

One company can receive only one individual consultation.

2.2.4 Based on the results of training course Contractor should define not less than 8 and up to 16 SMEs for individual mentorship support.

Contractor should develop selection criteria for not less than 8 up to 16 SMEs which will take individual mentorship support.

2.2.5 Conduct and facilitate not less 8 and up to 16 mentoring sessions according to previously scheduled with GIZ.

As a result of the mentoring sessions, not less 8 and up to 16 SMEs will prepare high-quality grant applications tailored that will be submitted to open call of proposals to existing grants, including a fully developed project proposal, budget, and timeline and will be submitted to grant funding. Additionally, not less 8 and up to 16 presentations for pitching event will be developed.

For indicative purposes:

Tentative number of man-hours used by each consultant on mentoring sessions is estimated in  24 hours (3 working days).

2.2.6 Collect feedback from the participants to assess the effectiveness of the learning program and individual mentoring. The items for collection of feedback are to be approved with GIZ

2.3 Work Package 3. Organizing pitching online event where not less 8 and up to 16 participants will present their projects

2.3.1 Organize and conduct pitching online event where not less 8 and up to 16 participants will present developed projects in the format of a presentation for GIZ representatives, partners and contractor will share the overall results of the Programme.

2.3.2 Prepare a detailed report in accordance with GIZ template summarizing activities, outcomes, and recommendations

2.3.3 Prepare not less than 5 successful projects according to GIZ format.

2.3.4 Maintain close communication with GIZ team, Consultants, Evaluators and 50 SMEs throughout all activities

- The contractor is responsible for selecting, preparing, training and steering the experts assigned to perform the advisory tasks.

- The contractor provides equipment and supplies (consumables) and assumes the associated operating and administrative costs.

- The contractor manages costs and expenditures, accounting processes and invoicing in line with the requirements of GIZ.

- The Contractor shall ensure the development of communications materials where necessary within the Programe.

- The Contractor shall develop documentation and reporting according to GIZ templates including interim reports, final report and assessment of the Programe's overall impact. The Contractor should consider that evaluation of the Programe after contract expiration by GIZ will take place and consultants will be interviewed about the quality of the Programe on the part of the Contractor, at the same time, GIZ should be informed if Contractor makes internal evaluation activities.

- The Contractor shall develop up to 5 publications in English and Ukrainian languages according to GIZ PR guidelines aimed at informing the social media users about the Programme conducted, provide photo and/or video content according to GIZ PR guidelines. The topics of the publications are to be determined in cooperation with GIZ.

- The Project reserves the right to request any information on a current status of the ongoing process by the Contractor at any time.

- In case of existing questions of need in clarification, Contractor should contact GIZ as soon as possible to resolve questions and inaccuracies.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/partial works | Anticipated deadline/place/person responsible | Criteria for acceptance |
| --- | --- | --- |
| 2.1.1 The Contractor shall develop the project team that will work on the goals and tasks set out in the TOR with clear identification of roles and responsibilities | 7 calendar days after the contract is signed / Team Lead / Key experts | 2.1.1 Online meeting conducted with GIZ where the team is presented |
| 2.1.2 Contractor shall conduct a comprehensive Open Call campaign to attract SMEs from all over Ukraine to apply for participation in the Programme. | 25 calendar days after the contract is signed / Team Lead / Key experts | 2.1.2 List of questions and selection criteria in Word format in English Text of the open call announcement, approved by GIZ |
| 2.1.3 Received application form should be evaluated by 3 independent experts engaged by the Contractor according to the evaluation criteria approved by GIZ. | 30 calendar days after the contract is signed / Team Lead / Key experts | 2.1.3 Evaluation summary from experts in Excel |
| 2.1.4 Based on the independent evaluation Contractor will also develop the final list of 50 winners (+ reserve list up to 10 SMEs). Subject for approval with GIZ. | 30 calendar days after the contract is signed / Team Lead / Key experts | 2.1.4 The list of final selected participants of the Programme in Excel format in English (+ reserve list up to 10 SMEs) |
| 2.1.5 Organize set of PR & Communication activities to ensure spread the information throughout relevant channels and attracting SMEs to provide applications according to GIZ templates. | 25 calendar days after the contract is signed / Team Lead / Key experts | Brief interim report on points 2.1.1-2.1.5 of up to 5 pages in Word format in English Developed script and visual of the announcement about the 50 selected participants aimed at publishing on EU4Business social media in English and Ukrainian |
| 2.2.2 Develop and facilitate training modules online (6 modules up to 2 hours each) for 2 groups up to 25 participants each. Training modules should include agenda, content and learning materials (workbook, templates etc.). | 100 calendar days after the contract is signed / Team Lead / Key experts | 2.2.2 Developed 6 agendas and presentations for online training modules in Word or PDF format in English according to PR guidelines Up to 5 photos from each of the training modules uploaded to cloud List of participants in GIZ template |
| 2.2.3 Conduct and facilitate up to 50 Individual Consultations according to previously scheduled with GIZ. | 100 calendar days after the contract is signed / Team Lead / Key experts | 2.2.3 Up to 50 elaborated project proposals and budgets in Word/Excel format |
| 2.2.4 Based on the results of training course Contractor should define not less than 8 and up to 16 SMEs for individual mentorship support. | 105 calendar days after the contract is signed / Team Lead / Key experts | 2.2.4 List of participants in Excel format and developed selection criteria in Word format |
| 2.2.5 Conduct and facilitate not less 8 and up to 16 mentoring sessions according to previously scheduled with GIZ. | 127 calendar days after the contract is signed / Team Lead / Key experts | 2.2.5 Developed and submitted not less 8 and up to 16 grant proposals in Word/Excel format, and PPT presentations for final pitching event |
| 2.2.6 Collect feedback from the participants to assess the effectiveness of the learning program and individual consultations. The items for collection of feedback are to be approved with GIZ | 140 calendar days after the contract is signed / Team Lead / Key experts | 2.2.6 Provide the report on the results of the evaluation of Participants in Word format in English |
| 2.3.1 Organize and conduct final pitching online event where not less 8 and up to 16 participants will present developed projects in the format of a presentation for GIZ representatives, partners and contractor will share the overall results of the Programme. | 130 calendar days after the contract is signed / Team Lead / Key experts | 2.3.1 Developed agenda for final online event in Word or PDF format in English according to PR guidelines Up to 10 photos/screenshots from final online event uploaded to cloud |
| 2.3.2 Prepare a detailed final report in accordance with GIZ template summarizing activities, outcomes, and recommendations) | 130 calendar days after the contract is signed / Team Lead / Key experts | 2.3.2 Developed final report in Eng of up to 15 pages according to GIZ template Photo and/or video content developed and provided to GIZ by email |
| 2.3.3 Prepare 5 successful projects in UKR/ENG according to GIZ format. | 140 calendar days after the contract is signed / Team Lead / Key experts | 2.3.3 Developed 5 successful projects according to GIZ templates |

Implementation period: from 18.11.2024 until 18.04.2025.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| 2.1 Work package 1 2.1.1-2.1.5 1. List of questions and selection criteria in Word format in English 2. The list of final selected participants of the Programme in Excel format in English 3. Narrative interim report on points 2.1.1- 2.1.5; at least 5 pages 4. Script and visual of the announcement about the 50 selected participants aimed at publishing on EU4Business social media in English and Ukrainian | - Document in Word format in English - Document in Excel format in English - Document in Word format in English up to 5 pages - Document in Word format in Ukr/Eng up to 1 pages, visual in JPEG/PNG format | 31.12.2024 |
| 2.2 Work package 2. 2.2.2 - 2.2.6 1. Agendas for 6 online trainings in Word or PDF format in English according to PR guidelines Photos from each of the training modules uploaded to cloud 2. List of training participants in GIZ template 3. up to 50 developed project prototypes 4. Not less than 8 and up to 16 developed projects submitted 5. Interim narrative report on points 2.2.1-2.2.6 on results of the performed services, including data on achieved outputs, results | - 6 documents in Word format in English Up to 10 screenshots/photos from the webinars - Document in Excel format 3. up to 50 documents in Word/Excel format in in Eng of up to 10 pages 4. Not less than 8 and up to 16 documents in Word/Excel format and PPT presentations for the final pitching event 5. Document in Word format in in Eng of up to 15 pages | 25.03.2025 |
| 2.3 Work Package 3. 2.3.1-2.3.4 1. Agenda for final online event in Word or PDF format in English according to PR guidelines 2. Up to 10 photos from final online event uploaded to cloud 3. Up to 5 publications provided to GIZ by email in English and Ukrainian 4. 5 successful projects 5. Final narrative report on results of the performed services, including data on achieved outputs, results | - Document in Word format in English - Up to 10 screenshots/photos. Photo and/or video content provided to GIZ by email - Links on Facebook publications made by Contracor - Document in Word format Ukr/Eng - Document in Word format in Eng of up to 15 pages according to GIZ template | 04.04.2025 |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation.

## Project management of the contractor (1.6)

The tenderer is required to explain its approach for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the tender; the plan includes information on assignment dates (duration and expert months) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

Personnel concept (proposed staff)

The tenderer is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 9), the range of tasks involved and the required qualifications.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team leader

Tasks regarding the team lead

- Overall responsibility for the work packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Regular reporting in accordance with deadlines

- Responsibility for checking the use of funds and financial planning with the officer responsible for the commission at GIZ Tasks regarding the international trade expertise

- Management of experts and activities for development and implementation of the training activities and individual consultations

- Participating in activities withing WP 1 and WP2, WP3

- Development and follow up on operational plan

- Reporting Support

Qualifications of the Team Leader

- Education/training (2.1.1): University degree (master’s or equivalent) in Economics, Management, International Trade or similar

- Language (2.1.2):  C1 - level language proficiency in English

- General professional experience (2.1.3): 10 years of professional experience in private sector development and/or project management

- Specific professional experience (2.1.4): 7 years of professional experience in organizing educational trainings on project management and access to finance

- Leadership/management experience (2.1.5): 5 years of management/leadership experience as project team leader or a manager in a company

## Project assistant

Tasks of key expert 1

- Support Team Leader to plan and monitor the activities of the contract;

- Support in organization and coordination activities of experts/consultants;

- Support in data and information gathering;

- Support in communication with SMEs and the experts/consultants;

- Communication with experts/consultants;

- Communication with GIZ project team;

- Reporting to GIZ for provided services

Qualifications of key expert 1

- Education/training (2.2.1): Diploma or BA degree in Economics, Finance, Economic Development, Public Administration or other subjects;

- Language (2.2.2):  C1-level language proficiency in Ukrainian;

- General professional experience (2.2.3): 5 years of experience in project management;

- Specific professional experience (2.2.4): 2 years of experience in assisting in coordinating of projects in multi-stakeholders’ environment;

- Other (2.2.8): Knowledge of Microsoft tools indicated in CV

## Short-term expert pool with minimum 7, maximum 12 members

Please send a CV for each pool member (see below Chapter 10 Requirements on the format of the bid).

The bidder is expected to provide CVs of up to 9 experts for providing webinars/ individual consultations/mentorship sessions indicated in cl. 2.2.1-2.2.5, CVs of up to 3 individual evaluators for preparation of the criteria and assessment of the applications received during Open Call.

Evaluators engaged for the assessment of the applications, could not provide individual consultations in terms of cl. 2.1.3. CVs of consultant shall cover different areas of expertise and shall meet the requirements described below.

Tasks of the short-term expert pool

- Provide technical expertise and consulting in their specific fields of competence according to the needs of the tasks

- Provide specific market experience (sectoral as well as regional) to the Ukrainian SMEs;

- Agree on results and KPIs to be achieved;

- Be engaged in process of developing of the selection criteria’s and selection process of the SMEs

- To analyse all materials (application form, eligibility criteria), hold preparatory meetings with the Contractor and GIZ team, if needed;

- Provide individual process of all received SMEs’ applications

- Provide ranked list of the evaluated companies, 50 winners and reserve list with up to 10 companies.

- Provide reporting documents including the deliverables.

- Provide training and individual consultations on project management and access to finance (sectors critical infrastructure, focuses on rebuilding, manufactory, energy efficiency and food safety)

Qualifications of the short-term expert pool

- Education/training (2.6.1): all experts with university degree (German ‘Diplom’/Master) in Economics, Finance, Economic Development, Food production, Processing, Law or similar

- Language (2.6.2):  all experts with C1 -level language proficiency in Ukrainian

- General professional experience (2.6.3): all experts with more than 10 years of professional experience in work with/in private and/or public sector

- Specific professional experience (2.6.4): up to 3 experts with 1 project experience in developing and/or conducting of evaluation processes; up to 9 experts with 5 years of professional experience in providing training and/or consulting and/or advisory support on project management and access to finance (sectors critical infrastructure, focuses on rebuilding, energy efficiency and food processing)

- Other (2.6.7): all experts with proven experience in drafting comprehensive recommendations for SMEs on grant management, access to finance (sectors critical infrastructure, focuses on rebuilding, manufacture, energy efficiency and food processing); experience of successful submission of grant applications and received funding

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Socio-cultural skills

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

The tenderer must provide a clear overview of all proposed short-term experts and their individual qualifications.

# Costing requirements

## Assignment of personnel and travel expenses

All business travel must be agreed in advance with the staff member responsible for the project.

## Sustainability aspects for travel and travel regulations

If applicable on ground of these Terms of Reference the following travel regulations are to be observed. See Annex 1 to these Terms of Reference.

The following basic calculations for the contract for works are a reference value based on the acceptance criteria for each partial work/milestone specified in Chapter 2 (Tasks to be performed by the contractor).

Since the contract to be concluded is a contract for works, we would ask you to offer your services at a lump sum price.

| Milestones/partial works | Estimated expert days for orientation | Anticipated deadline/place/person responsible |
| --- | --- | --- |
| Identification of Ukrainian SMEs that are working in critical infrastructure, focuses on rebuilding, manufacture, energy efficiency and food processing | - Team Lead (8 days) - Project assistant/Expert 1 (8 days) - Short-term expert pool (12 days) | 31.12.2024/Ukraine/Team Leader |
| Development and facilitation training course on Project Cycle Management and Access to Finance for Ukrainian SMEs and providing individual consultation | - Team Lead (13 days) - Project assistant/Expert 1 (15 days) - Short-term expert pool (107 days) | 25.03.2025/Ukraine/Team Leader |
| Organizing pitching online event where not less 8 and up to 16 participants will present their projects | - Team Lead (8 days) - Project assistant/Expert 1 (5 days) | 04.04.2025/Ukraine/Team Leader |

# Inputs of GIZ or other actors

Not Applicable

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the commercial bid.

Anticipated payment schedule:

In consideration of work completed, the Contractor shall be paid in the following instalments:

| Instalment # | Anticipated payment date | Payment of up to % from total contract value | Deliverables and reporting | Project Number and % of costs split (if applicable) |
| --- | --- | --- | --- | --- |
| 1 Interim payment | 10.01.2025 | 20 % | Acc. to cl. 2.1 Section Deliverables and Reporting | 18.2197.4-010.00 |
| 2 Final payment | 15.04.2025 | 80% | Acc. to cl. 2.2- 2.3 Section Deliverables and Reporting | 18.2197.4-010.00 |

  - Financial proposal

The total cost of the Contract is set in UAH including all direct and related expenses, taxes and fees, but excl. VAT .

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

The total value of the bid shall not exceed the maximum acceptable amount of 1,501,418. 00  UAH. Price bids exceeding this amount shall not be accepted.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of reports accepted by GIZ;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done on the ground of the scanned invoices and acts of acceptance submitted in digital form within 10 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Invoices, acts of acceptance  etc. shall be scanned as one PDF document (up to 4 mb) and send as an attachment to the e-mail of the GIZ Project Representatives (the e-mail shall be provided additionally) together with other financial supporting documents as and if stipulated by the Contract; the technical documents (reporting/ deliverables) can be submitted either in the same or in a separate e-mail;

- The e-mail body/ text from the Contractor should also contain the following:

- List of the attached documents incl. title of the document, number, date of issue, amount UAH;

- Confirmation, that the services/ works/ goods specified in the attached documents were provided/ delivered/ supplied in full;

- Full name, position, contact details, full name of the organization.

- Confirmation, that the original documents (invoices, 2 copies of acts of acceptance, other financial supporting documents) will be kept by the Contractor and submitted later as soon as the security situation permits upon the request of GIZ. The deadline and the address for the delivery of documents will be agreed between GIZ and the Contractor via e-mail.

- By submitting the Invoice the Contractor should indicate (in the invoice or in the e-mail) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

Timesheet standard template can be found here https://www.giz.de/en/worldwide/63065.html

- Other Provisions

  - General

The Contract will be signed by the Parties as a soft copy version by sending to each other by electronic means signed and scanned copies of the Contract and annexes. Such Contract shall have full legal force as the hard copies of it. The hard copies will be submitted as soon as the security situation in Ukraine stabilizes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine published on the link  Закупівлі - giz.de (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor Ilona Knyshuk +380632549422 ilona.knyshuk@giz.de

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU;

- not be in the process of termination;

- not be registarted on temporary occupaied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, a citizen of the Russian Federation, except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation.

GIZ reserves the right to verify this information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

7.2.1 The given procurement of services/ works upon the Contract shall be carried out at the funds of the Project of International Technical Assistance (ITA Project), PN: 2018.2197.4 ENI/2020/418-940, Project title “Utilization and Implementation of the Association Agreement between European Union and Ukraine in the field of Trade/ EU4Business: SME Recovery, Competitiveness and Internationalization”, registered by the by ​Directorate for Coordination of International Technical Assistance to the Cabinet of Ministers of Ukraine ​(Registration Card of the ITA Project (program) No. 4545-12 dated 03.07.2024) and complies with the category (type) of Services specified in the Procurement Plan of the Project as “Consulting Services” available at address of the Governmental Portal: https://www.kmu.gov.ua/diyalnist/mizhnarodna-dopomoga/pereliki-zareyestrovanih-proektiv-z-planami-zakupivel.

7.2.2 The above-mentioned ITA Project is implemented within the Framework Agreement between the Government of Ukraine and the Government of the Federal Republic of Germany on Counselling and Technical Cooperation dated 29/05/1996 and ​Framework Agreement between the Government of Ukraine and the Commission of European Communities ratified by the Law of Ukraine № 360-VI of 03.09.2008​.

7.2.3 The given procurement of services/ works upon the Contract shall be determined free from VAT under provisions of cl.197.11 Art. 197 of the Tax Code of Ukraine. Operations for providing services under this Agreement are subject to VAT exemption.

# 7.3. Outsourced processing of personal data

7.3.1The performance of the contract may involve the processing of personal data by the Contractor, such as (but not limited to) names and contact details, where the nature of such data and the way such processing is carried out shall be solely determined by the Contractor. In such cases, the Contractor shall act as an independent data controller and shall be solely responsible for complying with all applicable data protection obligations, including those arising from regional and local laws.

7.3.2The Contractor shall only process personal data if a specific objective cannot reasonably be achieved without such data. Data protection principles such as lawfulness, data minimization, accuracy, purpose limitation, storage limitation, transparency, integrity and confidentiality and accountability, as well as the numerous rights of the data subject, must be duly taken into account. The data transfer rules of the GDPR must be considered whenever personal data is transferred from the EU to a third country. GIZ is in no way responsible for such processing. If the contractor carries out the instructions of a GIZ partner regarding such processing, the partner is the data controller, and the data processing must be carried out in accordance with the instructions of the partner and the laws and standards to which it is subject. If the contractor is not subject to the GDPR and the applicable laws do not contain an explanation of the data protection principles and rights mentioned here, the definitions and meanings provided by the GDPR (Regulation (EU) 2016/679) may be helpful. GIZ is available to assist the Contractor as needed.

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- personnel (team) concept

- CVs of all experts with relevant work experience, qualifications (education, certificates).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 0 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up English (language).

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Commercial bid must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

    - Documents for tenderer’s eligibility confirmation

| The tenderer is obliged to conform to the following eligibility requirements: | The tenderer must provide the following document to confirm the compliance with eligibility requirements: |
| --- | --- |
| Provide the list of implemented projects aimed at SME support in Ukraine | 2 relevant projects of SME support in Ukraine including KPIs, target audience |
| Provide project on providing consultations on Project management/Grant Writing and Access to Access to Finance for Ukrainian SMEs | 1 relevant project on providing consultations on Project Management/Grant Writing for Ukrainians SMEs |
| Contracor should be registered in Ukraine at least 2 years | Provide a registration documents (Registration Card, Statute) |

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU;

- not be in the process of termination;

- not be registarted on uncontrolled territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, a citizen of the Russian Federation, except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation.

GIZ reserves the right to verify this information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

It is expected that 50 companies participate in the program, based on the ranked list provided after the evaluation process by the independent evaluators. The reserve list with 10 companies is needed in case when one of the first 50 companies, according to the provided list, will reject it’s participation. In that case the next company with the highest rank from the reserve list will take it’s place.