| DEVELOPMENT OF CONTENT FOR E-LEARNING COURSE ON CENTRALIZED PUBLIC PROCUREMENT VIA PROZORRO MARKET Human capacity development (HCD): Yes No | Project number/ cost centre: 2021.2146.5-001.00 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	    Commissioning party

AN	    Contractor

AVB	    General terms and conditions of contract (‘local terms and conditions’) for  supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	    Expert

FKT	    Expert days

GIZ	    Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH

GovTech Project    “Good Governance through GovTech and Transparency” Project

KZFK	   Short-term expert

n/a		        not applicable

PM		        Prozorro Market

SI		        State Institution

PP		        public procurement

ToRs	   Terms of reference

- Context

The Ukrainian-German technical cooperation Project “Good Governance through GovTech and Transparency” (the GovTech Project) launched in 2023 is implemented by the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH on behalf of the German Government. Its goal is to strengthen the use of data- and technology-based solutions for an inclusive and transparent recovery as part of joint efforts by key actors from the public sector and civil society. State Institution (SI) “Professional Procurement”, a public institution under authority of the Ministry for Economy of Ukraine, is one of essential GovTech Project’s partners.

Pandemic COVID-19 has accelerated online formats of communication. Becoming effective to continue with human capacity development in times of the pandemic, e-learning remains relevant in war times. Learners can participate online from any place where an Internet connection is available. Benefiting from just-in-time learning they can access courses in the moment they need, rather than physical events in fixed dates and places what due to security reasons might be unsafe. Furthermore, online courses may have higher effectiveness and outreach rather than traditional ones, as they are usually available for longer periods with higher number of participants.

ProZorro is an online public procurement (PP) platform and collaboration environment that ensures open access to tenders in Ukraine. Being a part of Prozorro, an e-catalogue of goods Prozorro Market (PM) was designed to simplify work of the PP entities. It is a systematic database of profiles for standardized categories of goods e.g. electricity, oil, food. PM works like an online store for the PP entities and is the fastest and the most effective tool for competitive tenders for goods. PM database is being formed and filled by administrators of the e-catalogue - Centralized purchasing authorities. One of them is SI "Professional Procurement" that is administering categories like electricity, oil, food, construction goods etc.

Due to a tendency to savings and effectiveness of PP of goods via PM, there is a need to involve more PP entities and businesses in usage of PM, as well as raise awareness among public how and what does the state spends public costs on. E-learning course on centralized PP via PM could be a solution to cover the need to (purposes):

- provide the target audience with a general and comprehensive understanding about philosophy of centralized procurement, main directions of development of PP system and benefits of using e-catalogue PM;

- develop capacities of PP entities on how to use PM to cover their needs more effectively;

- raise awareness among target audiences about PM and its opportunities.

Target audience: PP entities, private business, civil society organizations, public.

Results to be expected after participants complete e-learning course successfully:

- gained knowledge on how quickly and efficiently conduct PP of goods by using PM;

- enhanced level of professionalism of PP entities and their experience in PP via PM;

- increased level of awareness of target audience about PM opportunities;

- increased usage of PM leading to higher performance of public administration and cost efficiency due to savings of working time and public finance.

- Tasks to be performed by the Contractor

The aim of the assignment is to develop content for e-learning course on centralized public procurement via Prozorro Market. The e-learning course content means production of 13 videos, one promotional video and 3 Reels consisting of all necessary elements defined below. Methodological and educational materials for conceptual filling the course will be provided to the Contractor after signing the Contract. The course is expected to be interactive, consist of educational series, tests for each educational series and a final test, so that the developed content could be posted on Dia.Education platform and social media later on. A decision on course format will be taken at the initial stage of cooperation after the Contract has been signed.

  - Tasks

The Сontractor is responsible for providing the following scope of works:

2.1.1 The Contractor shall coordinate activities with a representative of the GovTech Project, GIZ who together with SI "Professional Procurement" will accept/not accept/request improvements to the deliverables under the Contract and tasks completion by the Сontractor;

Although GIZ is the Сustomer, the Contractor shall perform the scope of works under the contract ensuring close coordination and transparent communication with the following stakeholders:

- SI "Professional Procurement";

- Dia.Education team;

- GovTech Project, GIZ

This requires a dedicated Team Leader from the side of the Contractor, whom the stakeholders can address questions and suggestions. Within the 1st kick-off meeting all aspects of the scope of works will be discussed with the Contractor. According to experience, some stages may go quicker and more smoothly if creative experts (scriptwriter, designer etc.) attend common meetings and thus understand tasks and requirements better. So, it is desired not to limit communication with creative experts in written form only.

2.1.2 The Contractor shall not approve and not perform any changes to the scope of work proposed by the Сontractor itself and/or the stakeholders. Changes in the scope of work can be done only in supplement to the Contract what is a subject for prior negotiations with GIZ.

2.1.3 The Contractor shall elaborate а general concept based on a filming format approved by stakeholders, а detailed storyboard and 13 original scenarios in Ukrainian including literary editing for all 13 educational series and one promotional video based on the conceptual content prepared by SI „Professional Procurement”;

2.1.4 The Contractor shall perform filming of 13 videos with duration 5-8 minutes each based on the approved scenario and storyboards, as well as one promotional video with duration of 30-60 seconds; these videos shall contain Ukrainian subtitles;

2.1.5 The Contractor shall perform dubbing with voice-over into English (no original Ukrainian sound shall be heard) for 13 videos and one promo-video, translation of 13 original scripts with literary editing into English shall be ensured; all 13 dubbed videos shall contain English subtitles; one promo-video shall have dubbing with voice-over without English subtitles; the Contractor shall provide the stakeholders with min. 3 options of actor’s voices for choosing;

2.1.6 The Contractor shall perform all steps of postproduction of videos in line with the approved concept and storyboards, including editing the footage according to scenarios, professional coloring, adding graphic design, creation motion design, and assuring qualitative sound design of the product; all the sounds and music of the e-learning course shall be either produced as unique element of the final product, or copyrights for usage of existing sounds and music shall be ensured for unlimited time.

2.1.7 The Contractor shall transform speakers’ presentations in a uniform style based on visual guidelines (will be shared with the Contractor after signing the Contract).

2.1.8 The Contractor shall take photos of speakers (approx.10 persons) including backstage photos during video filming and further editing these photos, as well as produces three short videos in Reels format for further usage in social media;

2.1.9 The Contractor shall assure quality of the produced content and make changes in unlimited quantities according to the feedback provided by the stakeholders.

2.1.10 The Contractor shall incorporate Dia.Education branding into content of the e-learning course according to Dia.Education visual guidelines (will be shared with the Contractor after signing the Contract). Placing of partners logos in defined spaces of e-learning course shall be foreseen and this will be discussed with the Contractor after signing the Contract.

2.1.11 The Contractor shall communicate with the GIZ counterparts according to specified platforms (e.g. e-mail, MS Teams) which are preferred and transparently visible to GIZ.

The Contractor shall treat all written and oral information received during the assignment as confidential and is not allowed to disclose any information to third parties. The knowledge received as written or oral information (collectively, the Information) is not considered to be public, but confidential. Unless required by law or under written consent of the GIZ, all information will be kept confidential. Upon GIZ consent in any publication on services provided, the Сontractor shall always indicate in an appropriate manner that it is conducting or has conducted its activities within the framework of the GovTech Project implemented by GIZ on behalf of the Government of the Federal Republic of Germany. The Сontractor shall respect the visibility guidelines of GIZ and agree e.g. on wording, layout of logos and/or other visualization items in advance with GIZ. The Сontractor shall not under any circumstances publicly engage in political discussions or politically sensitive issues with the potential to disrupt ongoing work.

2.1.12 The Сontractor shall list all the deliverables developed within this contract in the Handover record. They shall be accepted by SI “Professional Procurement” prior to being included into the Handover record. All deliverables will be reviewed and approved by the GovTech Project, GIZ.

The Сontractor shall transfer all the deliverables prepared and created in the framework of this contract to GIZ officially via the Handover record including transfer of all related rights and intellectual property rights. The transfer of work results from the Contractor to GIZ is completed after the transfer of a data carrier (e.g. USB Flash drive) containing all deliverables/work results under the contract as well as signing Act of acceptance of works and Handover record. All deliverables shall remain in property of GIZ after completion of the assignment.

The rights for the work results of the Сontractor belong exclusively to GIZ. The Сontractor shall assign to the GIZ an exclusive, assignable, sublicensable right without content-related restriction to reproduce, distribute, make publicly accessible, process and redesign the work results, including studies, drafts, documentation, articles, information, files, illustrations, drawings, calculations, materials and other documents (“work results”) that are produced in connection with the performance of the Contract. The materials and documents, deliverables elaborated shall be considered as GIZ property and shall not be used by the awarded contractor or any other legal entity or private person without prior written approval by the GIZ. GIZ receives all exclusive intellectual property rights, including those provided by the current legislation of Ukraine (in particular, but no limited to the Civil Code of Ukraine, the Law of Ukraine ”On Copyright Law and Related Rights”) in full to all materials, works and developments created by the Contractor, during the period of this contract assignment.

The Сontractor has no right to continue using objects of intellectual property created under this contract for commercial purposes or for any other purpose, or in any other way without the written consent of GIZ.

2.1.13 The Contractor manages costs and expenditures, accounting processes and invoicing in line with the requirements of GIZ.

MILESTONES

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/partial works | Anticipated deadline/place/person responsible | Criteria for acceptance |
| --- | --- | --- |
| 1.Prototyping content of 13 videos and one promotional video This stage is aimed to form common understanding of all stakeholders on the final product. At this stage, a course format and approaches shall be selected and approved on to how conceptual content with methodological and educational materials will be converted to video format. | December 2024 – January 2025. Deadline can be reviewed with approval of the GovTech Project, GIZ depending on circumstances. Kyiv Contractor | A general concept of the e-learning course that includes sub-concepts of each of 13 videos and one promotional video with an implementation plan consisting of work steps, indicative schedule, division of responsibilities between team members is elaborated by the Contractor and approved by the stakeholders. |
| 2.Detailed storyboard for 13 videos and one promotional video Detailed storyboard for 13 videos and one promotional video with an advanced scenario that contains all the final versions of narratives, and how each scene in the final video will look like, designing layouts for different scenes should be developed at this stage. The storyboard includes suggestions and references to how people in different scenes are filmed, examples of the potential studio the video will be shoot at, design of titles, headings and graphic (other interactive and visual elements) and other important aspects which may better convey the idea of the product. Since e-learning course consists not only of videos, the detailed storyboard should also foresee all other assets of the product: questions and answers for quizzes, texts for course pages, etc. | January - February 2025. Deadline can be reviewed with approval of the GovTech Project, GIZ depending on circumstances. Kyiv Contractor | Detailed storyboard for 13 videos and one promotional video is developed by the Contractor and approved by the stakeholders. |
| 3.Visual design for 13 videos, one promotional video and three Reels for social media about the course (design layouts) This stage is aimed to form the final visual concept for 13 videos, one promotional video and three short videos in Reels format: get graphic and motion design approved, adjusting visual layouts according to the feedback received from the stakeholders until the final version is approved. Videorecording of the content according to the approved storyboard on the agreed filming location and taking photos of speakers including backstage is the final step of this stage (approx. 10 speakers are expected). | February - March 2025. Deadline can be reviewed with approval of the GovTech Project, GIZ depending on circumstances. Kyiv Contractor | Visual concept for 13 videos, one promotional video and three Reels that includes layouts of all visual and interactive elements is developed by the Contractor and approved by the stakeholders |
| 4.Production of a test version of content for e-learning course Creating illustrations, audios, videos, animations, interactive and visual elements etc. Preparation of content-specific graphics, charts, animations, etc. Editing photos of all e-learning course speakers (e.g. to be put on the title of the e-learning course). Creation of three Reels for promotion of the e-learning course. Creation of one promotional video. Translation of content into English with literary editing. | March - April 2025. Deadline can be reviewed with approval of the GovTech Project, GIZ depending on circumstances. Kyiv Contractor | A test version of content for e-learning course including 13 videos, one promotional video and three Reels are developed by the Contractor and sent to the stakeholders for checking and commenting. |
| 5.Production of content of the final version of e-learning course All changes are made for content of e-learning course according to comments provided by the stakeholders. Dubbing with voice over in English with English subtitles for 13 educational series has been made. Dubbing with voice over in English without subtitles for one promotional video has been made. The final product consists of an Ukrainian version of the content of e-learning course and an English version of the content of e-learning course (dubbing with voice over and English subtitles). | April - May 2025. Deadline can be reviewed with approval of the GovTech Project, GIZ depending on circumstances. Kyiv Contractor | The final version of e-learning course is developed by the Contractor and approved by the stakeholders. The final product is handed over to the GovTech Project, GIZ. |

The contract duration is from 01.12.2024 till 15.06.2025.

TECHNICAL REQUIREMENTS

The Contractor shall meet the following technical requirements and have available material and technical base (own or leased) as specified below.

Requirements for filming video

The Contractor shall use modern technology and tools for filming the e-learning course. For this, the following shall be met:

- The final video should be dynamic and shoot from different angles; minimum of three cameras needed.

- Light scheme should be set professionally and require a minimum of eight light sources;

- The picture must be crisp, and the video should be taken in 4k with further downscaling to 1080p on postproduction. Filming equipment used in production must be selected to meet the mentioned requirement: Sony e-mount cameras, Fujifilm X-mount cameras, Blackmagic EF-mount cameras (not limited/or equivalent) which support 4k shooting. List of lenses may be used: Optics Sigma 18-35 f1.7, or Sony 16-35 f 2.8, or Zeiss Batis 25 mm f 2 E mount, or Zeiss Batis 40 mm f 2 E mount, or Canon EF 24-70mm f / 2 8L 82 mm, or Canon EF 70-200mm f / 2 8 IS 77 mm (not limited/or equivalent).

- Audio recording devices should be properly selected to record the qualitative low-noise sound. Recorded audio must not contain hiss, reverberation, unwanted noise, clipping, picking; edited audio must not contain pops (P-sounds) and esses (S-sounds) produced by actors. We expect the Contractor foresees situations with spoiled audio and use modern recording equipment that allows to record audio in 32 bit, or equipment that records backup audio file with lower audio levels.

Types of microphones can be used:

a) For boom pole recording: microphones with Equivalent Noise Level not more than 16dBA (Rode NT5 or NTG3 or Audio-Technica AT4053B or similar which feet for indoor shooting) - not limited/or equivalent;

b) For lavaliere microphones: microphones with Equivalent Noise Level not more than 27dBA (Rode, Sennheiser) - not limited/or equivalent. Lavaliere microphones should be put on actors in a way their movements do not produce unwanted interference and noise in the audio;

c) If microphones are in use with wireless transmitters, the input noise level must not be higher than 20dBA. Some manufacturers may not specify this characteristic for their products; make sure systems you use offer a signal to noise ratio of more than 110dB(A);

Requirements for media files

| Name | SD |
| --- | --- |
| Container | *.MP4 |
| Codec | H264 |
| Resolution and Field rate | 625 @ 25i fps |
| Bitrate | 25 Mbps Constant Bit rate |
| Screen dimensions | 1920 x 1080p |
| Aspect Ratio | 16:9 |
| Aspect Ratio Bits | Correctly set to Material Aspect Ratio |
| Interlacing | Progressive |
| Audio Encoding |  |
| Codec | uncompressed |
| Bit | 16 bit |
| Sample Rate | 48 000 Hz |
| Channel Configuration | 1&2 (dual mono) or Stereo 1&2 (1=L, 2=R) |
| Audio reference level | -18dBfs |
| Peak audio level | Compressed peaks, reference -15dBfs |
| Audio pre-emphasis | None |

Requirements for location

The Contractor shall provide the stakeholders with min. 3 options for filming location. Location shall be with availability of power sources in case of power cuts, space for light equipment shall be sufficient, as well as have possibility for free usage of other technical means needed for ensuring continuous filming process.

  - Deliverables and Reporting:

The Contractor is responsible for the following:

| # | Reporting/ Deliverable | Requirements to the format | Anticipated period, by |
| --- | --- | --- | --- |
| 1 | Interim Report General concept, storyboard and visual design as deliverables (see details in the table above, milestones 1-3) | The Interim Report shall be in writing in English in digital form max.2 pages, where the Contractor describes measures carried out and results achieved in the certain time. All documentation related to carrying out the scope of works and evidence of delivery of related deliverables shall be documented and annexed to the Interim Report. All deliverables must be accepted by SI "Professional Procurement" prior to being included into the Interim Report. Data formats for the Interim Report and their annexes are Word, PowerPoint, PDF, while all the products, templates and materials developed in the framework of this Contract should be transferred to the GIZ officially including the transfer of intellectual property rights. These materials should be provided to GIZ in original format, vector or any other editable relevant format (if relevant). | March 2025 upon completion of milestones 1-3 specified in the table above. The Interim Report and relevant deliverables shall be provided together with financial reporting documents for relevant interim payment (see item 7.4). |
| 2 | Final Report Test version and final version of the e-learning course as deliverables (see details in the table above, milestones 4-5) | The Final Report shall indicate all measures carried out and all results achieved within the whole contract period. The Final Report shall be in writing in English in digital form max.2 pages. All documentation related to carrying out the scope of works and evidence of delivery of related deliverables shall be documented and annexed to the Final Report. All deliverables must be accepted by SI "Professional Procurement" prior to being included into the the Final Report. Data formats for the Final Report and its annexes are Word, PowerPoint, PDF, while all the products, templates and materials developed in the framework of this contract should be transferred to the GIZ officially including the transfer of intellectual property rights. These materials should be provided to GIZ in original format, vector or any other editable relevant format (if relevant). | May 2025 upon completion of milestones 4-5 specified in the table above. The Final Report and all related deliverables shall be provided for final payment together with financial reporting documents (see item 7.4) |

The Contractor shall be able to report in oral and/or in writing, in English, to the GovTech Project, GIZ and/or SI "Professional Procurement" about the progress under the contract upon request.

- Concept (technical-methodological design) – Not Applicable

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualification. CVs should serve as evidence that the proposed personnel suit to fulfil the tasks under the Contract. The CV must contain information about below listed qualification criteria that represent the requirements to reach the maximum number of points in the technical assessment of staff (see section 2. Assessment of proposed staff of the document “Grid of technical assessment”). The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team Leader – PROJECT MANAGER/PRODUCER

## See item 2.1. Team Leader, section 2. Assessment of proposed staff in the document ”Grid of technical assessment”

Tasks of the Team Leader - Project Manager/Producer:

- Overall responsibility for the assignment of the Contractor (quality and deadlines);

- Coordinating and ensuring communication with GIZ and other stakeholders involved;

- Personnel management, in particular, identifying the need for involving personnel to perform the tasks within the contract and available budget, as well as planning and steering assignment and supporting personnel;

- Overall project management, planning, implementation and follow up of activities;

- Elaboration of implementation plan, preparation, improvement and maintenance of project documentation and regular reporting in accordance with deadlines;

- Quality assurance of the product and its compliance with ideas and expectations of stakeholders within all stages of production;

Qualifications of the Team Leader - Project Manager/Producer (confirmed in CV):

- Education/training (2.1.1): Master’s degree in Film/TV Producing, Management, Journalism, PR, Marketing, Economics, Social Sciences or related field;

- Language (2.1.2): B1-level language proficiency in English;

- General professional experience (2.1.3): 5 years of professional experience in the video production sector;

- Specific professional experience (2.1.4): 3 years in managing projects as Project Manager/Producer;

- Development cooperation (DC) experience (2.1.7): 3 online courses produced in cooperation with international organizations, international technical assistance projects or similar;

- Other (2.1.8): management of production of 3 e-learning courses posted on Dia.Education or similar educational platforms as Project Manager/Producer.

Expert 1 – VIDEO PRODUCTION DIRECTOR

## See item 2.2 Expert 1, section 2. Assessment of proposed staff in the document ”Grid of technical assessment”

Tasks of the expert 1 – Video Production Director

- Monitoring of performance of creative team, so that they implement the product according to an idea during production, postproduction and finalization of the product;

- Management of processes on filming location;

- Generating ideas for elaboration of deliverables (general concept etc.), participation in work of creative experts (screenwriter, designer etc) and quality control over deliverables;

- Participation at work of the creative team within post-production (editing);

- Quality assurance of produced deliverables according to storyboards, design and stakeholders’ expectations;

Qualifications of the expert 1 – Video Production Director (confirmed in CV):

- Education/training (2.2.1): Bachelor’s degree in Film/TV Direction, Journalism, PR, Marketing, Management, Social Sciences or related field;

- General professional experience (2.2.3): 5 years of professional experience in the video production sector;

- Specific professional experience (2.2.4): 3 years in the video production sector as Video Production Director;

- Other (2.2.8): engagement in production of 3 e-learning courses posted on Dia.Education or similar educational platforms as Video Production Director.

Expert 2 – SCREENWRITER

## See item 2.3 Expert 2, section 2. Assessment of proposed staff in the document ”Grid of technical assessment”

Tasks of the expert 2 - Screenwriter

- Work with provided thematical and educational content and participation in elaboration of general course concept and relevant specifications;

- Elaboration and writing of scenarios, scripts and other course content, work with presentations and other course interactions;

- Work with visual references and elaboration of instructions for graphic designer;

- Adoption of learning content and literary editing according to actual linguistic and stylistic requirements, orthography, punctuation;

Qualifications of the expert 2 – Screenwriter (confirmed in CV):

- Education/training (2.3.1): Master’s degree in Journalism, PR, Marketing, Management, Social Sciences or related field;

- General professional experience (2.3.3): 5 years of professional experience in the video production sector;

- Specific professional experience (2.3.4): 4 years in producing online courses as Screenwriter;

- Other (2.3.8): engagement in production of 3 e-learning courses posted on Dia.Education or similar educational platforms as Screenwriter.

Expert 3 – CAMERAMAN

## See item 2.4 Expert 3, section 2. Assessment of proposed staff in the document ”Grid of technical assessment”

Tasks of the expert 3 - Cameraman

- Work with different camera types, light equipment and other relevant equipment needed for qualitative ensuring of filming process;

- Setting of scenes and lighting according to requirements for reaching visual goals of stakeholders;

- Recording of qualitative video production, promo video;

- Providing technical support where it is needed;

Qualifications of the expert 3 – Cameraman (confirmed in CV):

- General professional experience (2.4.3): 5 years of professional experience in the video production sector;

- Specific professional experience (2.4.4): 4 years in video production as Cameramen;

- Other (2.4.8): engagement in production of 3 e-learning courses posted on Dia.Education or similar educational platforms as Cameraman.

Expert 4 – EDITING DIRECTOR

## See item 2.5 Expert 4, section 2. Assessment of proposed staff in the document ”Grid of technical assessment”

Tasks of the expert 4 – Editing Director

- Maintenance and managing video recordings

- Work on postproduction, preliminary and final editing of the filmed material;

- Processing and editing of digital content (videos, graphics etc), setting colors, adding graphic, preliminary voice over, adding subtitles, other interactive and visual elements etc;

- Making relevant corrections and creation of the final version of the product;

- Editing of short videos in Reels format for further posting on social media;

Qualifications of the expert 4 – Editing Director (confirmed in CV):

- General professional experience (2.5.3): 5 years of professional experience in the video production sector;

- Specific professional experience (2.5.4): 3 years in video production sector as Editing Director;

- Other (2.5.8): engagement in production of 3 e-learning courses posted on Dia.Education or similar educational platforms as Editing Director.

Expert 5 – GRAPHIC/MOTION DESIGNER

## See item 2.6 Short-term expert pool 1, section 2. Assessment of proposed staff in the document ”Grid of technical assessment”

Tasks of the expert 5 – Graphic/Motion Designer

- Adaptation of visualization according to visual guidelines, development of design concept of the online course;

- Creation of graphic and work with graphic and motion design of creative content for deliverables;

- Development of design layouts of online course;

- Engagement in post-production for meeting stakeholders expectations;

Qualifications of the expert 5 – Graphic/Motion Designer (confirmed in CV):

- Education/training (2.6.1): completed trainings on Graphic/Motion Design or similar;

- Specific professional experience (2.6.4): 3 years in production sector as graphic/motion designer;

- Other (2.6.7): engagement in production of 3 e-learning courses posted on Dia.Education or similar educational platforms as Graphic/Motion Designer.

Expert 6 – SOUND DIRECTOR

## See item 2.7 Short-term expert pool 2, section 2. Assessment of proposed staff in the document ”Grid of technical assessment”

Tasks of the expert 6 – Sound Director

- Work on filming location and performing work with sounds, assembling of sound equipment,

- Setting voices and sounds, responsible for sound quality,

- Sound recording on filming location and at studio for voice over,

- Post-handling of sounds, including light sound design.

- Making relevant changes and creation of the final version of the sound;

- Bringing together the final version of the sound.

Qualifications of the expert 6 – Sound Director (confirmed in CV):

- General professional experience (2.7.3): 5 years of professional experience in the sound production;

- Specific professional experience (2.7.4): 2 years in production sector as Sound Director;

- Other (2.7.7): work on 3 e-learning courses posted on Dia.Education or similar educational platforms as Sound Director.

Soft skills of team members:

In addition to their specialist qualifications, the following qualifications are required of team members:

- Teamwork

- Initiative

- Communication skills

- Socio-cultural skills

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

# Costing requirements

## Assignment of personnel and travel expenses

No business trips are foreseen.

Specification of inputs

The following basic calculations for the contract for works are a reference value based on the acceptance criteria for each partial work/milestone specified in Chapter 2 (Tasks to be performed by the contractor).

Since the contract to be concluded is a contract for works, we would ask you to offer your services at a lump sum price.

|  | Item | Unit | Quantity |
| --- | --- | --- | --- |
| 1 | Milestone 1/partial works 1 Prototyping content of 13 videos and one promotional video | item | 1 |
| 2 | Milestone 2/partial works 2 Detailed storyboard for 13 videos and one promotional video | item | 1 |
| 3 | Milestone 3/partial works 3 Visual design for 13 videos, one promotional video and three Reels for social media about the course (design layouts) | item | 1 |
| 4 | Milestone 4/partial works 4 Production of a test version of content for e-learning course | item | 1 |
| 5 | Milestone 5/partial works 5 Production of content of the final version of e-learning course | item | 1 |

# Inputs of GIZ or other actors

GIZ and/or other actors are expected to make the following available:

- provide the Contractor with a thematical concept of the course, its structure, methodological and educational content, topics of the videos. So, there is no need to interview experts to develop a structure of the course by the Contractor and no need in development of a prototype of the product by a methodologist from Contractor’s side; SI “Professional Procurement” provides the Contractor with the conceptual, methodological and educational content for transforming it in video scenarios for filming.

- SI “Professional Procurement” defines speakers of the course and coordinates them (approx.10 speakers).

- It will not be a task of the Contractor to elaborate a knowledge evaluation system in frames of the course (educational tests, tasks for participants).

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the commercial bid.

Anticipated payment schedule:

In consideration of work completed, the Contractor shall be paid in the following instalments:

| Instalment # | Anticipated payment date | Payment of up to % from total contract value | Deliverables and reporting | Project Number and % of costs split (if applicable) |
| --- | --- | --- | --- | --- |
| 1 Interim payment | 30 March 2025 | upon completion of milestones 1-3 | Acc. to cl.2.2 above | PN 2021.2146.5-001.00 |
| 2 Final payment | 30 May 2025 | upon completion of milestones 4-5 | Acc. to cl. 2.2 above | PN 2021.2146.5-001.00 |

  - Financial proposal

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of reports accepted by GIZ;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done on the ground of the scanned invoices, acts of acceptance and reports submitted in digital form within 7-10 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Invoices, acts of acceptance shall be scanned as one PDF document (up to 4 mb) and send as an attachment to the e-mail of the GIZ Project Representatives (the e-mail shall be provided additionally) together with other financial supporting documents as and if stipulated by the Contract; the technical documents (reporting/ deliverables) can be submitted either in the same or in a separate e-mail;

- The e-mail body/ text from the Contractor should also contain the following:

- List of the attached documents incl. title of the document, number, date of issue, amount UAH;

- Confirmation, that the services/ works/ goods specified in the attached documents were provided/ delivered/ supplied in full;

- Full name, position, contact details, full name of the organization.

- Confirmation, that the original documents (invoices, 2 copies of acts of acceptance, other financial supporting documents) will be kept by the Contractor and submitted later as soon as the security situation permits upon the request of GIZ. The deadline and the address for the delivery of documents will be agreed between GIZ and the Contractor via e-mail.

- 	Each invoice and act of acceptance shall contain the Project Number 2021.2146.5-001.00 and Contract number

-	By submitting the Invoice the Contractor should indicate (in the invoice or in the e-mail) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

- Other Provisions

  - General

The Contract will be signed by the Parties as a soft copy version by sending to each other by electronic means signed and scanned copies of the Contract and annexes. Such Contract shall have full legal force as the hard copies of it. The hard copies will be submitted as soon as the security situation in Ukraine stabilizes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force. The Contract enters into force from the date of its signing by all the Parties.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine published on the link  Закупівлі - giz.de (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor Nadiia Rozhko (nadiia.rozhko@giz.de, phone +380 44 2874237).

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU;

- not be in the process of termination;

- not be registarted on temporary occupaied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, a citizen of the Russian Federation, except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation.

GIZ reserves the right to verify this information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

GIZ bears no responsibility for personal data being processed by the contractor within the contract. The contractor shall furthermore not disclose any personal data to GIZ other than on a legitimate legal basis and in keeping with applicable data protection requirements such as sufficient privacy notice.

  - VAT Exemption - Not Applicable

# Outsourced processing of personal data - Not Applicable

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the technical bid containing CVs of all experts with relevant work experience, qualifications (education, certificates), soft skills (see requirements in Chapter 4 above). Technical bid must be signed and stamped (if stamp is used). The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise, the bid will be disqualified.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs shall not exceed 2 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up either in English or Ukrainian.

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation. Commercial bid must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

    - Documents for tenderer’s eligibility confirmation

| The tenderer is obliged to conform to the following eligibility requirements: | The tenderer must provide the following document to confirm the compliance with eligibility requirements: |
| --- | --- |
| Experience in cooperation with international technical assistance projects/organizations and/or public institutions and/or civil society organizations in implementation of similar e-learning projects | Portfolio of at least 3 reference projects in the field e-learning implemented in cooperation with international technical assistance projects/organizations e.g. GIZ, USAID, UNDP and/or public institutions and/or civil society organizations in the last 3 years in Ukraine. |
| Availability of minimum material and technical base (owned or leased) to be used to confirm meeting technical requirements according to Chapter 2. - Minimum three cameras: Sony e-mount cameras, Fujifilm X-mount cameras, Blackmagic EF-mount cameras (not limited/or equivalent) which support 4k shooting; - Lenses: Optics Sigma 18-35 f1.7, or Sony 16-35 f 2.8, or Zeiss Batis 25 mm f 2 E mount, or Zeiss Batis 40 mm f 2 E mount, or Canon EF 24-70mm f / 2 8L 82 mm, or Canon EF 70-200mm f / 2 8 IS 77 mm (not limited/or equivalent); - Minimum of eight light sources; - Audio recording devices; - Microphones for boom pole recording: microphones with Equivalent Noise Level not more than 16dBA (Rode NT5 or NTG3 or Audio-Technica AT4053B or similar which feet for indoor shooting) - not limited/or equivalent; - Lavaliere microphones: microphones with Equivalent Noise Level not more than 27dBA (Rode, Sennheiser) - not limited/or equivalent: | List of equipment to be used within the Contract in accordance to technical requirements in the Chapter 2. |

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU;

- not be in the process of termination;

- not be registered on uncontrolled territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, a citizen of the Russian Federation, except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation.

GIZ reserves the right to verify this information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.