| Preparing and organizing the participation of SMEs in Spielwarenmesse 2025 International Toy Fair | Project number/ cost centre: 18.2197.4-010.00 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	  Commissioning party

AN	  Contractor

AVB	  General Terms and Conditions of Contract for supplying services and work

BIO        Business Intermediate Organisation(s)

DCFTA  Deep and Comprehensive Free Trade Agreement

EEPO	  Entrepreneurship and Export Promotion Office

EU	  European Union

GDPR   EU General Data Protection Regulation

SME	 Small and medium-sized enterprise

ToRs	 Terms of reference

- Context

The objective of the EU-BMZ co-funded GIZ Programme “EU4Business: Small and medium-sized enterprises (SME) Recovery, Competitiveness and Internationalisation / Utilization and Implementation of the Association Agreement between European Union (EU) and Ukraine in the field of trade” (hereafter “the EU4Business Programme”) is to enhance Ukrainian SME’s competitiveness and to facilitate their access to the EU´s internal market. A special emphasis will be put on strengthening the capacities of Ukrainian SMEs to comply with the EU-Ukraine Deep and Comprehensive Free Trade Agreement (DCFTA).

Currently, political decision makers are lacking steering competencies while Ukrainian private companies lack the necessary technical knowledge to comply with required EU exporting standards. Whilst various Ukrainian institutions and business support organizations, like e.g., Entrepreneurship and Export Promotion Office (EEPO) and the Ukrainian Chamber of Commerce and Industry (UCCI), had started training local export advisers and offering some demand-oriented services to export-oriented companies, these services are not yet sufficient in terms of quantity and quality due to a lack of knowledge, skills (marketing) and institutional capacities. Ukraine is thus not yet able to capitalize on the economic opportunities provided by the EU-Ukraine DCFTA.

The EU4Business Programme pursues a multi-level, multi-actor approach, intervening on different levels and with different organizations. On the macro level Ukrainian ministries (e.g., Ministry of Economy of Ukraine, Ministry of Digital Transformation) and state entities such as the EEPO are being supported. On the meso-level, SME clusters with export potential are strengthened in their capacities, as are business intermediate organizations (BIOs) and other Ukrainian export-oriented institutions and business support organizations, with whom the EU4Business Programme closely cooperates.

On the micro level, the EU4Business Programme supports SMEs via two types of assistance – financial support combined with advisory support. It supports business continuity of micro businesses hit worst by the crisis, supports the providers of basic supplies by micro and small firms and stimulates economic recovery (via SME with growth potential) in the medium term through:

1. Financial liquidity ensuring business continuity of micro and small businesses affected by the war and securing basic supplies (short-term impact).

2. Support of investment and internationalization projects of SME to raise their competitiveness in international (EU) markets (short- to mid-term impact).

3. Key market connections to kick-start a more enabling environment for export-oriented sectors (mid-term impact).

The onset of war and the ensuing economic upheaval has compelled SMEs to shift their focus from expansion to ensuring business continuity, sustainability, and recovery, particularly for internally displaced enterprises. The russian invasion has caused disruptions to trade routes, extensive infrastructure damage, labor migration, and the disruption of value chains. In such challenging conditions, enhancing international trade has indeed become significantly formidable task.

Among Ukraine’s export-oriented industries, the toy sector stands out for its export potential, with SMEs aiming to penetrate the EU market through value-added products that meet European standards. Industry associations in this sector play a key role in fostering shared goals, supporting networking opportunities, and enabling SMEs to pool resources and knowledge, which is especially vital for meeting international standards and strengthening partnerships.

Given the toy industry’s export potential, SME internationalization in this sector is critical for fostering partnerships and knowledge exchange. Active participation in trade missions, exhibitions, and other export-oriented events – especially major international exhibitions such as Spielwarenmesse 2025 in Germany – serves as an effective strategy to drive the sector’s internationalization and growth in the European market. Collaborative efforts within associations and industry groups further support SMEs in navigating complex export requirements, ensuring they can compete successfully on the global stage.

- Tasks to be performed by the contractor

The primary objective of this task is to provide a comprehensive suite of consulting services tailored to selected SMEs within Ukraine’s toy industry, aimed at preparing and organizing their successful participation at the Spielwarenmesse 2025 trade fair. The preparatory phase entails open recruitment and subsequent selection of participating companies, capacity-building for the chosen SMEs, including training facilitation, matchmaking preparation, creation of promotional materials and coordination the design of the exhibition booth to highlight each company's strengths.

The execution phase encompasses continuous onsite support to participating SMEs, assisting with product demonstrations, matchmaking efforts, while also promoting Ukrainian toy brands through various communication channels and offering ongoing guidance to optimize their exhibition performance and facilitate contract opportunities.

The target participants for this project are members of sectoral association – SMEs with export potential and value-added products, selected based on competitive criteria.

Eligibility criteria for SMEs to receive the services:

- The company is a small or medium company registered in Ukraine (government-controlled area) and under Ukrainian law;

- 100% of the company’s beneficiaries are Ukrainian citizens;

- The company has 5-249 registered employees (SMEs);

- The company does not operate or has its subsidiaries in the Russian Federation and/or Belarus and other countries in sanction list;

- The company, it’s owner’s and final beneficiaries are not registered in EU and Ukrainian sanction lists;

- The company is not in the process of termination or bankruptcy, is not bankrupt and has no tax debts.

The contractor is responsible for promotional campaign with the objective of distributing information about the project among SMEs and enticing their participation as well as highlighting the results of the trade fair.

  - Tasks

The contractor is responsible for providing the following services:

Working package 1.  Preliminary Phase: Recruitment and Capacity-Building for Spielwarenmesse 2025

2.1.1. Selection of up to 10 but not less than 7 Ukrainian SMEs, representatives of toy industry, demonstrating the highest export potential to partake in the trade fair.

2.1.2. Facilitating capacity-building for the selected SMEs is tailored to their specific needs in preparing for participation in the trade fair. This process encompasses various elements, including an online kick-off webinar that clarifies the project's agenda, timeline, participation conditions, and participant requirements. Additionally, targeted trainings (minimum 2 online events) are scheduled to prepare selected SMEs for effective participation in the trade fair, covering international market standards and presentation strategies.

2.1.3. Creation of promotional materials, and promotion of participants across various channels. Promotional materials should include an informational catalogue that will be compiled of the companies’ profiles and other relevant information aimed at the foreign companies that will be attracted to conducting negotiations with the UA companies during the B2B meetings in the framework of the trade fair. The contractor is responsible for coordination of the design of the exhibition booth to highlight each company's strengths.

Working package 2. Preliminary Phase: Matchmaking Preparation

2.1.4. Coordination and pre-arrangement matchmaking meetings for Ukrainian companies, ensuring their participation at the fair garners visibility and interest. A minimum of 10 targeted B2B meetings will be organized for each SME with outreach to minimum 70 relevant contacts in advance to maximize engagement and potential partnerships for Ukrainian participants. This task requires a tailored approach for each participant to invite the most relevant partners, aiming to facilitate concrete export contracts as a result.

Working package 3. Execution Phase: Participation in Spielwarenmesse 2025

2.1.5. Onsite support to participating SMEs and B2B Matchmaking. The contractor should provide real-time assistance to SMEs throughout the event, enhancing their engagement and ensuring smooth interactions with visitors, facilitate minimum 10 B2B meetings for each SME to establish connections with potential partners and clients in the European market. The signing of no less than 7 formal agreements by a minimum of 5 SMEs will serve as a key success indicator for this visit.

Selected companies must be informed of the necessity to arrange their logistics and accommodations to and in Germany.

The EU4Business Programme’s budget is allocated solely for compensating experts' services. All organizational costs, including booth renting, logistics, accommodation, per diems, etc., must be covered separately, utilizing the SME's own funds or other available resources.

Working Package 4. Post-Exhibition Phase: Follow-Up

2.1.6. Preparation follow-up letters for all contacts established by SMEs during the fair, ensuring consistent communication. The contractor should provide consultation to SMEs to assist them in developing and sending customized cooperation offers to potential clients, with the aim of strengthening connections and fostering partnership opportunities. The contractor must also ensure that the achievement of key indicators is addressed, specifically the signing of no less than 7 formal agreements by a minimum of 5 SMEs. These formal agreements may include contracts, MoUs, partnership agreements, etc., or, at minimum, expressions of interest or letters of intent for collaboration, documented in follow-up emails that reflect intentions discussed during B2B meetings. If the contractor is unable to provide evidence of these agreements, GIZ reserves the right to withhold the full payment of the contract amount.

2.1.7. Conduction of follow-up activities to collect feedback from participating SMEs, analyse outcomes, and assess the overall impact and effectiveness of their participation and the provided support.

A comprehensive promotional campaign should be implemented at all stages of the project to attract SMEs and raise awareness about export promotion, partnership development, and opportunities within the toy industry.

We also encourage conducting a follow-up survey among participating SMEs six months after the exhibition to analyze the impact of participation over time. This survey may assess key metrics such as new business leads generated, partnerships formed, sales growth or other improvements gained from the event. Such feedback will provide GIZ with a valuable data to enhance the support provided to SMEs for similar initiatives.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/partial works | Deadline/place/person responsible | Criteria for acceptance |
| --- | --- | --- |
| Working package 1. Preliminary Phase: Recruitment and Capacity-Building for Spielwarenmesse 2025 (Acc. to cl. 2.1.1.-2.1.3.) | 2 months after the start of the contract / Ukraine/ Project team | Shortlist (SME details without personal data) of the selected SMEs, agendas, participant lists, promotional materials, developed profiles of each selected SMEs (SME details without personal data) and photos with participant’s consent / print screens from the events according to the provided templates, promotional materials in line with GIZ’s PR requirements, design of the exhibition booth |
| Working package 2. Preliminary Phase: Matchmaking Preparation (Acc. to cl. 2.1.4.) | 2 months after the start of the contract / Ukraine / Project team | List of potential partners, agenda of pre-arrangement matchmaking meetings |
| Working package 3. Execution Phase: Participation in Spielwarenmesse 2025 (Acc. to cl. 2.1.5.) | 3 months after the start of the contract / Germany / Project team | List of conducted B2B meetings, photos from the trade fair with participant’s consent according to the provided templates |
| Working Package 4. Post-Exhibition Phase: Follow-Up (Acc. to cl. 2.1.6.-2.1.7.) | 4 months after the start of the contract / Ukraine / Project team | 7 copies of the formal agreements (сonfidential information may be blurred), the survey results from the fair participants |

The contract duration is from 09.12.2024 till 14.04.2025.

  - Deliverables and Reporting:

The contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| Narrative report on results of the performed services, including data on achieved outputs, results of working packages 1-2 implementation (Acc. to cl. 2.1.1.-2.1.4.) Shortlist (SME details without personal data) of the selected SMEs Agendas, participant lists, developed profiles of each selected SMEs (SME details without personal data) and photos with participant’s consent / print screens from the events Promotional materials in line with GIZ’s PR requirements Design of the exhibition booth List of potential partners, agenda of pre-arrangement matchmaking meetings | According to the provided template in English at least 10 pages in digital format According to the provided templates According to the provided templates In an arbitrary form in line with GIZ’s PR requirements In an arbitrary form in line with GIZ’s PR requirements In an arbitrary form | 27.01.2025 |
| Final report on overall results of the performed services, including data on achieved outputs, results of working packages 1-4 implementation (Acc. to cl. 2.1.1.- 2.1.7.) List of conducted B2B meetings Photos from the trade fair with participant’s consent 7 copies of the formal agreements (сonfidential information may be blurred) The survey results from the fair participants | According to the provided template in English up to 10 pages in digital format According to the provided templates According to the provided templates In an arbitrary form In an arbitrary form | 01.04.2025 |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to present and explain its approach to steering (1.3) the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

The tenderer is required to describe the key processes (1.4) for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the Contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

- Personnel concept (proposed staff)

The tenderer is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

The tenderer is required to gather a project team that should consist of up to 4 team members, including team leader and 3 experts.

## Team leader

Tasks of the team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting experts

- Regular reporting in accordance with deadlines

Qualifications of the team leader

- Education/training (2.1.1): Master’s degree in Economics, Management, Marketing, Management of Foreign Economic Activities, or another related topic

- Language (2.1.2): B2 level language proficiency in English, C2 level language proficiency in Ukrainian

- General professional experience (2.1.3): 5 years of professional experience in project management

- Specific professional experience (2.1.4): 5 years in export promotion

- Leadership/management experience (2.1.5): 5 years of management/leadership experience as project team leader or manager in a company

## Key expert

Tasks of key expert

- Preparation of the technical materials and detailed project concept

- Preparation of the agenda and organizing of the part of the capacity-building program provided in Ukraine

- Preparation of the criteria and participation in the selection process of the participants

- Support in preparation of matchmaking activities

- Regular reporting in accordance with deadlines

Qualifications of key expert

- Education/training (2.2.1): Master’s degree in Marketing, Economics, Management, Marketing, Management of Foreign Economic Activities, or another related topic

- Language (2.2.2): B2 level language proficiency in English, C2 level language proficiency in Ukrainian

- General professional experience (2.2.3): 5 years of relevant experience in export promotion

- Specific professional experience (2.2.4): 1 year of proven experience in toy industry

## PR expert

Tasks of the PR expert

- Creation of promotional materials, and promotion of participants across various channels

- Design of the exhibition booth

Qualifications of the PR expert with focus on international market

- Education/training (2.3.1): Master degree in Marketing, Public Relations, Communications, Journalism, Economics, or another related topic

- Language (2.3.2): B2 level language proficiency in English, C2 level language proficiency in Ukrainian

- General professional experience (2.3.3): 5 years of relevant experience in marketing

- Specific professional experience (2.3.4): 5 years of proven experience in manufacturing sector

## Export promotion expert

Tasks of the export promotion expert

- Support in organizing of the part of the capacity-building program provided in Ukraine

- Preparation of matchmaking activities

- Coordination and organization of the participation in the trade fair

Qualifications of the export promotion expert

- Education/training (2.4.1): Master’s degree in Marketing, Economics, Management, Management of Foreign Economic Activities, or another related topic

- Language (2.4.2): B2 level language proficiency in English, C2 level language proficiency in Ukrainian

- General professional experience (2.4.3): 5 years of relevant experience in export promotion

- Specific professional experience (2.4.4): 2 years of proven experience in conduction of export-oriented events

- Regional experience (2.4.6): 2 years of experience in promotion to EU market

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Socio-cultural skills

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

# Costing requirements

| Milestones/partial works | Estimated expert days for orientation | Deadline/place/person responsible |
| --- | --- | --- |
| Working packages 1 (Acc. to cl. 2.1.1.-2.1.3.) | Team leader: 30 Key expert: 28 PR expert: 28 Export promotion expert: 10 | 2 months after the start of the contract / Ukraine/ Project team |
| Working packages 2 (Acc. to cl. 2.1.4.) | Team leader: 21 Key expert: 21 Export promotion expert: 42 | 2 months after the start of the contract / Ukraine/ Project team |
| Working packages 3 (Acc. to cl. 2.1.5.) | Team leader: 5 Key expert: 7 PR expert: 18 Export promotion expert: 5 | 3 months after the start of the contract / Germany / Project team |
| Working packages 4 (Acc. to cl. 2.1.6.-2.1.7) | Team leader: 49 Export promotion expert: 49 | 4 months after the start of the contract / Ukraine / Project team |

In case of non-fulfilment or incomplete fulfilment of milestones or partial works, payment for expert days associated with these tasks will not be issued.

# Inputs of GIZ or other actors

N/A

- Place of assignment

Kyiv, Ukraine and Nurnberg, Germany

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the bid for the tender.

In consideration of work completed, the Contractor shall be paid according to anticipated payment schedule:

| Instalment # | Anticipated payment date | % of payment from total contract value | Deliverables and reporting | Project Number and % of costs split (if applicable) |
| --- | --- | --- | --- | --- |
| 1 Interim payment | 10.02.2025 | 58% | Acc. to cl. 2.1.1.-2.1.4. | 18.2197.4-010.00, 100% |
| 2 Final payment | 14.04.2025 | 42% | Acc. to cl. 2.1.5.-2.1.7. | 18.2197.4-010.00, 100% |

  - Financial proposal

The total cost of the bid shall be set in UAH, including all direct and related expenses, taxes and fees, but excl. VAT.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of reports accepted by GIZ;

- All the activities shall be done exclusively within the timeframe of the Contract;

- The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor;

- All the payments shall be done on the ground of the scanned invoices and acts of acceptance submitted in digital form within 15 working days after their submission by the Contractor and acceptance by GIZ.

  - Requirements to the submission of the financial reporting documents

- Invoices, acts of acceptance, etc.shall be scanned as one PDF document (up to 4 mb) and send as an attachment to the e-mail of the GIZ Project Representatives (the e-mail shall be provided additionally) together with other financial supporting documents as and if stipulated by the Contract; the technical documents (reporting/ deliverables) can be submitted either in the same or in a separate e-mail;

- The e-mail body/ text from the Contractor should also contain the following:

- List of the attached documents incl. title of the document, number, date of issue, amount UAH;

- Confirmation, that the services/ works/ goods specified in the attached documents were provided/ delivered/ supplied in full;

- Full name, position, contact details, full name of the organization.

- Confirmation, that the original documents (invoices, 2 copies of acts of acceptance, other financial supporting documents) will be kept by the Contractor and submitted later as soon as the security situation permits upon the request of GIZ. The deadline and the address for the delivery of documents will be agreed between GIZ and the Contractor via e-mail.

- Each invoice and act of acceptance shall contain the Project Number

By submitting the Invoice the Contractor should indicate (in the invoice or in the e-mail) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

  - VAT Exemption

The given procurement of services/ works upon the Contract shall be carried out at the funds of the Project of International Technical Assistance (ITA Project), PN: 2018.2197.4-003.00 , Project title “ReACT4UA (Utilization and Implementation of the Association Agreement between the EU and Ukraine in the field of trade) / EU4Business: SME Recovery, Competitiveness and Internationalisation”, registered by the by Directorate for Coordination of International Technical Assistance to the Cabinet of Ministers of Ukraine (Registration Card of the ITA Project (program) No. 4545-12 dated 03.07.2024) and complies with the category (training services) of Services specified in the Procurement Plan of the Project as consultancy services available at address of the Governmental Portal: https://www.kmu.gov.ua/diyalnist/mizhnarodna-dopomoga/pereliki-zareyestrovanih-proektiv-z-planami-zakupivel.

The above-mentioned ITA Project is implemented within the Framework Agreement between the Government of Ukraine and the Government of the Federal Republic of Germany on Counselling and Technical Cooperation dated 29/05/1996 and Framework Agreement between the Government of Ukraine and the Commission of European Communities ratified by the Law of Ukraine № 360-VI of 03.09.2008.

The given procurement of services/ works upon the Contract shall be determined free from VAT under provisions of cl.197.11 Art. 197 of the Tax Code of Ukraine. Operations for providing services under this Agreement are subject to VAT exemption.

- Other Provisions

The Contract will be signed by the Parties as a soft copy version by sending to each other by electronic means signed and scanned copies of the Contract and annexes. Such Contract shall have full legal force as the hard copies of it. The hard copies will be submitted as soon as the security situation in Ukraine stabilizes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine and Supplements to General Terms of contract governing Contracts with Appraisers/Firms of Consultants (local) published on the link  Закупівлі - giz.de (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor: Oksana Novodon, +380673111109, oksana.novodon@giz.de; Roman Lysenko, +380958618041, roman.lysenko@giz.de.

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

Additionally, the Contractor should:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU;

- not be in the process of termination;

- not be registarted on uncontrolled territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, a citizen of the Russian Federation, except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation.

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- personnel (team) concept;

- CVs of all experts with relevant work experience, qualifications (education, certificates).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English (language).

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Commercial bid must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provided according to the requirements of tender documentation.

    - Documents for tenderer’s eligibility confirmation

| The tenderer is obliged to conform to the following eligibility criteria: | The tenderer must provide the following document to confirm the compliance with eligibility criteria: |
| --- | --- |
| At least 1 reference project (trade fair completed to EU countries) Capacity for providing promo campaign via own online resources (website, social media, mobile application, bots etc.) | Portfolio with information: - on trade fair with photographic and\or video documentation and\or with links on social media or web pages - provided promo campaign examples with links on social media or web pages |

GIZ reserves the right to verify this information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Personal data protection

The Contractor confirms its acceptance of personal data processing in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and Law of Ukraine “About personal data protection” № 2297-VI dd. 01.06.2010.

The performance of the Contract may be associated with the processing of personal data by the Contractor, who would alone define the nature of such data and how such processing would be carried out. In such cases, the Contractor shall act as an independent DATA CONTROLLER and must alone comply with ALL applicable data protection obligations, including regional and local laws. The Contractor must process personal data only when a given goal cannot be reasonably attained without such data. The data protection principles such as lawfulness, data minimization, accuracy, purpose limitation, storage limitation, transparency, integrity and confidentiality, and accountability, as well as the numerous rights of the data subject must be paid due attention. The GDPR’s data transfer rules must be considered whenever personal data leaves the EU for a third country. The GIZ is NOT in any way responsible for such processing.