| Climate Risk and Vulnerability Assessment of Crop Farming and Animal Husbandry sectors of Ukraine | Project number/ cost centre: 21.9025.4-012.00 (100%) |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

BMUV	Federal Ministry for the Environment, Nuclear Safety and Consumer Protection

IKI	International Climate Initiative

PA	Paris Agreement

OECD	Organisation for Economic Co-operation and Development

EBA	European Business Association

IEF	Institute for Economics and Forecasting of the National Academy of Sciences of Ukraine

NDC	Nationally Determined Contribution

MRV	Monitoring, Reporting and Verification

CRVA	Climate Risk and Vulnerability Assessment

IPCC	Intergovernmental Panel on Climate Change

CID	Climatic Impact Drivers

GIS	Geographic Information System

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

- Context

The project “Promoting Green Deal Readiness in the Eastern Partnership Countries” (PROGRESS) is funded by the International Climate Initiative (IKI) of the German Federal Government and is implemented by the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH, as the lead agency, in partnership with the Organisation for Economic Co-operation and Development (OECD), the Regional Environmental Centre for the Caucasus (REC), the European Business Association (EBA) Moldova and the Institute for Economics and Forecasting of the National Academy of Sciences of Ukraine (IEF). The project supports the countries of the Eastern Partnership in their transition to climate-oriented, resilient, and green economic development.

The project aims to support the Eastern Partnership (EaP) countries to achieve long-term mitigation and sustainable development consistent with the EU Green Deal objectives and 1.5°C pathways of the Paris Agreement thus supporting key stakeholders in selected sectors and regions in transitioning towards climate-oriented, resilient and green economic development. PROGRESS supports the introduction of more sustainable production patterns in various agricultural value chains in the partner countries through the improvement of institutional framework conditions as well as measures in the related industrial and financial sectors.

EU4ClimateResilience is jointly co-financed by the European Union and the Federal Ministry for the Environment, Nuclear Safety and Consumer Protection (BMUV), and implemented by GIZ and OECD. The Action and the BMUV-funded project ‘Promoting Green Deal Readiness in the Eastern Partnership Countries’ (PROGRESS) are complementary since PROGRESS also aims to support EaP countries in the context of the EU Green Deal. This complementarity and implementation of both the Action and PROGRESS by GIZ and OECD therefore reflects the Team Europe approach.

The Overall Objective of the Action is to support the green transition, enhance decarbonisation, boost energy security and increase resilience to counter the effects of climate change in the EaP countries.

The Action supports the Eastern Partnership (EaP) countries in improving climate change and adaptation policies to achieve the mitigation and adaptation goals and targets under the Paris Agreement (PA) and related to bilateral agreements with the EU. This is achieved inter alia by technical support for the NDC 2025 update, improving the regulatory framework as well as further improving the institutional capacities to update the Nationally Determined Contribution (NDC), elaborate and implement Monitoring, Reporting and Verification (MRV) systems and mainstream climate change into sectoral and regional policies. The Action also acts on a local level by supporting the implementation of local climate adaptation projects, increasing the preparedness and resilience of cities and municipalities against short- and long-term climate risks. To mobilise additional sustainable investments, the introduction of innovative financial instruments such as green bonds will be supported.

EU4ClimateResilience and PROGRESS are complementary, enhancing the effectiveness of both initiatives. While EU4ClimateResilience focuses on broad climate resilience, adaptation and decarbonization, PROGRESS concentrates on preparing EaP countries specifically for the EU Green Deal in the agricultural sector. This coordination ensures that efforts are not duplicated but instead strategically aligned, reflecting the collaborative nature of the Team Europe approach.

The Objective of the Climate Risk and Vulnerability Assessment (CRVA) for the crop farming and animal husbandry sectors in Ukraine would be to identify, analyze, and assess the specific climate-related risks and vulnerabilities affecting these sectors. The assessment aims to understand the extent to which these agricultural sectors are exposed to climate variability and change, such as increased temperatures, altered precipitation patterns, and extreme weather events.

.

Expected results from the Climate Risk and Vulnerability Assessment (CRVA) for Ukraine’s crop farming and animal husbandry sectors will include Risk and Vulnerability Maps: detailed geographic maps and profiles indicating areas with high climate risk for specific crops and livestock, showing which regions and farming systems are most susceptible to climate impacts. Assessing Vulnerabilities: Evaluating the susceptibility of crops and livestock to these climate risks, factoring in aspects like regional differences, soil health, water availability, and crop/livestock types. CRVA will include calculation and visualization of climate change impacts, overall mean and maximum vulnerability of sectors. Moreover, CRVA will include recommendations and conclusions for the Ukrainian government to National Strategy on Adaptation to Climate change and other legislative documents.

The abovementioned enquiries have been addressed from the Ministries within the protocol meeting between PROGRESS GIZ Ukraine and Ministry of Agrarian Policy and Food of Ukraine on the 11th March 2024, protocol meeting between PROGRESS GIZ Ukraine and Ministry of Environmental Protection and Natural Resources of Ukraine on the 21st June 2024, joint protocol meeting between CCIG PROGRESS UA – GIZ, OECD, IEF and Ministry of Agrarian Policy and Food of Ukraine, Ministry of Environmental Protection and Natural Resources of Ukraine on the 24th June 2024, 1st Round Table of Local Partners Coordination Group of PROGRESS Ukraine on the 10th July 2024, and reflect the need of support to the Government of Ukraine in development and further implementation of the National Strategy of ecological security and adaptation to climate change 2030, especially in Agriculture and Food Sector.

- Tasks to be performed by the contractor

  - Tasks

The contractor is responsible for providing the following scope of work:

Preparation of Climate Risk and Vulnerability Assessment of Crop Farming and Animal Husbandry sectors of Ukraine

What: prepare analytical report with maps, diagrams, and description of vulnerability and risks of climate change for crop farming and animal husbandry in Ukraine.

Where: ensure that the report covers 8 study regions: North (4 oblasts), Center (4 oblasts), East (3 oblasts), West (8 oblasts), South (5 oblasts + Crimea), West mountains (Carpathians), South mountains (Crimea), Coastal (Black and Azov sea).

Timeframes: 2021-2040, 2041-2060 (2081-2100) vs 1991-2010.

Scenarios: RCP 4.5, RCP 8.5

Initial data: E-Obs (historical), 34 Regional Climate Models with resolution 0.1o Euro CORDEX (future)

Methodology: based on the IPCC approach to vulnerability and risk assessment of climate change with updates according to the AR6 (2021-2023). Namely, estimates will be based on projections of change in 32 Climatic impact drivers (CIDs) grouped into 5 categories: (1) heat and cold, (2) wet and dry, (3) snow, (4) wind, (5) coastal.

The Contractor should approve final methodological approach of the study with Ministry of Environmental Protection and Natural Resources of Ukraine and Ministry of Agrarian Policy and Food of Ukraine. The interim reports and the final report should be approved by both Ministries also.

The Contractor should consider Methodological recommendations to assess socio-economic risks and vulnerabilities sectors and natural components to climate change, which was adopted by the Ministry of Environmental Protection and Natural Resources of Ukraine (Annex 1).

Structure: The final analytical report should have the following structure with tentative titles:

Climate Change Risks and Vulnerability Assessment for Crop Farming

1.	Introduction (why there is a need of such a document)

2.	The current impact of climate change on crop farming

3.	Future impacts based on the scenarios for regions

4.	Climate change risks and vulnerability assessment

5.	Recommendations	for	National	Strategy	on	Adaptation to Climate change (Conclusion, non-technical summary)

Climate Change Risks and Vulnerability Assessment for Animal Husbandry

1.	Introduction (why there is a need of such a document)

2.	The current impact of climate change on animal husbandry

3.	Future impacts based on the scenarios for regions

4.	Climate change risks and vulnerability assessment

5.	Recommendations	for	National	Strategy	on	Adaptation to Climate change (Conclusion, non-technical summary)

The final analytical report should have the following information:

- Impact: The Contractor should determine, analyze, and compare the maximum vulnerability and risks from climate change among the study areas by 32 climatic impact drivers (with subcategories:  mean air temperature, extreme heat, mean precipitation, heavy precipitation, droughts, fire weather, snow cover, moderate snowfall days, surface wind speed, and coastal CIDs). In each subcategory, the maximum degree of impact from the relevant climatic impact driver should be determined.

- Sensitivity: The Contractor should prepare sensitivity assessments based on IPCC CID (Heat and cold, wet and dry, snowfall and snow cover, surface wind speed, Coastal CID's). IPCC CID Category should include Mean Air Temperature, Extreme Heat, Cold Spell, Frost, Mean Precipitation, Heavy Precipitation and Pluvial Flood, Droughts, Fire Weather, Snow Cover, Snowfall, Mean wind speed, Relative sea level rise, Extreme storm surge level (coastal flood).

- Vulnerability: The vulnerability of economic sectors and territories to changes in climate indicators will depend not only on sensitivity but also on the degree of influence of changes in climate impact drivers. In this case, the Contractor should draft colour coding of vulnerability from low to very high with scenarios RCP 4.5 in timeframe 2021-2040, 2041-2060, 2081-2100 and RCP 8.5 2021-2040, 2041-2060, 2081-2100 (with min, mean, max). For the whole territory of Ukraine, maps should represent a vulnerability to climate change.

For all 8 study regions, scenarios, and timeframes vulnerability should be summarized with figures with the sensitivity of the sector (which represents maximum vulnerability) by Mean Air Temperature, Extreme Heat, Cold Spell, Frost, Mean Precipitation, Heavy Precipitation and Pluvial Flood, Droughts, Fire Weather, Snow Cover, Snowfall, Mean wind speed, Severe wind storm, Extreme storm surge level (coastal flood).

- Risks: The Contractor should estimate for change in the main hazards (up to 10), namely mean temperature, extreme heat, heavy precipitation, wind gusts, etc. Additionally, mean and maximum risk assessments should be presented in tables for each of the study regions for two periods with central years 2030 and 2050 color-coded from very high to low risk.

- Recommendations and conclusions for the Ukrainian government to National Strategy on Adaptation to Climate change: The Contractor should provide recommendations for further actions and strategic steps based on the assessment outcomes, identifying regions and sectors most at risk due to climate change impacts with action plan.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/partial works | Anticipated deadline/place/person responsible | Criteria for acceptance |
| --- | --- | --- |
| First interim report | Deadline: to be submitted within 8 weeks after the contract signature | - Online presentation and confirmation about the methodology used to the Ministry of Environmental Protection and Natural Resources of Ukraine and Ministry of Agrarian Policy and Food of Ukraine. - Delivery of calculating and visualizing climate change impacts, including the mean and maximum vulnerability of the sectors to climate impact drivers (CIDs) across all regions for three future periods under two scenarios (word document, min. 20 pages in EN and UA). - Presentation and confirmation for the first interim report to the Ministry of Environmental Protection and Natural Resources of Ukraine and Ministry of Agrarian Policy and Food of Ukraine - Minutes with the feedback based on the comments during 2 events (word document, up to 4 pages) in EN and UA. |
| Second interim report | Deadline: to be submitted within 16 weeks after the contract signature | - Delivery of assessing and visualizing the risks of maximum probable impacts of five CID categories across all regions for three future periods with joint scenarios (min. 20 pages in EN and UA). - Presentation and confirmation of the second interim report to the Ministry of Environmental Protection and Natural Resources of Ukraine and Ministry of Agrarian Policy and Food of Ukraine (word document, min. 20 pages in EN and UA). - Minutes with the feedback based on the comments during event (word document, up to 4 pages) in EN and UA. |
| Final report` | Deadline: to be submitted within 28 weeks after the contract signature | - Compiling the findings into a comprehensive final report Climate Risk and Vulnerability Assessment of Crop Farming and Animal Husbandry sectors of Ukraine (word document, min. 60 pages in EN and UA languages analytical report, including data/graphs with maps, diagrams) and ppt in both languages (EN, UA) with key findings. - Presentation of the study to Ministries and interested stakeholders. - Preparation of recommendations and conclusions for the Ukrainian government to National Strategy on Adaptation to Climate change (In EN and UA languages, word document, min. 10 pages). |

The contract duration is from 16.12.2024 till 30.09.2025.

  - Deliverables and Reporting:

The Contractor shall submit the following reporting documents (signed and stamped):

|  | Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- | --- |
| 1 | First interim report: Calculate and visualize climate change impacts, overall mean and maximum vulnerability of sectors to all CIDs in all regions for three future periods and two scenarios. First interim report. | In EN and UA languages, word document (min. 20 pages), including data/graphs with maps, diagrams etc. | 8 weeks after the contract signature |
| 2 | Second interim report : Calculate and visualize risks of maximum probable impacts of 5 categories of CIDs in all regions for three future periods and joint scenarios. Second interim report. | In EN and UA languages, word document (min. 20 pages), including data/graphs with maps, diagrams etc. | 16 weeks after the contract signature |
| 3 | Final report. Compiling the findings into a comprehensive final report. | In EN and UA languages, word document (min. 60 pages), including data/graphs with maps, diagrams etc. | 28 weeks after the contract signature |
| 4 | 4 Online events - presentation of the methodology, interim reports and its results to the Ministry of Environmental Protection and Natural Resources of Ukraine and Ministry of Agrarian Policy and Food of Ukraine and interested stakeholders | 4 Brief documents - minutes with the feedback based on the comments during event (word document, up to 4 pages) in EN and UA languages. | 28 weeks after the contract signature |
| 5 | Recommendations and conclusions for the Ukrainian government to National Strategy on Adaptation to Climate change | Brief document - the contractor shall provide recommendations for further actions and strategic steps based on the assessment outcomes, identifying regions and sectors most at risk due to climate change impacts with action plan. In EN and UA languages, word document (min. 10 pages). | 28 weeks after the contract signature |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them. – not applicable

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2). – 1.3.1 and 1.3.2 not applicable

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided.

In particular, the tenderer is required to describe the necessary work steps and if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2). (1.4.2 is not applicable).

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation. – 1.5.1 and 1.5.2 not applicable

## Project management of the contractor (1.6) – not applicable

## Further requirements (1.7) – not applicable

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

Tasks of Team Leader

- Lead and coordinate the overall analysis project of vulnerability and risks of climate change for crop farming and animal husbandry in Ukraine

- Supervise the identification and application of two climate scenarios, ensuring they are properly modeled for the three future periods (2021-2040, 2041-2060, 2081-2100). Review scenario assumptions and ensure they are in line with relevant climate data sources

- Guide the assessment process across the 5 geographical regions and 3 special territories, ensuring consistency in the analysis

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project.

- Regular reporting in accordance with deadlines

Team Leader

- Education/training (2.1.1): university degree (Master) in Environment, Meteorological, Physics or similar studies

- Language (2.1.2): C1-level language proficiency in English

- General professional experience (2.1.3): 15 years of professional experience in the climate sector

- Specific professional experience (2.1.4): 10 years in climate change adaptation sector

- Leadership/management experience (2.1.5): 3 years of management/leadership experience as project team leader or manager in a company

- Regional experience (2.1.6): 10 years of experience in projects in Ukraine

- Development cooperation (DC) experience (2.1.7) – not applicable

- Other (2.1.8) – not applicable

Tasks of key expert 1

- Gather and manage relevant climate data

- Provide expertise in daily air temperature monitoring (average, maximum, minimum), climate-vulnerable areas

- Provide extensive research on climate change risks and vulnerability assessment in Crop Farming and Animal Husbandry sectors of Ukraine

Key Expert 1

- Education/training (2.2.1): university degree (Master) in Environment, Hydrometeorology, Meteorology or similar studies

- Language (2.2.2): B1-level language proficiency in English

- General professional experience (2.2.3): 12 years of professional experience in the environment or climate sector, or/and in preparation analytical studies in the climate sector as researcher

- Specific professional experience (2.2.4): 10 years of experience in conducting studies or/and analyses in climate-sensitive areas or/and forecasting climate-vulnerable areas

- Leadership/management experience (2.2.5): – not applicable

- Regional experience (2.2.6): – not applicable

- Development cooperation (DC) experience (2.2.7) – not applicable

- Other (2.2.8) – not applicable

Tasks of key expert 2

- Research on the assessment of climate change in Ukraine based on scenarios of possible global climate change

- Provide extensive research on climate change risks and vulnerability assessment in Crop Farming and Animal Husbandry sectors of Ukraine

- Informing the study design with relevant knowledge on climate change

Key Expert 2

- Education/training (2.3.1): university degree (Master) in Geographical Sciences, Meteorology, Climatology, Agrometeorology or other relevant

- Language (2.3.2): B1-level language proficiency in English

- General professional experience (2.3.3): 12 years of professional experience in the environment or climate sector, or/and in preparation analytical studies in the climate sector as researcher

- Specific professional experience (2.3.4):  10 years of experience in conducting studies or/and analyses in meteorology and climatology

- Leadership/management experience (2.3.5): – not applicable

- Regional experience (2.3.6): – not applicable

- Development cooperation (DC) experience (2.3.7) – not applicable

- Other (2.3.8) – not applicable

Tasks of key expert 3

- Gather and manage relevant climate data

- Use GIS tools to conduct spatial analysis for the 5 geographical regions and 3 special territories. Model the potential impacts of the 32 CIDs across the three future periods for both scenarios

- Provide GIS-based contributions to reports.

Key Expert 3

- Education/training (2.4.1): university degree (Master) in Geographic Information Sciences, Environmental Sciences or other relevant

- Language (2.4.2): B1-level language proficiency in English

- General professional experience (2.4.3): 6 years of professional experience in the environment or climate sector, or/and in preparation analytical studies in the climate sector as researcher

- Specific professional experience (2.4.4):  3 years of experience in Geographical Information Systems

- Leadership/management experience (2.4.5): – not applicable

- Regional experience (2.4.6): – not applicable

- Development cooperation (DC) experience (2.4.7) – not applicable

- Other (2.4.8) – not applicable

Tasks of key expert 4

- Design and implement statistically rigorous studies relevant to crop farming and animal husbandry, ensuring data collection methodologies are aligned with agricultural best practices.

- Process and analyze agricultural data to derive actionable insights on crop productivity, livestock health, and sustainable farming practices.

Key Expert 4

- Education/training (2.5.1): university degree (Master) in Agricultural Sciences, Animal Husbandry, Crop Science, Environmental Science, or other relevant fields related to agriculture and sustainability

- Language (2.5.2): B1-level language proficiency in English

- General professional experience (2.5.3): 5 years of professional experience in the agricultural sector with a focus on crop farming, livestock management, or related fields such as sustainable agriculture or rural development

- Specific professional experience (2.5.4):  3 years of experience in designing and conducting studies related to agricultural systems, with an emphasis on mesostructural aspects of farming, climate impacts on crop and livestock production, or agricultural adaptation strategies

- Leadership/management experience (2.5.5): – not applicable

- Regional experience (2.5.6): – not applicable

- Development cooperation (DC) experience (2.5.7) – not applicable

- Other (2.5.8) – not applicable

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Socio-cultural skills

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

# Costing requirements

## Specification of inputs

The following basic calculations for the contract for works are a reference value based on the acceptance criteria for each partial work/milestone specified in Chapter 2 (Tasks to be performed by the contractor).

Since the contract to be concluded is a contract for works, we would ask you to offer your services at a lump sum price.

| Milestones/partial works | Estimated expert days for orientation | Anticipated deadline/place/person responsible |
| --- | --- | --- |
| First interim report Online presentation (methodology and first interim report) Minutes with the feedback | TL: 20 days Expert 1: 12 days Expert 2: 12 days Expert 3: 10 days Expert 4: 9 days | 8 weeks after the contract signature |
| Second interim report Online presentation (second interim report) Minutes with the feedback | TL: 20 days Expert 1: 12 days Expert 2: 12 days Expert 3: 10 days Expert 4: 9 days | 16 weeks after the contract signature |
| Final report Presentation of the result Recommendations and conclusions for the Ukrainian government to National Strategy on Adaptation to Climate change | TL: 25 days Expert 1: 16 days Expert 2: 16 days Expert 3: 15 days Expert 4: 12 days | 28 weeks after the contract signature Deadline: 07 July 2024 |

# Inputs of GIZ or other actors Not Applicable

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the commercial bid.

Anticipated payment schedule:

In consideration of services completed, the Contractor shall be paid in the following instalments:

| Instalment # | Anticipated payment date | Payment of up to % from total contract value | Deliverables and reporting | Project Number and % of costs split (if applicable) |
| --- | --- | --- | --- | --- |
| 1 Interim payment | 27.02.2025 | 30% | Acc. to cl. 2.2 | 21.9025.4-012.00 (100%) |
| 2 Interim payment | 27.04.2025 | 30% | Acc. to cl. 2.2 | 21.9025.4-012.00 (100%) |
| 3 Final payment | 17.07.2025 | 40% | Acc. to cl. 2.2 | 21.9025.4-012.00 (100%) |

  - Financial proposal

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, but incl. VAT.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments.

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of reports accepted by GIZ;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done on the ground of the scanned invoices and acts of acceptance submitted in digital form within 7 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Invoices, acts of acceptance etc. shall be scanned as one PDF document (up to 4 mb) and send as an attachment to the e-mail of the GIZ Project Representatives (the e-mail shall be provided additionally) together with other financial supporting documents as and if stipulated by the Contract; the technical documents (reporting/ deliverables) can be submitted either in the same or in a separate e-mail;

- The e-mail body/ text from the Contractor should also contain the following:

- List of the attached documents incl. title of the document, number, date of issue, amount UAH;

- Confirmation, that the services/ works/ goods specified in the attached documents were provided/ delivered/ supplied in full;

- Full name, position, contact details, full name of the organization.

- Confirmation, that the original documents (invoices, 2 copies of acts of acceptance, other financial supporting documents) will be kept by the Contractor and submitted later as soon as the security situation permits upon the request of GIZ. The deadline and the address for the delivery of documents will be agreed between GIZ and the Contractor via e-mail.

- Each invoice and act of acceptance shall contain the Project Number

By submitting the Invoice the Contractor should indicate (in the invoice or in the e-mail) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

- In case the Contractor is a VAT Payer at the moment of the Invoice issuing, the VAT exemption clause shall be applicable and the Contractor should also submit the Tax Invoice to GIZ as soon as that is available.

Timesheet standard template can be found here https://www.giz.de/en/worldwide/63065.html

- Other Provisions

  - General

The Contract will be signed by the Parties as a soft copy version by sending to each other by electronic means signed and scanned copies of the Contract and annexes. Such Contract shall have full legal force as the hard copies of it. The hard copies will be submitted as soon as the security situation in Ukraine stabilizes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine and Supplements to General Terms of contract governing Contracts with Appraisers/Firms of Consultants (local) published on the link  Закупівлі - giz.de (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor _________________________________.

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU;

- not be in the process of termination;

- not be registarted on temporary occupaied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, a citizen of the Russian Federation, except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation.

GIZ reserves the right to verify this information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

Not Applicable

# Outsourced processing of personal data

Not Applicable

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- CVs of the experts with relevant work experience, qualifications (education).

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted . The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English (language).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Commercial bid must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

    - Documents for tenderer’s eligibility confirmation

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU;

- not be in the process of termination;

- not be registarted on uncontrolled territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, a citizen of the Russian Federation, except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation.

GIZ reserves the right to verify this information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Option

Not Applicable

- Annexes

Annex A – Methodological recommendations to assess socio-economic risks and vulnerabilities sectors and natural components to climate change adopted by the Ministry of Environmental Protection and Natural Resources of Ukraine