| ToR for providing organizational and logistical support for the Off-line / online workshops for dissemination of the nationally standardized municipal energy management methodology and FEER best practices | Project number/ cost centre: 2019.2290.5-003.00 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	 Commissioning party

AN	 Contractor

AVB	 General Terms and Conditions of Contract for supplying services and work

FK	 Expert

FKT	 Expert days

KZFK	 Short-term expert

ToRs	 Terms of reference

EE	 Energy efficiency

MinInfra	 The Ministry for Communities, Territories and Infrastructure Development of Ukraine

SAEE	 State Agency on Energy Efficiency and Energy Saving of Ukraine

GIZ	 Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH

MEM	 Municipal Energy Management

LEP	 Local Energy Planning

BMZ	 German Federal Ministry for Economic Cooperation and Development

NEEAP	 National Energy Efficiency Action Plan

EEIM II	 Energy Efficiency in Municipalities II

SECO	 State Secretariat for Economic Affairs of Switzerland

FEER	 Promotion of Energy Efficiency and Implementation of the EU Energy Efficiency Directive in Ukraine

ToRs	Terms of reference

- Context

The project “Promotion of Energy Efficiency and Implementation of the EU Energy Efficiency Directive in Ukraine” (further on – Project) targets the improvement of the capacities of national institutions for the effective implementation of the EU Energy Efficiency Directive and promotion of energy efficiency in Ukraine. The project supports the Ministry for Communities, Territories and Infrastructure Development of Ukraine (MinInfra) and the State Agency on Energy Efficiency and Energy Saving of Ukraine (SAEE) in three fields of action: policy advice and implementation of partial reforms (output 1), spread of municipal energy management in Ukraine (output 2), design of qualification possibilities with reference to energy efficiency for professionals and employees (output 3) and support companies in increasing energy efficiency (output 4).

FEER Project output 2 strengthens the energy management of municipalities in public buildings, supports them in implementation of specific EE measures, and thus contributing directly to Project objective indicator 2 (lowering of primary energy consumption in partner communities).

FEER Project output 2 selected 20 pilot communities to assist and support them in writing their Local Energy Plans, in particular:

Zhytomyr, Zviahel, Korosten, Trostynets, Fastiv, Ivano-Frankivsk, Chernivtsi, Khotyn, Myrhorod, Konotop, Sambir, Drogobych, Novovolynsk, Lubny, Chuguev, Chornomorsk, Pokrovske, Zhmerynka, Sumy, Slavutych.

In pursuance of the Law of Ukraine on Energy Efficiency, in particular Article 6 Energy Planning at the Local Level, it is planned to hold a number of events with pilot communities that are already preparing Local Energy Plans in their communities.

With the support of national and international experts who help and advise selected communities that have decided to implement Local Energy Plans in their communities, it is planned to hold an event from 4 to 6 February 2025 for community representatives. The event is aimed at raising awareness and exchanging experiences among community representatives who are in the process of writing Local Energy Plans.

- Tasks to be performed by the contractor

The objective of this assignment is to provide organizational and logistical services for conducting of a three-day event (workshops) for representatives of 20 pilot municipalities (GIZ partners):

| Description of event | Off-line/online event for dissemination of the nationally standardized municipal energy management methodology and FEER best practices for high-level management and implementation representatives of municipalities |
| --- | --- |
| Duration of the event | The three-day event is to be held during the period January - February 2025 The planned event dates are February 4-6, with the possibility of a postponement due to the security situation in Ukraine |
| Date and time | 4 February - conducting of the workshop (10:00-18:00) 5 February - conducting of the workshop (10:00-18:00) 6 February - conducting of the workshop (10:00-18:00) The exact dates of the workshops will be communicated by the Project no later than 10 calendar days beforehand. |
| Location (city, country) | Kyiv, Ukraine |
| Number of Participants (up to) | up to 50 participants will attend the workshops to be held during three days |

  - Tasks

The contractor is responsible for providing the following services:

- Accommodation arrangements in Kyiv with the possibility for early check-in (7:00 AM) for up to 50 persons. It is necessary to accommodate guests, each in a single room, including breakfast and tourist tax. The hotel must provide shelter in case of a missile threat. Location: City center or no further than 2km from the city center with convenient access to public transportation.

- Organization of a conference hall in a hotel with a shelter and the possibility of holding lunch and coffee breaks during the 3 days of the event.

- Managing reimbursement of travel expenses for up to 50 participants traveling from their place of residence (Zhytomyr, Zviahel, Korosten, Trostynets, Fastiv, Ivano-Frankivsk, Chernivtsi, Khotyn, Myrhorod, Konotop, Sambir, Drogobych, Novovolynsk, Lubny, Chuguev, Chornomorsk, Pokrovske, Zhmerynka, Sumy, Slavutych) to the city of destination - Kyiv and vice versa. Reimbursement of round-trip tickets is required for participants traveling by train and/or bus.

- Organizing the distribution of participants into 4 groups of 10-12 people in 4 different rooms for individual work with a mentors

- Access to a large screen in the large hall for broadcasting presentations and speakers + technical support during the event (connecting a computer, setting up microphones, displaying the presentation on a large screen and general technical support throughout all days of the event).

- Development and printing of the agenda for the entire event.

- Organization of online broadcast and technical support.

- Provision of microphones, roll-up or clasic banners, badges with ribbon, magnetic markers flipcharts, markers for badges, papers for flipchart, eco-bags, pens, notebooks

- The contractor is responsible for selecting, preparing and steering the experts assigned to provide administrative and technical support for the event, namely:

- Event Manager

- Event Coordinator

The Contractor shall be available for clarification, questions within contract duration without limitations.

The event should be organized according to sustainability criteria, e.g. reduction of plastic and food waste.

The GIZ will make payment for actually provided services by the Contractor.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| Arranging accommodation for up to 50 participants including breakfast (provide for early check-in for all participants) | January - February 2025 / Kyiv / Responsible Expert from Contractor |
| Managing reimbursement of travel expenses for up to 50 participants | January - February 2025 / Kyiv / Responsible Expert from Contractor |
| Providing catering services (coffee breaks and lunches) for up to 50 participants during 3 days of the event. | January - February 2025 / Kyiv / Responsible Expert from Contractor |
| Organization of one dinner for up to 50 participants | January - February 2025 / Kyiv / Responsible Expert from Contractor |
| Comprehensive organization of online broadcast of the event with translation (on the Microsoft Teams or any other software allowed by IT department of GIZ). | January - February 2025 / Kyiv / Responsible Expert from Contractor |

The contract duration is from 20.01.2025 till 31.03.2025.

  - Deliverables and Reporting:

The Contractor shall submit the following reporting documents to report for event services:

- lists of participants for all workshops

- invoices for payment and acts of acceptance, signed and stamped (if applicable) by Contractor;

- all other documents specified for each item in paragraph 5 “	Costing (quantitative) requirements” of these ToR.

The Contractor will be responsible for the following:

| # | Reporting/ Deliverable | Requirements to the format | Anticipated period, by |
| --- | --- | --- | --- |
| 1 | Lists of participants of the workshops, signed by participants for each day of event | pdf | January - February 2025 |
| 2 | Documents according to Para. 5 | pdf | January - February 2025 |
| 3 | Photos of the provided equipment next to the event agenda (flipcharts, flipchart markers, flipchart paper, badge markers, badges, eco-bags, pens, notebooks, banners) | JPG, JPEG | January - February 2025 |
| 4 | Comprehensive final report | PDF doc / Word doc (at least 2 pages) – Ukrainian and English language | 3 working days after conducting event |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them, namely presentation and interaction between the relevant actors in the contractor`s area of responsibility (1.2.1) and Strategy for establishing cooperation and then cooperation with the relevant actors (1.2.2)

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

## Team leader - event manager

Tasks of the event manager

- Coordinating all aspects of the event.

- Participating in online meetings with the project team to discuss all details of the event.

- Managing event preparation activities, including assigning tasks, providing guidance, and ensuring effective teamwork to meet deadlines and achieve the goals of the events.

- Managing the events budget, including cost estimation and financial tracking.

- Communicating with key vendors, such as venue providers, catering services, negotiating favourable terms and ensuring the highest quality of services.

- Managing participant registration, responding to inquiries and providing support to participants before and during the event. Resolving any issues related to registration and badges.

- Ensuring attendance and overseeing logistics during the event.

- Conducting post-event follow-up tasks.

- Compiling and submitting comprehensive event report.

Qualifications of the event manager

- Education/training (2.1.1): Diploma (Bachelor or Master) in administration, management or related sphere

- Language (2.1.2): C1-level language proficiency in Ukrainian

- General professional experience (2.1.3): 2 years of professional experience in the event coordination or related sector

## Key expert 1 - event coordinator

Tasks of the event coordinator

- Actively participation in the event preparation meetings.

- Preparation and coordination of participant registration and transportation cost reimbursements.

- Collecting all original supporting documents for transportation services, meal services etc. making sure they meet GIZ requirements.

- Providing organizational and technical assistance during the event. Be present during the event to ensure that everything runs smoothly, including coordinating with venue staff, overseeing setup, managing changes in the schedule, and addressing any on-site issues.

- Readiness to solve unexpected issues as they arise, such as last-minute changes, and provide quick solutions.

Qualifications of the event coordinator

- Education/training (2.2.1): Diploma (Bachelor or Master) in administration, management or related sphere

- Language (2.2.2): C1-level language proficiency in Ukrainian

- General professional experience (2.2.3): 2 years of professional experience in the event coordination or related sector

# Costing (quantitative) requirements

## Assignment of personnel and travel expenses

All business travel activities must be agreed in advance with the staff member responsible for the project.

## Sustainability aspects for travel and travel regulations

If applicable on ground of these Terms of Reference, the following travel regulations are to be observed. See Annex 1 to these Terms of References.

Specification of inputs

|  | Expert services (experts that are directly involved in preparation of the event) | Unit of measurement | Number of experts | Total number of days | Comments |
| --- | --- | --- | --- | --- | --- |
| 1. | Team leader – Event manager | working day | 1 | 4 | Contractor shall provide timesheet with the actual days utilized, including a brief description of the work performed and any deliverables or outcomes from their contribution. |
| 2. | Key expert 1 – Event coordinator | working day | 1 | 4 | Contractor shall provide timesheet with the actual days utilized, including a brief description of the work performed and any deliverables or outcomes from their contribution. |
|  | Transportation | Unit of measurement | Quantity (up to) | Total number of persons | Comments |
| 3. | Reimbursement of travel expenses (train / bus) for up to 50 participants of event to be held in Kyiv Tickets 2-nd class train and/or bus should be purchased for participants traveling from their place of stay (Zhytomyr, Zviahel, Korosten, Trostynets, Fastiv, Ivano-Frankivsk, Chernivtsi, Khotyn, Myrhorod, Konotop, Sambir, Drogobych, Novovolynsk, Lubny, Chuguev, Chornomorsk, Pokrovske, Zhmerynka, Sumy, Slavutych) to the city of destination and back | round trip ticket | 50 | – | Contractor must provide proof of evidence as a package of following documents: - Copies of tickets purchased by participants. - List of passengers signed by each person. The ticket purchase fee is not to be reimbursed. |
|  | Accommodation | Unit of measurement | Quantity (up to) | Total number of persons | Comments |
| 4. | Reservation and payment for accommodation for up to 50 participants in Kyiv for two nights Provide early check-in (7am) for all participants on the first day Standard rooms with single stay & breakfast Hotels not less than 3*, located Kyiv, in the city central part, which should have a bomb shelter in case of missile danger + independent power generator | night | 100 | – | Contractor must provide proof of evidence as a package of following documents: - Copy of invoice from the hotel or other actual service provider with period of stay, names of guests, type and number of rooms and nights, price per night, total amount, meals Service fee of booking platforms will not be reimbursed. |
|  | Catering | Unit of measurement | Quantity (up to) | Total number of persons | Comments |
| 5. | Organization of coffee breaks for 3-days event for up to 50 participants 2 times per each day plus one additional morning coffee break at the first day of the event. In total 7 coffee breaks Should include coffee with milk, black tea, green tea, orange juice, sandwiches, fruits, cold cuts, bottled sparkling and still water | portion | 350 | – | Contractor must provide proof of evidence as a package of following documents: - Copy of invoice from actual service provider with indication of meals, quantity of portions, price and total amount. |
| 6. | Organization of lunches for 3-days event for up to 50 participants Should include main dish, salad, canapes, desserts, and non-alcoholic beverages. Allergies and other dietary preferences must be considered | portion | 150 | – | Contractor must provide proof of evidence as a package of following documents: - Copy of invoice from actual service provider with indication of meals, quantity of portions, price and total amount. |
| 7. | Organization of one dinner Should include main dish, salad, canapes, desserts, and non-alcoholic beverages | portion | 50 | – | Contractor must provide proof of evidence as a package of following documents: - Copy of invoice from actual service provider with indication of meals, quantity of portions, price and total amount. |
|  | Equipment and materials for conducting event | Unit of measurement | Quantity (up to) | Total number of equipment / materials | Comments |
| 8. | Badges with ribbon for up to 50 participants The badge on the ribbon is blank to write the participant's name with GIZ logo (design details are discussed with the project) | pc. | 50 | – | Contractor must provide proof of performance as a package of following documents: - Photo of actually provided materials - List of actually provided materials signed by GIZ representative (if GIZ staff is present), otherwise list of actually provided materials signed by Contractor |
| 9. | Rent of 4 magnetic marker flipcharts for 3-days workshops (1 flipchart for each of 4 groups of participants) The height of the flipchart board can be adjusted from 125 to 196 cm from the floor. The paper block is attached under a metal bar at the top of the flipchart. There is a shelf for markers at the bottom of the flipchart. The stand extends 40 cm. It is recommended to write on the surface of the paper block with flipchart markers. Size: 70×100 cm. | day | 3 | – | Contractor must provide proof of performance as a package of following documents: - Photo of actually provided materials - List of actually provided materials signed by GIZ representative (if GIZ staff is present), otherwise list of actually provided materials signed by Contractor |
| 10. | Markers for badges Black permanent marker. Suitable for all types of surfaces. The line width is 1 mm. | pc. | 5 | – |  |
| 11. | Markers for flipchart (1 set for each flipchart) Set of markers (=4 colours) for whiteboards and flipcharts | set | 4 | – |  |
| 12. | Paper for flipchart (1 set for each flipchart) Set of flipchart paper (=20 sheets) without lines 64x90 cm | set | 4 | – |  |
| 13. | Roll-up banner or classic banner 1000x2000 mm The design and text to be applied must be agreed with the Project Print quality 1080 dpi | pc. | 4 | – | Contractor must provide confirmation of evidence as a package of following documents: - Copy of invoice from actual supplier with list of materials, quantity, price and total amount - Photo of actually provided materials |
| 14. | Development and printing of the agenda for the entire event Size: 105x148 mm. Matte coated paper 130-350 g/m2. Full-color printing on 2 sides. The design and text to be applied must be agreed with the Project | pc. | 100 | – | Contractor must provide proof of performance as a package of following documents: - Photo of actually provided materials - List of actually provided materials signed by GIZ representative (if GIZ staff is present), otherwise list of actually provided materials signed by Contractor |
| 15. | Eco-bags with GIZ logo 100% cotton. Density – 220 g/m2. Bag size 38x42/35x41 cm. Handle length 60/70 cm. Screen printing. The design and text to be applied must be agreed with the Project | pc. | 50 | – | Contractor must provide confirmation of evidence as a package of following documents: - Copy of invoice from actual supplier with list of materials, quantity, price and total amount - Photo of actually provided materials |
| 16. | Pens with GIZ logo Body - thick kraft paper, color - blue with click-clack mechanism The design must be agreed with the Project | pc. | 50 | – | Contractor must provide proof of performance as a package of following documents: - Photo of actually provided materials - List of actually provided materials signed by GIZ representative (if GIZ staff is present), otherwise list of actually provided materials signed by Contractor |
| 17. | Notebooks with GIZ logo A6 notebook, 50 sheets. Binding on a metal Wario spiral. Size 105x148 mm. blank sheets The design must be agreed with the Project | pc. | 50 | – | Contractor must provide confirmation of evidence as a package of following documents: - Copy of invoice from actual supplier with list of materials, quantity, price and total amount - Photo of actually provided materials |
| Other costs |  |  |  |  |  |
| 18. | Online broadcast and technical support Services for online broadcasting of the event (on the Microsoft Teams or any other software allowed by IT department of GIZ). including: Equipment for video broadcasting Video remote control - 1 Video camera PTZ (FullHD) - 2 Laptop - 1 Light equipment - 2 Sound equipment Sound set - 1 Digital mixer console (16 inputs) - 1 Radio microphone - 3 Equipment Microsoft Teams Organization of translation with a licensed Microsoft Teams software Technical support Video engineer Installation / dismantling of equipment Equipment delivery | day | 3 | – | Contractor must provide confirmation of evidence as a package of following documents: - Copy of invoice from a third party indicating the duration of service provision, price, and the total amount. |
| 19. | Rental of hall and meeting rooms Rental of 1 large hall for 50-70 people with a large screen or projector on which presentations and speakers can be broadcast, with the possibility of holding coffee breaks and lunches, Rental of 3 smaler rooms for 10-12 people with tables for possibility of divide participants in 4 groups for individual works with mentors (mandatory with shelter in the same building) | days | 3 | – | Contractor must provide confirmation of evidence as a package of following documents: - Copy of invoice from the venue or other actual service provider with indication of location and a period of rent. |
| 20. | Flexible remuneration The Contractor shall act only in terms of prices per unit provided. Exceeding such costs is not allowed. Flexible renumeration may be used only to order additional quantities without changing the unit price. |  |  |  | In case flexible renumeration is used, the explanation of the reasons which led to this, and evidence relevant to the particular item(s) must be provided. A budget of 68924,45 UAH is foreseen for flexible remuneration. Please incorporate this budget into the commercial offer. Use of the flexible remuneration item(s) requires prior written approval from GIZ |
| 21. | Service fee incl. applicable taxes (X%) Service fee incl. applicable taxes is calculated based on the estimated contract price (sum of all services provided + sum of used flexible remuneration, excluding items 1, 2, 8-12, 14 and 16 * X%) Contractor shall calculate its tax(es) according to the taxation scheme of Ukraine incl. VAT, if applicable and indicate the initial price including all applicable taxes (price gross) |  |  |  |  |

The exact dates of the event, number of people participating in the event, number of required services, preliminary agenda, necessary equipment, and other relevant information will be communicated by the Project no later than 10 calendar days prior to the event.

Contractor should be aware that overall sum of reimbursable meal (namely – lunch and dinner) for each event should not exceed 28 EUR (according to the exchange rate in December 2024 – 43,84418 UAH per 1 EUR that equals 1227.63 UAH per person), highest rate for accommodation services (standard room) should not exceed: Kyiv - 130 EUR (according to the exchange rate in December 2024 – 43,84418 UAH per 1 EUR that equals 5 699.74 UAH per person)

- Inputs of GIZ or other actors

GIZ and/or other actors are expected to make the following available:

- During implementation of the assignment, the Project will organize joint online meetings with the Contractor to discuss and finalize the agenda and other organizational details such as transportation of the participants, meals, etc.

- The GIZ Project will provide comments and suggestions on the implementation of the assignment

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the commercial bid.

Anticipated payment schedule:

In consideration of services provided, the Contractor shall be paid as follows:

| Instalment # | Anticipated payment date | Payment of up to % from total contract value | Deliverables and reporting | Project Number and % of costs split (if applicable) |
| --- | --- | --- | --- | --- |
| 1.Final payment | 28.02.2025 | 100% | Acc. to cl. 2.2 | 19.2290.5-003.00 |

  - Financial proposal

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, but excl. VAT

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

The Contractor shall be paid 100% post payment upon performance in the agreed instalments;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the payments shall be done exclusively for the actually performed services (“up to”), on the ground of reports accepted by GIZ;

- All the activities shall be done exclusively within the timeframe of the Contract;

- The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor;

- All the payments shall be done on the ground of the scanned invoices and acts of acceptance and reporting documents according to Section 5 of the present ToR submitted in digital form within 10 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Invoices, acts of acceptance and reporting documents indicated in Specification of inputs Section 5 of the present ToR,  etc. shall be scanned as one PDF document (up to 4 mb) and send as an attachment to the e-mail of the GIZ Project Representatives (the e-mail shall be provided additionally) together with other financial supporting documents as and if stipulated by the Contract; the technical documents (reporting/ deliverables) can be submitted either in the same or in a separate e-mail;

- The e-mail body/ text from the Contractor should also contain the following:

- List of the attached documents incl. title of the document, number, date of issue, amount UAH;

- Confirmation, that the services/ works/ goods specified in the attached documents were provided/ delivered/ supplied in full;

- Full name, position, contact details, full name of the organization.

- Confirmation, that the original documents (invoices, 2 copies of acts of acceptance, other financial supporting documents) will be kept by the Contractor and submitted later as soon as the security situation permits upon the request of GIZ. The deadline and the address for the delivery of documents will be agreed between GIZ and the Contractor via e-mail.

- Each invoice and act of acceptance shall contain the Project Number and contract number.

- By submitting the Invoice the Contractor should indicate (in the invoice or in the e-mail) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

- In case the Contractor is a VAT Payer at the moment of the Invoice issuing, the VAT exemption clause shall be applicable, and the Contractor should also submit the Tax Invoice to GIZ as soon as that is available

Timesheet standard template can be found here https://www.giz.de/en/worldwide/63065.html

- Other Provisions

  - General

The Contract will be signed by the Parties as a soft copy version by sending to each other by electronic means signed and scanned copies of the Contract and annexes. Such Contract shall have full legal force as the hard copies of it. The hard copies will be submitted as soon as the security situation in Ukraine stabilizes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine and Supplements to General Terms of contract governing Contracts with Appraisers/Firms of Consultants (local) published on the link  Закупівлі - giz.de (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor :__________ (indicate name/-s, surname/-s, phone/-s, e-mail/-s) (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation)

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

Additionally, the Tenderer/ Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, a citizen of the Russian Federation, except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation.

GIZ reserves the right to verify this information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

The given procurement of services/ works upon the Contract shall be carried out at the funds of the funds of the Project of International Technical Assistance (Project ITA), PN: 19.2290.5-003.00, Project title “Promotion of Energy Efficiency and Implementation of the EU Energy Efficiency Directive in Ukraine”, registered by the Secretariat of the Cabinet of Ministers of Ukraine (registration card of the project (program) No. 4644-02 dated 25.10.2023) and complies with the category (type) of Services specified in the purchase plan available at address https://www.kmu.gov.ua/diyalnist/mizhnarodna-dopomoga/pereliki-zareyestrovanih-proektiv-z-planami-zakupivel

The above-mentioned ITA project is implemented within the Framework Agreement between the Government of Ukraine and the Government of the Federal Republic of Germany on Counselling and Technical Cooperation dated 29/05/1996 and Agreement between the Government of Ukraine and the Government of the Swiss Confederation on technical and financial cooperation dated 13.10.1997.

The given procurement of services/ works upon the Contract shall be determined free from VAT under provisions of cl.197.11 Art. 197 of the Tax Code of Ukraine. Operations for providing services under this Agreement are subject to VAT exemption.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, then the Contractor must notify GIZ of such VAT registration in writing or in electronic form by means of submission of an e-mail with copy of the Excerpt from VAT Registration Registry to the GIZ’s e-mail address indicated in the details of the Contract. The Contractor must submit the mentioned notification to the GIZ not later than 1 calendar day following the day of VAT registration. 
At the same time the Parties agreed that the purchase of Services after the VAT registration of the Contractor shall be exempt from VAT in accordance with the abovementioned.

# Outsourced processing of personal data

The performance of the contract may be associated with the processing of personal data by the contractor, who would alone define the nature of such data and how such processing would be carried out. In such cases, the contractor shall act as an independent DATA CONTROLLER and must alone comply with ALL applicable data protection obligations, including regional and local laws. The contractor must process personal data only when a given goal cannot be reasonably attained without such data. The data protection principles such as lawfulness, data minimization, accuracy, purpose limitation, storage limitation, transparency, integrity and confidentiality, and accountability, as well as the numerous rights of the data subject must be paid due attention. The GIZ is NOT in any way responsible for such processing.

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- technical bid containing a description of the methodology proposed in relation to the identified tasks (described in Para 3). Technical bid must be signed and stamped (if stamp is used);

- CVs of 2 experts with relevant work experience, qualifications (education, certificates).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English / Ukrainian language.

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English language.

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise, the bid will be disqualified.

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Commercial bid must be signed and stamped (if a stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

    - Documents for tenderer’s eligibility confirmation

The tendered should:

| The tenderer is obliged to conform to the following eligibility requirements: | The tenderer must provide the following document to confirm the compliance with eligibility requirements: |
| --- | --- |

GIZ reserves the right to verify this information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Penalties:

In case of refusal in providing of services or non-provision of the ordered services under the Contract the Contractor shall pay a penalty of 100% of such unprovided Services;

In case of poor provision of the Services, which led to injuries of the Participants of the Events caused by Contractor’s actions or mass disease (e.g. poisoning) of the Participants of the Events, the Contractor shall reimburse 100% of the order amount and corresponding losses of those suffered, including but not limited to, the cost of hospitalization, medical treatment, and so on;

Payment of any penalties shall be made solely on the basis of a written request (via e-mail), which shall be addressed by one Party to another, along with a respective original invoice within 10 (ten) calendar days after the reasons for these sanctions occurred. After expiration of the specified period of 10 (ten) calendar days, any requests for payment of these penalties will not be accepted by GIZ and all such requests will be considered an invalid.

Penalties shall be paid by the Parties within 10 (ten) bank days after the respective written request and the invoice are received.

Payment of penalties does not relieve the Parties from performing their obligations.

- Annexes

- Annex 1 – Travel regulations

Annex 1 Travel regulations (hereinafter – Regulations)

1. Accommodation allowance Overnight accommodation costs are reimbursed to the extent agreed in the Contract against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). Limits for overnight accommodation shall be stipulated in the Contract. Hotel reservations are made by an expert/consultant by himself/herself. For accommodation during business trips room category not higher than Standard (or equal) is to be booked, unless otherwise is expressly stated in the Contract. Overnight accommodation costs during domestic and international business trips shall not be reimbursed for business trips to a place of residence during which the expert/consultant stays in his/her own home or place where he/she maintains his/her own household.

2. Trains Train tickets shall be booked and purchased by the expert/consultant/participant by himself/herself. The ticket purchase fee is not to be reimbursed. If required, first class tickets (abbreviation in Ukraine: Л – two-seater, soft-seated, М – deluxe, single-seater, three-seater) are possible in case your journey not less than 2 hours. The decision on the class tickets is in the responsibility of traveler and should be considered based on the cost-efficiency and security reasons (e. g. overnight trip).

3. Buses Bus tickets must be booked and purchased independently by an expert/consultant/participant.