| Analysis of the legislation on demolition and destruction waste management |  | Project number/ cost centre: 19.2290.5 – 001.00 |
| --- | --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

Project 	The Project "Promotion of Energy Efficiency and Implementation of the EU Energy Efficiency Directive in Ukraine"

MinDev	Ministry for Communities and Territories Development of Ukraine

- Context

The Project is aimed at supporting the improvement of the political and legal framework in the field of energy efficiency by providing appropriate technical assistance. The Project facilitates political consultations on the implementation of the EU Energy Efficiency Directive 2012/27/EU (EED) together with the EU Energy Performance of Buildings Directive 2010/31/EU (EPBD) into Ukrainian legislation.

The Project supports the MinDev (the Beneficiary), the Ministry of Energy of Ukraine (the Recipient) and the State Agency for Energy Efficiency and Energy Saving of Ukraine (the Recipient) in three areas of activity: political advice, implementation of reforms and implementation of legislation, informational and dialogue events. With the beginning of the full-scale invasion of Ukraine, the Project started supporting the MinDev in developing new construction legislation, which is essential during the war, including new legislation on construction and demolition waste management.

The MinDev addressed a request to the Project to provide advisory and expert support in developing a draft National Concept of Construction Waste Management, which takes into account the specifics of Ukrainian legislation and best European practices, and should include proposals for improving the existing regulatory framework, namely, contain a prepared indicative list of regulations (legislative and by-laws) necessary for the implementation of a new construction and demolition waste management policy.

To note, currently in Ukraine, buildings and structures of various targeted use have suffered significant damage and destruction as a result of the armed aggression in Ukraine, which has led to the generation of significant volumes of destruction debris including large-sized ones. The specified type of waste from the destruction creates difficulties in conducting restoration and search works that directly affects national security and defense, the natural environment, can entail significant financial and material losses and pose a threat to people's lives and health. The current destruction has affected all types of buildings and infrastructures, from rural dwellings to critical facilities such as dams and power plants. This complicates the dismantling process, requiring the involvement of various specialists, including engineers, hazardous waste and recycling experts. The World Bank (RDNA3) estimates that the economic cost of dismantling and removing debris could be as high as US$11 billion.

Restoration of damaged and destroyed buildings and structures in Ukraine is the main priority of the Ukrainian Government and the MinDev, which directly forms the policy in the field of restoration and seeks the best solutions for future reconstruction. Such decisions should be built on the world's best practices and principles of transparency and equal access. One of the main parameters that should be ensured by high-quality reconstruction is the high energy efficiency parameters based on the European model. This is necessary not only for the immediate reconstruction of destroyed cities, but also in the regions that have not suffered destruction. After all, the issue of excessive and, at times, abnormally inefficient use of energy resources is relevant for all spheres of the economy, but it is especially painful in the housing sector.

In addition, Ukrainian state policy requires a comprehensive approach to the management of such waste that would be in line with European standards and best international practices and the principles of the circular economy. Regulation of the management of debris from destructions is an integral part of the implementation of the EU Directives in field of energy efficiency. Building debris resulting from destruction from explosions and shelling is different from "classic" construction debris and, in a situation of an active phase of war, debris from destruction continues to increase and accumulate. Waste from destruction is a special, specific and dangerous type of waste, for which the mechanism of handling in a safe, ecological and efficient way required appropriate normative and legal regulation at the legislative level.

It should be noted that the state of waste management in the construction sphere in Ukraine is at the stage of formation and development, but the pace of such development has been somewhat slowed down due to military aggression. The Law of Ukraine ‘On Waste Management’ is currently the framework for waste management in Ukraine. Article 17 of the Law stipulates that business entities engaged in the construction or demolition of buildings and engineering structures are obliged to ensure separate collection of construction and demolition waste, its accounting and transfer to business entities in the field of waste management for their treatment. Construction and demolition waste that is not hazardous is subject to preparation for reuse, recycling, or other material recovery, including backfilling. It is also envisaged to set targets for the preparation of waste for reuse, recycling, other material recovery, including backfilling at the Government level.

Since the beginning of the full-scale invasion in 2022, the Cabinet of Ministers of Ukraine approved the Procedure for Waste Management resulting from damage (destruction) of buildings and structures as a result of hostilities, terrorist acts, sabotage or work to eliminate their consequences by Resolution No. 1073 dated 27 September 2022. According to MinDev, as of December 2024, about 650,000 tonnes of demolition waste has been accumulated at temporary storage sites and landfills, which does not include damaged and destroyed facilities that are subject to dismantling.

At the same time, the MinDev, together with the Ministry of Environment, is working on the National Waste Management Plan until 2033, which is a planning framework document that outlines the main directions to be taken to implement the state waste management policy and contains general principles for the formation of the state policy on construction and demolition waste management. After the Ukrainian Government approves the National Waste Management Plan until 2033, the MinDev will have to develop a National Concept of Construction Waste Management, which will regulate in detail the ways, methods and tools for construction waste management in Ukraine.   The main goal of a National Concept of Construction Waste Management is to improve Ukraine's policy in the field of construction and demolition waste management by developing a modern legislative approach that meets international standards, European practices and circular economy principles. This will contribute to sustainable development, efficient use of resources and support for vulnerable communities affected by military aggression. Supporting the need to continue the policy of managing waste from destruction, it is currently considered appropriate to introduce a new policy of managing waste from construction and demolition. This direction is in line with the Government's priorities on the path to European integration, in particular with regard to the implementation of the principles of the ‘circular’ economy to ensure the rational use of resources.

This approach will further provide for a gradual transition from the «emergency» regulation of martial law to a comprehensive solution to the problem of managing construction waste, of which demolition waste is a special case. However, the introduction of appropriate regulation requires in-depth analytical research. This will create the basis for the development of an effective regulatory framework that meets modern standards and the needs of Ukraine in the context of post-war recovery.

- Tasks to be performed by the contractor

The main objective of this Contract is to analyse the legislation of foreign and European countries in the field of construction waste management, as well as to analyse the best global practices of foreign countries in this area. Also, to analyse the Ukrainian legislation in force in the field of construction waste management and the situation in Ukraine due to the large amount of waste from demolition. Based on the analysis of different legislation, the Contractor will provide proposals for improving the legal framework in the field of construction waste and develop a draft National Concept of Construction Waste Management in Ukraine.

- Tasks

The contractor is responsible for providing the following tasks / works, distributed between the two work packages (WP1 and WP2) as set out in the table below:

- analysing global and European experience and legislation in the field of construction waste management, as well as preparing an analytical report for the MinDev;

- analysing Ukrainian construction legislation and by-laws in the field of construction waste management, identifying gaps in the legislation, determining ways to address the gaps, and preparing relevant recommendations for the MinDev;

- preparing and presenting of analytical materials (information materials, references, comparative tables of legislation) about global and European legislation, as well as analysis of Ukrainian legislation at the meeting of the Working Group in the MinDev (at least 1 Working Group meeting in offline format);

- preparing the final version of the Analytical Report, taking into account comments and remarks of the MinDev Working Group members, academics and representatives of Ukrainian business, provided to the draft Analytical Report;

- providing to Project the informational materials (references, comparative tables of legislation) for international knowledge exchange (public/private) for post-conflict and post-disaster countries for circular C&D and Circular Reconstruction;

- organising and conducting at least 2 roundtables in online format to discuss problematic issues of construction waste management policy in Ukraine with representatives of ministries, agencies, academics, and representatives of the Ukrainian construction business;

- collecting statistical data from local military administrations on the existing construction waste generated as a result of destruction and dismantling, as well as analysing such statistical data and providing a relevant analytical note to the MinDev (Department of Technical Regulation in Construction);

- developing of a draft National Concept of Construction Waste Management, which takes into account the specifics of Ukrainian legislation and best European practices, and should include proposals for improving the existing regulatory framework, as well as a list of regulations (legislative and by-laws) necessary for the implementation of the new construction and demolition waste management policy;

- presenting the draft National Concept of Construction Waste Management to the Working Group in MinDev, discussing comments from the Working Group members, and taking such comments into account (at least 1 Working Group meeting in offline format)

| Milestones/partial works | Anticipated deadline/place/person responsible | Criteria for acceptance |
| --- | --- | --- |
| WP 1 Analysing global, European and Ukrainian legislation on construction waste management 1.1. Preparing the draft of Analytical report on global, European and Ukrainian legislation on construction waste management, as well as recommendations for the implementation of best practices in Ukrainian legislation 1.2 Presentation of the draft of Analytical Report on global, European and Ukrainian legislation on construction waste management at the Working Group of the MinDev 1.3 Conducting the roundtable discussion with Ukrainian experts and representatives of Ukrainian business to discuss problematic issues of construction waste management 1.4 Preparing the final version of Analytical report on global, European and Ukrainian legislation on construction waste management, as well as recommendations for the implementation of best practices in Ukrainian legislation | March 31, 2025, responsible person(s) - contractor April 04, 2025, responsible person(s) - contractor April 04, 2025, responsible person(s) - contractor April 08, 2025, responsible person(s) - contractor | The draft of Analytical report prepared and provided to the Project team for comments and observations Presentation materials prepared and provided to the Project team for comments and observations Report on the roundtable, which includes lists of participants and materials that were presented, as well as feedback from participants The final Analytical report prepared and provided to the Project team |
| WP 2 Developing the draft of National Concept of Construction Waste Management 2.1 Preparing the draft of National Concept of Construction Waste Management 2.2. Presentation of the draft of National Concept of Construction Waste Management at the Working Group of the MinDev 2.3 Conducting the roundtable discussion with Ukrainian experts and representatives of Ukrainian business to discuss the main issues, principals of the draft of National Concept of Construction Waste Management | May 26, 2025, responsible person(s) - contractor May 29, 2025, responsible person(s) - contractor June 2, 2025, responsible person(s) - contractor | The draft of National Concept prepared and provided to the Project team for comments and observations Presentation materials prepared and provided to the Project team for comments and observations Report on the roundtable, which includes lists of participants and materials that were presented, as well as feedback from participants |

The contract duration is from 13.03.2025 till 30.06.2025.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| WP 1 Analysing global, European and Ukrainian legislation on construction waste management 1.1. Preparing the draft of Analytical report on global, European and Ukrainian legislation on construction waste management, as well as recommendations for the implementation of best practices in Ukrainian legislation 1.2 Presentation of the draft of Analytical Report on global, European and Ukrainian legislation on construction waste management at the Working Group of the MinDev 1.3 Conducting the roundtable discussion with Ukrainian experts and representatives of Ukrainian business to discuss problematic issues of construction waste management 1.4 Preparing the final version of Analytical report on global, European and Ukrainian legislation on construction waste management, as well as recommendations for the implementation of best practices in Ukrainian legislation | The draft of Analytical report (at least 30 pages) prepared and provided to the Project team for comments and observations. The Analytical report should be provided in Word format, in Ukrainian Presentation materials (at least 10 pages) prepared and provided to the Project team for comments and observations. The presentation materials should be provided in Word format, in Ukrainian. The Contractor must personally participate in the meeting of the Working Group at the MinDev offline Report on the roundtable (at least 10 pages), which includes lists of participants and materials that were presented, as well as feedback from participants. The report should be provided in Word format, in Ukrainian. The final Analytical report (at least 30 pages) prepared and provided to the Project team. The final Analytical report should be provided in Word format, in Ukrainian. The final Analytical report should take into account comments from the working group members and the Project team members | March 31, 2025, April 4, 2025, April 4, 2025, April 8, 2025, |
| WP 2 Developing the draft of National Concept of Construction Waste Management 2.1 Preparing the draft of National Concept of Construction Waste Management 2.2. Presentation of the draft of National Concept of Construction Waste Management at the Working Group of the MinDev 2.3 Conducting the roundtable discussion with Ukrainian experts and representatives of Ukrainian business to discuss the main issues, principals of the draft of National Concept of Construction Waste Management | The draft of National Concept of Construction Waste Management (at least 30 pages) prepared and provided to the Project team for comments and observations. The draft of National Concept of Construction Waste Management should be provided in Word format, in Ukrainian Presentation materials (at least 10 pages) prepared and provided to the Project team for comments and observations. The presentation materials should be provided in Word format, in Ukrainian. The Contractor must personally participate in the meeting of the Working Group at the MinDev offline Report on the roundtable (at least 10 pages), which includes lists of participants and materials that were presented, as well as feedback from participants. The report should be provided in Word format, in Ukrainian. | May 26, 2025, May 29, 2025, June 2, 2025, |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them, namely presentation and interaction between the relevant actors in the contractor`s area of responsibility (1.2.1) and Strategy for establishing cooperation and then cooperation with the relevant actors (1.2.2).

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

The personnel must be provided for all positions, otherwise, the bid will be disqualified. Each expert can hold only one position, multiple position holding is not permitted.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team leader

Tasks of the team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local and international short-term experts

- Regular reporting in accordance with deadlines

Qualifications of the team leader

- Education/training (2.1.1): university degree (Bachelor) in the field of engineering and/or construction

- Language (2.1.2): C2-level language proficiency (please use the A1-C2 proficiency levels defined in the CEFR) in Ukrainian

- General professional experience (2.1.3): 15 years of professional experience in the field of construction and/or in the field of construction production sector

- Specific professional experience (2.1.4): 9 years in in the field of energy efficiency, implementation of energy-efficient construction projects

- Leadership/management experience (2.1.5): 5 years of management/leadership experience as project team leader or manager in a company

## Key expert 1

Tasks of key expert 1

- Analysing global and European practices of construction waste management

- Collecting and analysing statistical information from regional military administrations

- Participation in the Working Group of the MinDev

- Preparation materials and presentations for participation in the Working Group of the MinDev

Qualifications of key expert 1

- Education/training (2.2.1): university degree (Bachelor) in the field of ecology

- Language (2.2.2): C2-level language proficiency (please use the A1-C2 proficiency levels defined in the CEFR) in Ukrainian

- General professional experience (2.2.3): 15 years of professional experience in the field of environmental safety, development of regulatory and technical documentation in the area of ecology of industrial enterprises, construction, and reconstruction projects sector

- Specific professional experience (2.2.4): 9 years in management systems, including environmental and life cycle management.

## Short-term expert pool with 4 members

For the technical assessment, an average of the qualifications of all specified members of the expert pool is calculated. Please send a CV for each pool member (see below Chapter 10 Requirements on the format of the bid) for the assessment.

Tasks of the short-term expert pool

- Analysing Ukrainian legislation and identifying gaps

- Developing recommendations for the MinDev on ways to shape policy in the field of construction waste management

- Developing a draft of National Concept of construction waste management

- Organising and holding roundtables, preparing materials

Qualifications of the short-term expert pool

- Education/training (2.6.1): 4 experts with university qualification (Master) in law

- Language (2.6.2): 4 experts with C2-level language proficiency (please use the A1-C2 proficiency levels defined in the CEFR) in Ukrainian

- General professional experience (2.6.3): 4 experts with 15 years of professional experience in the legal sector

- Specific professional experience (2.6.4): 4 experts with 9 years of professional experience in legal drafting

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Socio-cultural skills

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

# Costing requirements

## Assignment of personnel and travel expenses

No travel expenses are foreseen for this assignment.

## Sustainability aspects for travel and travel regulations

Not applicable

Specification of inputs

## contracts for works:

The following basic calculations for the contract for works are a reference value based on the acceptance criteria for each partial work/milestone specified in Chapter 2 (Tasks to be performed by the contractor).

Since the contract to be concluded is a contract for works, we would ask you to offer your services at a lump sum price.

| Milestones/partial works | Estimated expert days for orientation | Anticipated deadline/place/person responsible |
| --- | --- | --- |
| WP 1 Analysing global, European and Ukrainian legislation on construction waste management | 104 expert days | April 8, 2025, Kyiv |
| WP 2 Developing the draft of National Concept of Construction Waste Management | 160 expert days | June 2, 2025, Kyiv |

# Inputs of GIZ or other actors  Not Applicable

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the commercial bid.

Anticipated payment schedule:

In consideration of work completed, the Contractor shall be paid in the following instalments:

| Instalment # | Anticipated payment date | Price per WP | Deliverables and reporting | Project Number and % of costs split (if applicable) |
| --- | --- | --- | --- | --- |
| 1 Interim payment | 18.04.2025 | WP 1 | Acc. to cl. 2.2 (WP1) | 2019.2290.5-001.00 |
| 5 Final payment | 10.06.2025 | WP 2 | Acc. to cl. 2.2 (WP2) | 2019.2290.5-001.00 |

  - Financial proposal

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, incl. VAT.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works (“up to”), on the ground of scanned invoices, acts of acceptance, submitted in digital form within 10 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Invoices, acts of acceptance and etc. shall be scanned as one PDF document (up to 4 mb) and send as an attachment to the e-mail of the GIZ Project Representatives (the e-mail shall be provided additionally) together with other financial supporting documents as and if stipulated by the Contract; the technical documents (reporting/ deliverables) can be submitted either in the same or in a separate e-mail;

- The e-mail body/ text from the Contractor should also contain the following:

- List of the attached documents incl. title of the document, number, date of issue, amount UAH;

- Confirmation, that the services/ works/ goods specified in the attached documents were provided/ delivered/ supplied in full;

- Full name, position, contact details, full name of the organization.

- Confirmation, that the original documents (invoices, 2 copies of acts of acceptance, other financial supporting documents) will be kept by the Contractor and submitted later as soon as the security situation permits upon the request of GIZ. The deadline and the address for the delivery of documents will be agreed between GIZ and the Contractor via e-mail.

- Each invoice and act of acceptance shall contain the Project Number and contract number

- By submitting the Invoice the Contractor should indicate (in the invoice or in the e-mail) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%).

- Other Provisions

  - General

The Contract will be signed by the Parties as a soft copy version by sending to each other by electronic means signed and scanned copies of the Contract and annexes. Such Contract shall have full legal force as the hard copies of it. The hard copies will be submitted as soon as the security situation in Ukraine stabilizes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine published on the link  Закупівлі - giz.de (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor (indicate name/-s, surname/-s, phone/-s, e-mail/-s) (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation)

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify this information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption Not Applicable

# Outsourced processing of personal data

The performance of the contract may be associated with the processing of personal data by the contractor, who would alone define the nature of such data and how such processing would be carried out. In such cases, the contractor shall act as an independent DATA CONTROLLER and must alone comply with ALL applicable data protection obligations, including regional and local laws. The contractor must process personal data only when a given goal cannot be reasonably attained without such data. The data protection principles such as lawfulness, data minimization, accuracy, purpose limitation, storage limitation, transparency, integrity and confidentiality, and accountability, as well as the numerous rights of the data subject must be paid due attention. The GIZ is NOT in any way responsible for such processing

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- technical bid containing a description of the methodology proposed in relation to the identified tasks (described in Para 3). Technical bid must be signed and stamped (if stamp is used);

- CVs of all 6 (six) experts with relevant work experience, qualifications (education, certificates (if any)).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in  Ukrainian/English language.

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in Ukrainian/English language.
The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise, the bid will be disqualified.

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Commercial bid must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

    - Documents for tenderer’s eligibility confirmation

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on uncontrolled territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.