| Organization and delivery of the short-term requalification course «Solar power plant installer» | Project number/ cost centre: 19.9022.5-007.00 |
| --- | --- |

Terms of reference

- List of abbreviations

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

ToR	Terms of reference

TC 	Technical cooperation

TVET	Technical and Vocational Education and Training

BMWK	 Federal Ministry for Economic Affairs and Climate Action

SPP	Solar Power Plant

STС	Short-term course

PV	Solar photovoltaics

- Context

The German – Ukrainian cooperation within the framework of the project Renewables for resilient Ukraine (R2U) is targeting Ukrainian communities. The Project is implementing initiatives according to the agreement between the Ministry of Energy of Ukraine and Federal Ministry for Economic Affairs and Climate Action (BMWK) to deepen the German – Ukrainian energy partnership with a focus on green renewable energy and energy recovery in Ukraine. The goal of R2U project is to provide support to communities in the implementation of sustainable decentralized renewable energy systems for self-production and consumption in public buildings (schools, hospitals, kindergartens, retirement homes, etc.), critical infrastructure (drinking water utilities, etc.) and to showcase and communicate the advantages, the economic feasibility and to support an investment framework for broad scaling of respective approaches.

The Project is structured for supporting green recovery and modernization of the Ukrainian energy infrastructure.

Russian invasion that started on 24th of February 2022 has disrupted all sectors of the Ukrainian economy all over the country. All micro, small, medium, and large enterprises in Ukraine have been affected in one way or another. Running a business in war time poses a series of challenges for Ukrainian business owners: supply chains get disrupted, prices of inputs and outputs change, market demand shifts, infrastructure and connectivity become unreliable, workers’ turnover affects operations, basic services may not be available etc. Another challenge that become especially obvious during the last year is lack of qualified labor force caused by mobilization of men aged 25 to 60. To address labor shortages, companies are increasingly focusing on inclusive employment, opening jobs to women, young people, older people and people with disabilities.

At the same time, Ukraine is facing unprecedented challenges in rebuilding its power system and maintaining energy security due to the disruptions caused by the Russian aggression. According to DIW Econ’s study “Renewable energies in Ukraine”, renewables are a feasible and reasonable option to replace the destroyed thermal power plants in Ukraine. They are a feasible and reasonable option for rebuilding a resilient and sustainable energy system and will play a pivotal role in energy security. Transition from “brown” to a dark green economy requires transition of technologies. In response to this the Project is launching short term requalification courses for future professionals in renewable energy.

- Tasks to be performed by the contractor

The aim of the Project is strengthening the resilience of the Ukrainian energy system through decentralization of electricity generation and distribution, the use of adapted assistance tools and based on the concept of "Green Recovery", which should make these changes socially, economically, and environmentally sustainable.

Results of the recent studies conducted by GIZ, including DIW Econ’s study “Renewable energies in Ukraine” and the “Green Jobs in Lviv and Volyn regions” study conducted by NGO “Society and Environment”, demonstrate that the massive expansion of wind and solar energy will require large numbers of construction, installation and maintenance professionals.

In order to respond to the existing and potential labor market demand in the process of green transition, support the creation of equal and just opportunities for women and men, create possibilities for requalification for unemployed people, including internally displaced persons (hereinafter «IDP’s») and war veterans as well as to respond to the demand for professionals in renewable-energy industry, the Project is looking to continue its successful efforts in implementation of requalification courses.

The course introduction to solar photovoltaics aimed at building foundations of installation and maintenance of solar PV systems, basics of energy renovation for buildings and structures, types of photovoltaic modules and systems.

  - Tasks

The contractor is responsible for providing the following work:

- Developing questionnaire and conducting a survey among future participants with the aim of access their current level of awareness about the topics of the training program.

- Organization of enrolment of two groups of participants – 10 participants each (20 participants in total), including by conducting call for applications among possible participants withing the target groups (internally displaced people (hereinafter «IDP’s»), veterans, and women should be represented). The number of selected participants should be 20 individuals at least 30% of whom should be women.

- At least 40% of the selected participants should represent the following target groups: IDP and war veterans.

- Organization and delivery of the short-term requalification course «Solar power plant installer» (including training venues (labs, workshops, and other facilities), as well as necessary training materials, equipment, and tools to ensure comprehensive hands-on learning).

The study modules should cover the following topics:

Module 01 / Recorded video tutorials / Online (min 4 hours)

Solar power plants

- Basic concepts of photovoltaics

- Components and types of solar power plants

- Green tariff and market trends

Module 02 / Recorded video tutorials / Online (min 4 hours)

Photovoltaic modules

- Types of PV modules depending on the production method

- Types of connections, formation of arrays

Module 03 / Recorded video tutorials / Online (min 4 hours)

Batteries

- Parameters and features of battery operation

- Difference between lithium and lead-acid batteries

Module 04 / Recorded video tutorials / Online (min 4 hours)

Inverters

- Technical features of inverters

- Selection of inverters

- Effect of inverter on increasing and decreasing power generation

05 Module / Recorded video lessons / Online (min 4 hours)

Controllers

- The purpose of the controller in the PV chain

- The difference between PWM controllers and MPPTs

Module 06 / Recorded video tutorials / Online (min 4 hours)

Protective automation

- Ready-made protection boards for solar power plants and the principle of operation of protective automation elements

Module 07 / Recorded video tutorials / Online (min 4 hours)

Grid power plants

- Equipment selection and design of grid stations with a capacity of up to 30 kW

- Calculations of station location

- Practical task: Design a 30 kW station and select equipment.

Module 08 / Recorded video tutorials / Online (min 4 hours)

Autonomous and hybrid power plants

- Selection of PV modules, inverters, batteries and controllers for the assembly of an autonomous and hybrid PV system

- Practical task: Design an autonomous station and select equipment.

Module 09 / Recorded video tutorials / Online (min 4 hours)

Services and calculators for designers

- Services and online calculators for designers

- Ready-to-use online forms with templates for various tasks

Module 10 / Recorded video tutorials / Online (min 4 hours)

Legal aspects

- Main aspects of SPP registration

- Connecting SPP to the Green Tariff

Module 11 / Offline (min 2 days)

Introduction to installation: preparation, tools and mounting systems for PV modules

- Introduction to the profession

- Preparation for installation

- PV mounting systems

- Overview of tools

Module 12 / Offline (min 2 days)

Equipment and safety at height

- Basic regulations and legislation

- Overview of equipment

- Tying knots

- Evacuation of an injured person

- Practical use of equipment

Module 13 / Offline (min 2 days)

PV installation

- Theory of PV installation on different types of roofs

- Practice of PV installation on metal and bituminous roofs

Module 14 / Offline (min 2 days)

- Startup and basic configuration of the plant

- Theory of installation of the inverter and other system components

- Startup and basic setup of the LuxPower plant

- Assembling the protection panels

- Connecting the plant to the home distribution panel

Module 15 / Online (min 4 hours)

- Impacts of climate change on Ecosystems and Biodiversity

- Climate policy priorities in Ukraine

- Providing mentorship and employment advice to the participants of the course. Mentorship should include:

- One-on-one meetings with each of the 20 participants with the aim to provide personalized guidance according to his or her career goals, challenges, and current stage of professional development

- Industry Insight: Sharing knowledge about the solar energy industry, including trends, technological advancements, and challenges that may impact employment opportunities

- Recommendations on further skill development: Help participants identify areas where they need to improve (e.g., technical skills, communication, safety protocols) and guide them through resources to build these skills

- Job Search Strategies: Advise on where to look for job opportunities, such as specific companies in the solar industry, types of vacancies

- Recommendations on certifications and licensing in Ukraine to ensure participants understand any additional certifications or licenses they may need, such as those related to electrical work, safety standards, or specific solar installation qualifications

- Labor Market Trends: keep participants updated on the demand for solar installers in different regions and markets. Discuss potential for growth within the industry, as the renewable energy sector is rapidly expanding

- For participants interested in starting their own business, provide advice on how to navigate the entrepreneurial side of the industry, including business planning, certifications, and finding clients

- Where possible, work with partners to offer job placements for participants. This could include internships, apprenticeships, or direct hiring into a solar installation company

| Milestones/partial works | Anticipated deadline/place/person responsible | Criteria for acceptance |
| --- | --- | --- |
| Milestone 1: |  |  |
| 1.1. Developing questionnaire and conducting a survey among future participants | 31.03.2025 / Team Leader | Report on conducted needs assessment |
| 1.2. Enrolment of 20 students | 31.03.2025 / Team Leader | List of enrolled students for two groups of students |
| Milestone 2: |  |  |
| 2.1. Conducting 15 study modules for two groups | 25.04.2025 / Team Leader | List of graduates for two groups of students |
| 2.2. Providing mentorship and employment advice to the participants | 25.04.2025 / Team Leader | Final report that includes detailed description of the provided employment advice: - Results of the one-on-one meetings with each of the participants - Statistics on participants interested in starting their own business in the renewables industry - General overview of provided rrecommendations on further skill development, job Search Strategies, job placements, including internships/ apprenticeships opportunities that were proposed to the participants |

The contract duration is from 05.03.2025 till 30.04.2025.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| Report on conducted needs assessment | PDF | 31.03.2025 |
| List of enrolled students | PDF | 31.03.2025 |
| List of graduates | PDF | 25.04.2025 |
| Final report | PDF | 25.04.2025 |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

Not Applicable - The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

Not Applicable - The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

Not Applicable - The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation.

## Project management of the contractor (1.6)

Not Applicable.

## Further requirements (1.7)

Not Applicable.

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

The personnel must be provided for all positions, otherwise, the bid will be disqualified. Each expert can hold only one position, multiple position holding is not permitted.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team leader

Tasks of the team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local and international short-term experts

- Regular reporting in accordance with deadlines

Qualifications of the team leader

- Education/training (2.1.1): university degree (Master’s degree) in Engineering, Ecology, Management or similar field

- Language (2.1.2): B2-level language proficiency in English

- General professional experience (2.1.3): 15 years of professional experience in Engineering, Ecology, Management or similar relevant field

- Specific professional experience (2.1.4): 8 years of professional experience in providing trainings

- Leadership/management experience (2.1.5): 8 years of management/leadership experience as project team leader or manager in a company

- Regional experience (2.1.6): Not applicable.

- Development cooperation (DC) experience (2.1.7): 5 years of experience in DC projects

- Other (2.1.8): Not applicable.

## Key expert 1

Tasks of key expert 1

- Developing questionnaire and conducting survey

- Preparing call for applications

- Selection of participants

- Providing online training

- Quality control and assessment of the study process

Qualifications of key expert 1

- Education/training (2.2.1): university degree (Master’s) in Ecology, Economy or similar field

- Language (2.2.2): Not applicable.

- General professional experience (2.2.3): 8 years of professional experience in project management, education or similar field

- Specific professional experience (2.2.4): 7 years of professional experience in providing trainings

- Leadership/management experience (2.2.5): Not applicable.

- Regional experience (2.2.6): Not applicable.

- Development cooperation (DC) experience (2.2.7): 5 years of experience in DC projects

- Other (2.2.8): Not applicable.

## Key expert 2

Tasks of key expert 2

- Coordinating study process and communication with participants

- Providing online and offline trainings and assessment

Qualifications of key expert 2

- Education/training (2.3.1): university degree (Master’s) in Engineering, Ecology, Education or similar field

- Language (2.3.2): Not applicable.

- General professional experience (2.3.3): 10 years of professional experience in Engineering, Ecology, Education or similar relevant field

- Specific professional experience (2.3.4): 7 years of professional experience in providing trainings

- Leadership/management experience (2.3.5): Not applicable.

- Regional experience (2.3.6): Not applicable.

- Development cooperation (DC) experience (2.3.7): 2 years of experience in DC projects

- Other (2.3.8): Not applicable.

## Key expert 3

Tasks of key expert 3

- Coordinating study process and communication with participants

- Providing online and offline trainings and assessment

Qualifications of key expert 3

- Education/training (2.4.1): university degree (Master’s) in Engineering, Ecology, Education or similar field

- Language (2.4.2): Not applicable.

- General professional experience (2.4.3): 5 years of professional experience in Engineering, Ecology, Education or similar field

- Specific professional experience (2.4.4): 4 years of professional experience in providing trainings

- Leadership/management experience (2.4.5): Not applicable.

- Regional experience (2.4.6): Not applicable.

- Development cooperation (DC) experience (2.4.7): 2 years of experience in DC projects

- Other (2.4.8): Not applicable.

# Costing requirements

## Assignment of personnel and travel expenses

Not Applicable.

## Contracts for works:

The following basic calculations for the contract for works are a reference value based on the acceptance criteria for each partial work/milestone specified in Chapter 2 (Tasks to be performed by the contractor).

Since the contract to be concluded is a contract for works, we would ask you to offer your services at a lump sum price.

| Milestones/partial works | Estimated expert days for orientation | Anticipated deadline/place/person responsible |
| --- | --- | --- |
| 1.1. Developing questionnaire and conducting a survey among future participants | 10 Team leader; man/day; 5. Key Expert 1; man/day; 5. | 31.03.2025 / Team Leader |
| 1.2. Enrolment of 20 students (two groups, 10 students each) | 10 Team leader; man/day; 5. Key Expert 1; man/day; 5. | 31.03.2025 / Team Leader |
| 2 Conducting 15 study modules for two groups; Providing mentorship and employment advice to the participants | 65 Course preparation and management Team leader; man/day; 7. Key Expert 1; man/day; 5. Key Expert 2; man/day; 7. Key Expert 3; man/day; 7. Course conducting and evaluation Key Expert 1; man/day; 5. Key Expert 2; man/day; 9. Key Expert 3; man/day; 8. Mentorship Team leader; man/day; 2. Key Expert 1; man/day; 5. Key Expert 2; man/day; 5. Key Expert 3; man/day; 5. | 25.04.2025 / Team Leader |

# Inputs of GIZ or other actors

Not Applicable.

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the commercial bid.

Anticipated payment schedule:

In consideration of services completed, the Contractor shall be paid in the following instalments:

| Instalment # | Anticipated payment date | Payment of up to % from total contract value | Deliverables and reporting | Project Number and % of costs split (if applicable) |
| --- | --- | --- | --- | --- |
| 1 Interim payment | 10.04.2025 | 25 | Report on conducted needs assessment; List of enrolled students (for two groups) | 19.9022.5-007.00 |
| 2 Final payment | 30.04.2025 | 75 | List of graduates; Final report | 19.9022.5-007.00 |

  - Financial proposal

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees incl. VAT (if applicable).

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of scanned invoices, acts of acceptance, submitted in digital form within 10 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Invoices, acts of acceptance, etc. shall be scanned as one PDF document (up to 4 mb) and send as an attachment to the e-mail of the GIZ Project Representatives (the e-mail shall be provided additionally) together with other financial supporting documents as and if stipulated by the Contract; the technical documents (reporting/ deliverables) can be submitted either in the same or in a separate e-mail. If the prices in the contract are specified in foreign currency, the Contractor is obliged to indicate prices in all invoices and/or acts of acceptance in two currencies: in foreign currency and in the equivalent amount in UAH and to indicate applied currency exchange rate in accordance with Contract conditions.

- The e-mail body/ text from the Contractor should also contain the following:

- List of the attached documents incl. title of the document, number, date of issue, amount UAH;

- Confirmation, that the services/ works/ goods specified in the attached documents were provided/ delivered/ supplied in full;

- Full name, position, contact details, full name of the organization.

- Confirmation, that the original documents (invoices, 2 copies of acts of acceptance, other financial supporting documents) will be kept by the Contractor and submitted later as soon as the security situation permits upon the request of GIZ. The deadline and the address for the delivery of documents will be agreed between GIZ and the Contractor via e-mail.

- 	Each invoice and act of acceptance shall contain the Project Number, contract number

- By submitting an invoice the Contractor should indicate (in the invoice or in the e-mail) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

- In case the Contractor is a VAT Payer at the moment of the Invoice issuing, the VAT exemption clause shall be applicable and the Contractor should also submit the Tax Invoice to GIZ as soon as that is available.

- Other Provisions

  - General

The Contract will be signed by the Parties as a soft copy version by sending to each other by electronic means signed and scanned copies of the Contract and annexes. Such Contract shall have full legal force as the hard copies of it. The hard copies will be submitted as soon as the security situation in Ukraine stabilizes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine published on the link  Закупівлі - giz.de (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

Not applicable.

# Outsourced processing of personal data

The performance of the contract may bе associated with the processing of personal data bу the contractor, who would аІоnе define the nature of such data and how such processing would bе carried out. Іn such cases, the contractor shall act as аn independent DATА CONTROLLER and must аІоnе comply with ALL аррІісаbІе data protection obligations, including those stemming from regional and ІосаІ laws. The contractor must process personal data оnІу when а given goal cannot bе reasonably attained without such data. The data protection principles such as lawfulness, data minimization, accuracy, purpose limitation, storage limitation, transparency, integrity and confidentiality, and accountability, as well as the numerous rights of the data subject must bе paid due attention.

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- CVs of all experts with relevant work experience, qualifications.

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 2 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in Ukrainian or English language.

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Commercial bid must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

    - Documents for tenderer’s eligibility confirmation

| The tenderer is obliged to conform to the following eligibility requirements: | The tenderer must provide the following document to confirm the compliance with eligibility requirements: |
| --- | --- |
| To be registered as a legal entity/private entrepreneur at least five years before | Extract from the state register of legal entities |

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Option

Not applicable.

- Annexes

Not applicable.