| Services of an external expert in the field of municipal partnerships in eastern Ukraine | Project number/ cost centre: 62.3039.5-001.12 (100%) |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

KZFK	Short-term expert

SKEW                 Service Agency Communities in One World

ToRs	Terms of reference

- Context

On behalf of the Federal Ministry for Economic Cooperation and Development (BMZ) the Service Agency Communities in One World (SKEW) of Engagement Global gGmbH (EG) with Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) supports German-Ukrainian municipal relations and provides them with offers for professional exchange, information, training and networking as well as personnel and financial support instruments.

The German-Ukrainian Municipal Partnership Network has existed since 2016 and has grown significantly since the beginning of Russia's aggressive war against Ukraine in February 2022. Russia's aggressive war against Ukraine has also fundamentally changed German-Ukrainian municipal cooperation. Dozens of German municipalities have been supporting their Ukrainian partners since the first days of the war, including through the purchase of humanitarian aid to address the most pressing supply issues. More than 150 municipal partnerships have been established as solidarity partnerships since the beginning of the war. But partnerships that have been in existence for some times are also facing the challenge of adapting their cooperation to the changing situation in Ukraine. In addition to the acutely needed support services, practical municipal experience in the repair and construction of energy, water or health care systems as well as in the departments of urban development and municipal administrative structures - both regarding reconstruction and in preparation for European Union integration - is becoming increasingly important.

In view of this dynamic, the focus of the support services is on both the initiation of new (solidarity) partnerships and the deepening of existing partnerships.

It is necessary to engage an external expert in the field of municipal partnerships in eastern Ukraine to support the project team in deepening cooperation between German municipalities and Ukrainian municipalities in eastern Ukraine.

- Tasks to be performed by the contractor

The objective of this assignment is to provide expert services in the field of municipal partnerships in eastern Ukraine.

  - Tasks

The Contractor (AN) is responsible for providing the following services:

- In close coordination with the SKEW project team and following familiarisation with the project: advising Ukrainian municipalities in eastern Ukraine on current SKEW proposals, developing partnerships and informing them of upcoming events;

- Participation in activities/events organised by the partner municipalities with the aim of presenting the project "Municipal Partnerships in Ukraine" in eastern Ukraine, after coordination with the SKEW project team;

- Content and organisational support of international online/offline events in the field of German-Ukrainian and international municipal cooperation;

- Content and organisational support in the organisation of national online/offline events (workshops, seminars, etc.);

- Support in the monitoring and evaluation of partnership projects in municipalities and in advising the Ukrainian municipalities participating in the network on the development and implementation of partnership projects;

- Support for the project team in the preparation of guidelines, information sheets, newsletters with the objective of deepening knowledge within the network in the field of partnership understanding, development cooperation and partnership work;

- Support in the integration of other Ukrainian municipalities in eastern Ukraine (including those not in the SKEW network) in events and activities of the SKEW network;

- Content-related, conceptual and organisational support in the planning and implementation of needs-based information events for Ukrainian municipalities in eastern Ukraine.

The coordination includes meetings that monthly can take place by the Commissioning party (AG) as well as continuous coordination by telephone, Email or Webex/MS Teams meetings.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| Start of the Contract | 25.02.2025 / Ukraine |
| First online meeting with the AG and SKEW project team | up to the 15.03.2025 / Ukraine (online) / AG, SKEW, AN |
| First briefing to the SKEW proposals | up to the 20.03.2025 / Ukraine (online) / SKEW, AN |
| Coordination meetings with AG and SKEW project team | monthly during the contract duration or on the SKEW’s request / Ukraine (online) / AN |
| Performing of the tasks mentioned in clause 2.1. | during the contract duration / on the AG’s request / Ukraine (online and offline) and if required Germany (by participation on events in Germany/, AN |

The contract duration is from 25.02.2025 (begins when the contract is awarded) till 31.12.2026.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| Invoice for interim payment and act of acceptance – original; Timesheet for a month – original; Short interim report (up to 1,5 pages) with information about performed tasks in the reporting month, incl. number of: - online&offline meetings with partner municipalities, - new partnerships with municipalities in eastern Ukraine, if they have been established, - existing partnerships with municipalities in eastern Ukraine that have been consulted on the SKEW's support and financing instruments; Travel and accommodation receipts if they are initially paid by the Contractor; After purchasing the laptop (if necessary): copies of invoice, delivery note, warranty card, supplier's registration documents or a cashier's check (receipt) and a warranty card | All the documents shall be in German or English, signed and stamped (if applicable). Reimbursement of travel costs will be done in accordance with Chapter 5 and based on proof of evidence, which are to be provided by the Contractor: - Copies of bus/train tickets with costs in UAH/EUR and names of travellers (if available). The ticket purchase fee is not to be reimbursed.- Copy of invoice from the hotel/actual service provider with its signature and stamp (if applicable) with the following data: - Surname of guest, - Type of the room, - Type of meal (if available), - Number of nights, - Cost per room, - Total cost. Service fee of booking platforms will not be reimbursed. For non-cash payments in currencies other than UAH – copy of payment order/bank account statement must be provided. | each following month by the 5th day of the month during the contract duration |
| Invoice for final payment and act of acceptance – original; Timesheet for December 2026 – original; Documents if such will be prepared on the SKEW’s request in the corresponding month and indicated in Timesheet; Travel and accommodation receipts if they are initially paid by the Contractor; Final report about performing tasks including the number of new partnerships established and partnership projects implemented during 2025-2026, as well as proposals for new support instruments for municipalities in eastern Ukraine (up to 5 pages) |  | by 23.12.2026 |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept).

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

- Personnel concept (proposed staff)

The Contractor must be suited to filling the position described, on the basis of her/his CV (see Chapter 10), the range of tasks involved and the required qualifications.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

External Expert

Tasks of an external expert are specified in clause 2.1.

Qualifications of the external expert

- Education/training (2.2.1): university degree (Master) in public service, economic policy, (local) governance or a study programme relevant to the sector;

- Language (2.2.2): C1-level language proficiency in German and Ukrainian speaking person is mandatory;

- General professional experience (2.2.3): 5 years of professional experience in the public administration sector or related fields;

- Specific professional experience (2.2.4): 3 years in the field of municipal cooperation and experience of communication and cooperation with representatives of Ukrainian municipalities (mayoral and working level.

Soft skills of the external expert

In addition to their specialist qualifications, the following qualifications are required of the external expert:

- Organisational skills

- Communication skills and openness as well as diplomatic skills

- Commitment and reliability

- Flexibility and mobility

- Ability to work independently.

The tenderer must provide a clear overview of the expert experiences and his/her individual qualifications.

# Costing requirements

## Assignment of personnel and travel expenses

A daily rate corresponds to 8 working hours.

All business travel must be agreed in advance with the director of the project by SKEW and GIZ staff member responsible for the project.

Travel and accommodation costs within Germany as well as within Ukraine are initially paid by the Contractor and then reimbursed upon presentation of original receipts based on the Bundesreisekostengesetz (BRKG) BRKG - nichtamtliches Inhaltsverzeichnis (2nd class for train tickets in Germany) and Travel Guidelines GIZ Ukraine as part of the invoice.

Flight costs to the Germany shall be covered by the AG or SKEW (flight tickets shall be booked and paid for directly by the AG or SKEW).

Before starting a business trip, the Contractor must clarify with the GIZ Project Representative the current rates of per diem and hotel accommodation.

## Sustainability aspects for travel and travel regulations

If applicable on ground of these Terms of Reference the following travel regulations are to be observed. See Annex 1 to these Terms of Reference.

Equipment

The Contractor procures the following equipment, if he/she needs it for performing the tasks in the clause 2.1:

-  a portable laptop. The specification for the laptop incl. Microsoft Office with minimum parameters is in Annex 2.

with a value of up to EUR 1500.00.

The Contractor shall use this laptop for the duration of the Contract and has to return it to the Commissioning party by 27.12.2026 together with the invoice, delivery note, warranty card (original), supplier's registration documents or a cashier's check (receipt) and a warranty card.

Specification of inputs

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| External Expert | day | 1 | up to 360 | The expert is expected to work in average approximately 15 days a month and up to 18-20 days before the conferences or other big events on the SKEW’s request. Up to 180 working days per year. |
| Travel costs |  |  |  |  |
| Fixed travel budget |  |  |  | A budget is earmarked for travel within Ukraine and to Germany. A fixed budget of EUR 10000.00 is earmarked for settling travel expenses against evidence. Settlement is possible only until the budget is depleted. Travel expenses will be reimbursed against evidence, except for per diems. |
| Other costs | Unit of measurement | Quantity |  | Comments (if any) |
| Procurement of equipment | laptop | 1 |  | The budget contains the following costs EUR 1500.00. Equipment expenses will be reimbursed against evidence based on actual price specified in the invoice in UAH. |

## Only the services actually performed shall be invoiced. The actual working time performed shall be broken down according to the tasks described above in a table by days or half days and submitted to the Commissioning Party with the monthly invoice.

## There is no contractual right to use up the full days or budget. The number of days and the budget will be contractually agreed as maximum amounts.

# Inputs of GIZ or other actors

The SKEW will conduct the initial briefing and further coordination meetings with the Contractor.

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the commercial bid. Equipment, travel and accommodation costs are not part of the offer. They shall initially be paid by the Contractor itself and then reimbursed in UAH upon submission of receipts.

Anticipated payment schedule:

In consideration of services completed, the Contractor shall be paid in the following instalments:

| Instalment # | Anticipated payment date | Payment of up to % from total contract value | Deliverables and reporting |
| --- | --- | --- | --- |
| monthly | each following month by the 10th day of the month during the contract duration / 10 days after presentation of invoice | according to time sheet and presented proofs, approx. 6% / month | Acc. to cl. 2.2. |
| Final payment | 27.12.2026 | “ | “. |

  - Financial proposal

The total cost of the Contract is set in EUR, including all direct and related expenses, taxes and fees, incl. VAT to be paid by the Contractor as well as ancillary costs.

All other costs connected to the contract implementation are covered by the total value of the Contract. No additional budget lines are allowed.

All the payments are done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor. The amount in UAH will be calculated as of the month of the provided invoice based on the exchange currency rate of European commission Exchange rate (InforEuro) (europa.eu): https://commission.europa.eu/funding-tenders/procedures-guidelines-tenders/information-contractors-and-beneficiaries/exchange-rate-inforeuro_en

Travel costs provided in Ukraine shall be reimbursed in UAH in accordance with valid limits on the date of travel (per diem) or based on the amount specified in relevant proof of evidence (accommodation, transportation).

For the reimbursement travel costs provided abroad, the following mechanism will be realized:

a) in accordance with exchange rate that is indicated in bank account statement (for cashless transactions).

b) in accordance with European Commission’s official monthly accounting rate, published on

https://commission.europa.eu/funding-tenders/procedures-guidelines-tenders/information-contractors-and-beneficiaries/exchange-rate-inforeuro_en on the date when the financial documents (proof of evidence) was issued. (for cash transactions when no bank statement is available for confirmation of the used exchange rate),

c) in accordance with the exchange rate of National Bank of Ukraine https://bank.gov.ua/ua/markets/exchangerates  (on the date when the financial documents (proof of evidence) was issued)). (in case that invoiced foreign currency is not available at the European Commission site).

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works (“up to”), on the ground of scanned invoices, acts of acceptance and timesheets, submitted in digital form within 10 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Invoices, acts of acceptance and timesheets, etc. shall be scanned as one PDF document (up to 4 mb) and send as an attachment to the e-mail of the GIZ Project Representatives (the e-mail shall be provided additionally) together with other financial supporting documents as and if stipulated by the Contract; the technical documents (reporting/ deliverables) can be submitted either in the same or in a separate e-mail. If the prices in the contract are specified in foreign currency, the Contractor is obliged to indicate prices in all invoices and/or acts of acceptance in two currencies: in foreign currency and in the equivalent amount in UAH and to indicate applied currency exchange rate in accordance with Contract conditions.

- The e-mail body/ text from the Contractor should also contain the following:

- List of the attached documents incl. title of the document, number, date of issue, amount UAH;

- Confirmation, that the services specified in the attached documents were provided in full;

- Full name, position, contact details, full name of the organization.

- Confirmation, that the original documents (invoices, 2 copies of acts of acceptance, other financial supporting documents) will be kept by the Contractor and submitted later as soon as the security situation permits upon the request of GIZ. The deadline and the address for the delivery of documents will be agreed between GIZ and the Contractor via e-mail.

- Each invoice and act of acceptance shall contain the Project Number

- 62.3039.5-001.12

- By submitting the Invoice the Contractor should indicate (in the invoice or in the e-mail) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%).

Timesheet standard template can be found here https://www.giz.de/en/worldwide/63065.html.

- Other Provisions

  - General

The Contract will be signed by the Parties as a soft copy version by sending to each other by electronic means signed and scanned copies of the Contract and annexes. Such Contract shall have full legal force as the hard copies of it. The hard copies will be submitted as soon as the security situation in Ukraine stabilizes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine published on the link  Закупівлі - giz.de (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor (shall be specified).

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption  “Not Applicable”

# Outsourced processing of personal data  - “Not Applicable”

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- CV of expert with relevant work experience, qualifications (education, certificates).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in German or English (language).

The complete technical bid must not exceed 10 pages (excluding CV). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CV of the external expert proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CV shall not exceed 4 pages. It must clearly show the position and job the proposed person held in the reference project and for how long. The CV must be drawn up in German or English.

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Commercial bid must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

    - Documents for tenderer’s eligibility confirmation

| The tenderer is obliged to conform to the following eligibility requirements: | The tenderer must provide the following document to confirm the compliance with eligibility requirements: |
| --- | --- |
| A. Minimum requirements for working experience: at least 1 year of experience in local authority over the past 10 years in Ukraine | Tenders must provide: Eligibility Self-Declaration, 1 (one) supportive (reference) letter |
| B. Minimum requirements for experience with international organisations: at least 1 supportive (reference) letter about the cooperation with international organisation(s) | Tenders must provide: Eligibility Self-Declaration, 1 (one) supportive (reference) letter |
| C. Minimum requirements for reference projects in the required field: 1 reference projects in the field of local development/decentralisation/international relations | Tenders must provide: Eligibility Self-Declaration, Naming of 1 (one) reference project. |

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registarted on uncontrolled territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Annex

- Annex 1 – Travel regulations

- Annex 2 – Specification for a portable laptop

Annex 1 Travel regulations (hereinafter – Regulations)

1.Business trips of experts/consultants All experts/consultants who are travelling on behalf of and commissioned by GIZ should use these Travel regulations for calculation and compensation of costs if these costs are stipulated in the Contract. For the claim of travel expenses, the experts/consultants must submit documents according to the terms of the Regulations, unless otherwise is expressly stated in the Contract. Compensation of travel expenses is carried out exclusively within the limits of the amounts for individual items fixed in the Contract. Payment of advances for business trips is possible only if it is expressly stated in the Contract.

2. Definition of a business trip A business trip, as defined by the GIZ’ general regulations governing the reimbursement of travel expense and accommodation, involves an expert/consultant temporarily working at a place other than his/her regular domicile and/or seat of business to conduct official business with GIZ's approval. The duration of a business trip (period of absence) shall be calculated as the time between departure from the place of residence or the principal place of work at the start of the business trip and the return to any of the above-mentioned places on completion of the business trip.

3. Accommodation allowance Overnight accommodation costs are reimbursed to the extent agreed in the Contract against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). Limits for overnight accommodation shall be stipulated in the Contract. Hotel reservations are made by an expert/consultant by himself/herself. For accommodation during business trips room category not higher than Standard (or equal) is to be booked, unless otherwise is expressly stated in the Contract. Overnight accommodation costs during domestic and international business trips shall not be reimbursed for business trips to a place of residence during which the expert/consultant stays in his/her own home or place where he/she maintains his/her own household.

4. Per diem allowance The per-diem allowance covers the additional cost of subsistence to the expert/consultant during an assignment away from their regular domicile and/or seat of business and accrued if the condition of a one-day or more business trip is fulfilled. The minimum business trip time is a one-day business trip lasting 10 hours, including working hours and travel time. Per diems are paid within the amount specified in the Contract, as a lump sum. The reduced lump sum rate applies for one-day business trips lasting from 10 to 24 hours and depending on the type of meals at the hotel or the provision of meals from GIZ. The calculation of per diems for business trips depending on the type of meals is given in the Table 1 (see below).

5. Currency of reimbursement of travel expenses Reimbursements of costs of business trips within Ukraine are paid in Ukrainian Hryvnia (UAH). Reimbursements of costs of international business trips are paid in Ukrainian Hryvnia (UAH). Reimbursement of travel expenses in foreign currency (not UAH) must be made according to below mentioned: a) in accordance with the exchange rate that is indicated in bank account statement (for cashless transactions). b) in accordance with European Commission’s official monthly accounting rate, published on https://commission.europa.eu/funding-tenders/procedures-guidelines-tenders/information-contractors-and-beneficiaries/exchange-rate-inforeuro_en on the date when the financial documents (proof of evidence) was issued (for cash transactions when no bank statement is available for confirmation of the used exchange rate). c) in accordance with the exchange rate of National Bank of Ukraine https://bank.gov.ua/ua/markets/exchangerates/ (on the date when the financial documents (proof of evidence) were issued)). (In case that invoiced foreign currency is not available at the European Commission site).

6. Flights / ground transportation (train, taxi, private vehicles, car hire/car-sharing/) Costs for transportation are reimbursed within the amount specified in the Contract, against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). The preferred mode of transport shall be economically efficient and environmentally friendly. GIZ is committed to the principles of resource conservation and environmental protection and therefore requires all partners to choose the most environmentally friendly means of transport. Experts/consultants shall take advantage of any price reductions (special rates etc.) that are available. If travel time by train is 5 hours or less, train transport must be preferred for economic and environmental reasons

7.1 Flights Only economy class flight tickets can be reimbursed to experts/consultants. The choice of an airline company should be based on a comparison of ticket prices. The choice of a more expensive flight should be justified by an expert/consultant (e.g. a tight travel schedule combined only with the selected flight).

7.2 Trains Train tickets shall be booked and purchased by the expert/consultant by himself/herself. The ticket purchase fee is not to be reimbursed. If required, first class tickets (abbreviation in Ukraine: Л – two-seater, soft-seated, М – deluxe, single-seater, three-seater) are possible in case your journey not less than 2 hours. The decision on the class tickets is in the responsibility of traveler and should be considered based on the cost-efficiency and security reasons (e. g. overnight trip).

7.3 Taxis and group private transportation If the expert/consultant uses a taxi or a group private transportation during a business trip, abroad or in Ukraine, he\she should follow the principle of economic efficiency and necessity of usage this mean of transport. The justification for such a choice should be provided together with a financial document (proof of evidence).

7.4 Private vehicles As a rule, business trips should be made by rail rather than using a private vehicle. Compensation for usage of private vehicles is allowed if such a category of costs is stipulated in the Contract. In the case of using private vehicles, GIZ compensates for such costs at a fixed rate per kilometre, using the shortest possible route (according to the calculation of the Google Maps navigator). For journeys with a one-way distance of more than 200 km, the expert/consultant must provide evidence that using a motor vehicle is more economical than other means of transport. The basis for reimbursement and for determining which means of transport is more economical is the cost of a second-class rail ticket. If a private motor vehicle is used for other important reasons (e.g. to carry heavy luggage, documents or materials, or if local transport connections are poor), convincing and adequate reasons must be set out by the expert/consultant.

7.5 Buses Bus tickets must be booked and purchased independently by an expert/consultant.

Table 1 / Таблиця 1

The calculation of per diems for business trips per Travel Day

Annex 2 - Specification for a portable laptop

| N | Materials/Goods | Details Specification | Детальна специфікація | Quantity |
| --- | --- | --- | --- | --- |
| 1 | Portable Laptop / Портативний ноутбук | Display: 14.0-14.1" or 15.6; matte or anti-glare; min. resolution 1920*1080 Panel type: IPS Processor: Intel min. i5 min. Gen12 or AMD min. Ryzen 5 min. 6xxx RAM Memory: min. 16 GB Storage: SSD; min. 480-512 GB Ports, no less than: 1 х USB-C with PD (Thunderbolt) 2 x USB-A min. 3.0 1 x HDMI 1 x RJ45 10/100/1000 Gigabit Ethernet or 1 x Laptop Manufacturer External Ethernet Adapter included 1 x combined headphone / microphone 3,5mm Security: min. TPM 2.0 Wi-Fi: min. b, g, n, ac Bluetooth: min. 5.0 Sound: Integrated speakers and microphone Integrated camera: resolution min. 1280*720; built-in camera cover Keyboard: backlit keyboard; English US and Ukrainian layouts Battery: min. 40 W*h Body Material: metal, metal composition or plastic Color: black, grey or silver Weight: max.1.55 kg Warranty: min. 12 months from laptop maufacturer OS: Windows 11 Professional OEM | Дисплей: 14.0-14.1" або 15.6; матовий або анти-відблиск; роздільна здатність мін. 1920*1080 Тип панелі: IPS Процесор: Intel мін. i5 мін. Gen12 або AMD мін. Ryzen 5 мін. 6xxx Оперативна Пам'ять: мін. 16 ГБ Накопичувач: SSD; мін. 480-512 ГБ Роз'єми, не менш ніж: 1 х USB-C з PD (Thunderbolt) 2 x USB-A 3.0 1 x HDMI 1 x RJ45 10/100/1000 Gigabit Ethernet або 1 x зовнішній Ethernet адаптер від виробника ноутбука у комплекті 1 x комбінований роз'єм для навушників / мікрофона 3,5мм Безпека: мін. TPM 2.0 Wi-Fi: мін. b, g, n, ac Bluetooth: мін. 5.0 Звук: Вбудовані динаміки та мікрофон Вбудована камера: роздільна здатність мін. 1280*720; вбудована шторка для камери Клавіатура: підсвічування клавіатури; англійська США та українська розкладки Батарея: мін. 40 Вт*год Матеріал корпусу: метал, композит чи пластик Колір: чорний, сірий або сріблястий Вага: макс. 1.55 кг Гарантія: мін. 12 місяців від виробника ноутбука; ПЗ: Windows 11 Professional OEM | 1 |
| 2 | Microsoft Office | Microsoft Office Home & Business 2024 for 1 PC or Mac, FPP - boxed version, Ukrainian | Microsoft Office для дому та бізнесу 2024 для 1 ПК або Mac, FPP - коробкова версія, українська мова | 1 |