| Supporting the smooth implementation of grants | Project number/ cost centre: 21.2199.4-400.00 |
| --- | --- |

Contents

0.	List of abbreviations	2

1.	Context	3

2.	Tasks to be performed by the contractor	5

3	Personnel concept	9

4	Costing requirements	10

5	Inputs of GIZ or other actors	12

6	Requirements on the format of the tender	12

7	Annex	12

# List of abbreviations

AROCHA - International Christian Environmental Organization

CA - Conservation Agriculture

CAP - Community Action Plan

CIKOD - Center for Indigenous Knowledge and Organizational Development

DDDP - District Development Data Platform

DPCU - District Planning Coordination Unit

EU - European Union

GI-KACE - Ghana India Kofi Annan Center of Excellence in ICT

GIS - Geographic Information System

GIZ - Deutsche Gesellschaft für Internationale Zusammenarbeit

ICT - Information and Communication Technology

JPA - Joint Programme Area

NDPC - National Development Planning Commission

NGO - Non-Governmental Organization

OHLGS - Office of the Head of Local Government Service

REACH - Resilience Against Climate Change

SNV - Netherlands Development Organisation

TECAS - Training & Extension for Conservation Agriculture in the Savannahs

TUDRIDEP - Tumu Deanery Rural Integrated Development Programme

YARO - Youth Advocacy on Rights and Opportunities

# Context

1.1 The REACH project

The Resilience Against Climate Change (REACH) project aims to strengthen communities' resilience to the impacts of climate change within the Joint Programme Area (JPA) of the EU-Ghana Agricultural Programme. The JPA covers 14 districts, including 11 in the Upper West Region, Mamprugu Moagduri in the North-East Region, and Sawla-Tuna-Kalba and North Gonja in the Savannah Region. By the end of 2025, REACH aims to enhance climate resilience in at least 200 communities across the JPA (see Figure 1).

Figure 1. 200 target communities within the REACH JPA

The project is built around three output areas. Output area 1 focuses on strengthening the planning capacities of the 14 districts to improve the effectiveness and efficiency of their processes. This includes capacity building in strategic environmental assessments, the creation of an e-library for district documents, the development of spatial software, the provision of essential IT equipment, and IT and GIS training for members of the District Planning Coordination Units (DPCUs).

Output area 2 aims to promote Conservation Agriculture (CA) by building institutional and community-level capacities. This approach seeks to integrate CA sustainably among the 200 target communities, ensuring long-term adoption and impact.

Output area 3 emphasizes participatory planning processes at the community level. It empowers local government stakeholders to develop and implement Community Action Plans (CAPs), which serve as a foundation for both development and spatial planning efforts. Through this participatory approach, the project fosters collaborative solutions that align with the needs and priorities of local communities.

1.2 Scaling Up Through Grants

Initially, REACH staff worked directly with selected communities to pilot a range of approaches. To meet its ambitious targets, REACH has now partnered with NGOs and government bodies to expand activities. Currently, 12 grants and one local subsidy contract are being implemented to achieve the following goals categorized by output areas:

Output Area 1. Through a grant with the Ghana India Kofi Annan Center of Excellence in ICT (GI-KACE), REACH aims to train 750 district staff in IT and GIS skills within the Joint Program Area (JPA). GI-KACE will also develop e-learning content, accessible via a dedicated platform for future use. This project will be launched in December 2024 and will run until October 2025.

Output Area 2. REACH is supporting five local NGOs (AROCHA, Pro Net North, TUDRIDEP, YARO, CIKOD) to promote climate-smart farming practices, specifically conservation agriculture (CA), to farmers across all 200 REACH communities. These projects began in January 2024 and have been extended through October 2025. Additionally, through a local subsidy contract, REACH collaborates with the social enterprise TECAS (Training & Extension for Conservation Agriculture in the Savannahs) to provide CA mechanization services (such as ripping, harrowing, and no-till planting) to farmers in the JPA.

Output Area 3. REACH has provided grants to three large international NGOs (Action Aid, SNV, World Vision), one local NGO (CARD), and the government agency Office of the Head of Local Government Service (OHLGS) to implement CAP projects. These include borehole drilling, composting and CA training, as well as tree planting. In total, 250 CAP projects will be carried out in 200 communities between December 2024 and January 2026. Another REACH grant is funding the National Development Planning Commission (NDPC) to expand the District Development Data Platform (DDDP), allowing data collected through the CAP process to be digitally accessible.

1.3 Challenge

The 13 organizations working on different aspects of the upscaling activities have varying levels of experience with administrative and financial procedures. However, all grant activities must meet strict GIZ standards, procedures, and regulations. Any failure to adhere to these standards could lead to audit findings, jeopardizing both the organizations' and REACH's credibility and potentially resulting in underutilized grant funds.

1.4 Objective

REACH is seeking a contractor or firm to assist the 13 organizations in implementing their grant or local subsidy projects in full compliance with GIZ requirements.

# Tasks to be performed by the contractor

We expect the contractor to perform serval tasks to support the 13 organizations in the following way:

  - Capacity building on GIZ rules & regulations. The contractor will strengthen the capacity of grant recipients in understanding and applying GIZ rules, regulations, and reporting standards. The core reference for this training is the Annex 3a: Financial Guidelines for Grant Recipients (attached to this tender). Following the contract's signature, this annex is provided to the grantees. However, experience shows that the specific requirements are often not fully understood or consistently adhered to. The contractor will conduct a one-day training for each of the 13 grant recipients to be delivered during visits to the office of the grantee.

  - Portfolio-level monitoring of all REACH grants/local subsidy contracts. The contractor will design a monitoring system (e.g., an Excel table or similar tool) to track the grantees' use of funds. In coordination with the GIZ contracts department, grantees agree on a payment schedule for disbursement in tranches. Grantees must apply for each tranche, with a financial statement required before the disbursement of the third tranche (typically six months after the initial payment). The contractor will regularly collect information on fund disbursements and the submission of financial statements and reports. REACH will receive monthly updates on the status of disbursements. REACH should be promptly informed of any delays, along with details regarding their causes.

  - Improving grantees' internal control systems. The contractor will conduct a thorough review of the grantees' internal control systems, assessing both financial and administrative aspects. To gain a solid understanding of each grantee’s situation, a one-day office visit is planned. The review will focus on areas such as transparency, function segregation, dual controls, and adherence to the need-to-know principle. If any deficiencies are identified, the contractor will provide support to the grantees, either by implementing suitable tools or delivering targeted training to enhance their internal controls. It is anticipated that the quality of internal control systems will vary across organizations, with only a few needing significant support. We estimate that four grantees may require additional, substantial assistance, which would involve a second one-day office visit.

  - Ongoing finance and admin coaching. Throughout the implementation of grant or local subsidy contracts, the contractor will provide continuous coaching to grantees. This includes monthly check-ins of 1–2 hours with key finance and administrative staff at the respective organizations, as well as on-demand support via phone for any questions related to GIZ rules and regulations. If the contractor encounters questions beyond their expertise, they will promptly consult REACH contacts to obtain accurate information.

  - Technical follow up on implementation. The contractor will closely follow up on the implementation of the grant recipients. Whether or not funds are spent on time is heavily dependent on meeting timelines at the technical level. Similarly, the technical implementation produces the evidence (e.g., vouchers) that is used within the financial and administrative system. The contractor will hold monthly 1-2 hours update meetings (by phone, MS Teams, etc.) with the technical teams of the grantees and conduct selected site visits, specifically for activities that are considered risky from a finance and administrative perspective, requiring special attention. A narrative update on the status of the technical implementation will form part of the monthly updates that the contractor submits to REACH.

  - Quality assurance of reports. The contractor will be responsible for ensuring the quality of the financial reports before submitting to GIZ. When issues are detected, the contractor will closely collaborate with the grantee to improve the quality of reports and provide the necessary details. Grantees will have to submit two financial reports (one after 6 months, and one after completion). We assume that quality assurance will take 1 day for each report.

  - Support during audits. Ten grants exceed a value of 120,000 euros, requiring GIZ to commission audits at the end of the grant period. These audits will be conducted by the international firm BDO, following strict and rigorous standards. The audits are expected to take place between December 2025 and March 2026. The contractor will support all ten grantees in preparing for the audits by ensuring all necessary documents and evidence are in order. During auditor visits (requiring the contractor’s physical presence), the contractor will provide on-site assistance and advise the grantees on what information to share. Minimizing audit findings is of utmost importance.

  - Reporting. The contractor submits the following reports:

Inception report. The inception report shall be submitted one week after the inception meeting (1-hour MS teams call). The inception report provides details on the concept, method and planned activities, structured according to relevant processes. The inception report has a strategic focus and serves as a roadmap for the assignment. The inception report should not exceed 10 pages (Arial, font size 11).

Monthly brief update reports. As outlined above, the contractor will provide summative overview of the status of all ongoing grants. Status reports will include an overview of disbursements as well as a summary on the status of the technical implementation. The monthly reports are due every first Monday of a given month and should not exceed 2 pages (Arial, font size 11).

Final report. The final report should focus on the results, with particular emphasis on the capacities developed. It must follow the prescribed structure and not exceed 12 pages (Arial, font size 11). If additional detailed information needs to be provided, please include it in an annex, which has no page limit. The final report will undergo a review by REACH, and the contractor will be required to revise the document in accordance with the feedback provided before it can be accepted.

- Title Page (1 Page)

- Table of Content (1 Page)

- Introduction and context (2 Pages)

- Activities (3 Pages)

- Results (4 Pages)

- Problems, limitations, and lessons learned (1 Page)

- Annex (no page limitations)

Milestones

Certain milestones, as laid out in table 1 below, are to be achieved by certain dates during the contract period. During the implementation period, milestone deadlines may be adjusted, if necessary (e.g., due to unforeseen delays), subject to written approval from REACH staff.

Table 1. Milestones

The milestones are set up in accordance with the time structure of the assignment.

| Milestone | Deadline | Comment |
| --- | --- | --- |
| Inception meeting completed | 17.04.2025 | REACH will invite to the inception meeting; Contractor will prepare a presentation. |
| Inception report submitted | 25.04.2025 |  |
| Monthly update reports submitted | First Monday of each month |  |
| 2.1 Capacity on GIZ rules & regulations has been built | 02.06.2025 |  |
| 2.2 Portfolio-level monitoring established | 12.05.2025 |  |
| 2.3 Grantees' internal control systems is improved | 08.08.2025 |  |
| 2.4 Coaching completed | 14.01.2026 | Coaching will be completed with the ending of the implementation of grants on 14.01.2026. |
| 2.5 Follow up on technical implementation completed | 14.01.2026 | Follow up on technical aspects will be completed with the ending of the implementation of grants on 14.01.2026. |
| 2.6 Reports have been quality assured | 14.01.2026 | Quality assurance takes place as soon as reports are prepared by the various organizations. |
| 2.7 Support during audits has been provided | 31.03.2026 | Audits may take place until 31.03.2026 and the contractor will need to support organizations during the process. |
| Final report submitted | 16.03.2026 | The final report will be submitted about two weeks before the end of the contract. |

The period for delivering the assignment is 14.04.2025 until 31.03.2026.

In the tender submission, the tenderer must outline their approach to achieving the objectives outlined in Chapter 2 (Tasks to be performed) in the assignment, while also considering any additional methodological requirements. The tenderer must also describe the project management system they will use for service provision.

Note: The numbers in parentheses (Section 3 and 4) correspond to the lines of the technical assessment grid.

Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1, Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which they intend to provide the services for which they are responsible (see Chapter 2, Tasks to be performed) (1.1.2).

Cooperation (1.2): The tenderer is required to identify the key actors relevant to the services they will provide and describe how they plan to collaborate with them (1.2.2). The primary actors for this assignment include REACH and the various grant/local subsidy recipients mentioned above. Building strong, trust-based relationships with all involved organizations is essential for the success of this assignment. In their proposal, the tenderer should outline their approach to fostering these relationships and ensuring effective collaboration with the various stakeholders. We recommend holding monthly update meetings between the contractor and REACH, aligned with the submission of the monthly updates. These meetings, to be facilitated by the contractor, will provide a platform to address operational, administrative issues, and any challenges that arise.

Processes (1.4): The tenderer is required to describe the key processes for the services for which they are responsible and create an operational plan (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed) are to be delivered. In particular, the tenderer is required to describe the necessary work steps and take into account the milestones. The bidder is expected to provide a Gantt chart (as annex table to the bid) using a weekly temporal resolution to show when activities of the various processes will take place during the duration of the assignment.

Project management (1.6): The bidder is required to explain their approach to project management specifically considering the following points:

- The bidder shall make a provisional plan of work with a narrative regarding the execution of the assignment, demonstrating the roles and responsibilities and overall composition of the team. The narrative description should be accompanied by a table of the personnel assignment plan outlining who does what (with reference to the work steps listed under the processes above), including an explanation and specification of expert days (1.6.2).

- The bidder should describe in detail their backstopping/project management strategy. This includes both the technical and administrative backstopping to facilitate the smooth implementation of assignment against the defined objectives, workplan and budget. The CVs of the technical and administrative back stoppers should be included as appendix to the bid. The experience level of the back stoppers as well as the quality of the overall backstopping strategy will be assessed (1.6.3).

# Personnel concept

The consultancy firm is expected to provide personnel who meet the requirements for the specified roles, based on their CVs, relevant experience, and the qualifications needed for evaluation. The assignment team should include a team leader and two finance and administration experts. The team leader will primarily oversee the overall management and coordination of the assignment, while the two experts will focus on supporting and building the capacity of the organizations involved.

Team leader

Tasks of the team leader

- Overall responsibility including the steering, management, and oversight of the various processes of this assignment (quality and deadlines).

- Coordinating and ensuring communication with GIZ, partners and others involved in the project.

- Personnel management.

Qualifications of the team leader

- Qualifications (2.1.1): Master’s degree in business administration, economics, finance, project management, or any business-related field.

- Language (2.1.2): Good business language skills in English (knockout criterium).

- General professional experience (2.1.3): More than 12 years of experience in the sector of project fund management.

- Specific professional experience (2.1.4): 5 years in supporting structures managed by GIZ.

- Leadership/management experience (2.1.5): 3 years of management/leadership experience as project team leader or manager in a company/organization.

Key expert 1

Tasks of key expert 1

- Primarily responsible for executing specific technical tasks as outlined in Chapter 2

- Support the team leader on various administrative tasks (e.g., report writing, etc.)

Qualifications of key expert 1

- Qualifications (2.2.1): A bachelor’s degree in business administration, economics, finance, project management, or any business-related field.

- Language (2.2.2): Good business language skills in English (knockout criterium).

- General professional experience (2.2.3): 7 years of experience in the sector of project fund management.

- Specific professional experience (2.2.4): 3 years in supporting structures managed by GIZ.

Key expert 2

Tasks of key expert 2

- Primarily responsible for executing specific technical tasks as outlined in Chapter 2

- Support the team leader on various administrative tasks (e.g., report writing, etc.)

Qualifications of key expert 2

- Qualifications (2.2.1): A bachelor’s degree in business administration, economics, finance, project management, or any business-related field.

- Language (2.2.2): Good business language skills in English (knockout criterium).

- General professional experience (2.2.3): 7 years of experience in the sector of project fund management.

- Specific professional experience (2.2.4): 3 years in supporting structures managed by GIZ.

# Costing requirements

In the following, various quantities are specified that determine the framework of this assignment. Bidders are required to use the exact amounts specified below in their financial bid. For this assignment, the costs of personnel, travel, and other expenses contribute to the overall costs. We anticipate the following number of expert days required for each position for this assignment as detailed in Table 2.

Table 2. Assignment of personnel

| Item | Number of days per expert |  |  | Comments |
| --- | --- | --- | --- | --- |
|  | Team Lead | Expert 1 | Expert 2 |  |
| Execution of the activities detailed in Chapter 2. | 100 | 110 | 110 |  |

Travel costs:

Overall, three types of travel are planned: first, an initial visit to the offices of the 13 organizations to gain insight into their internal control systems; second, a field visit to a key implementation site; and third, a visit to the organizations' offices during the audit phase. Since travel expenses are not position-dependent, we have provided only the total estimated costs. Note that travel expenses are reimbursable against evidence in compliance with all GIZ regulations.

Table 3. Travel expenses

| Item | Unit count (e.g., days) | Comments |
| --- | --- | --- |
| Per-diem allowance (full travel day) | 53 | The per diem for a full travel day is set at 450 GHC, in line with GIZ rates. |
| Per-diem allowance (half travel day) | 40 | Half travel days, covering arrival and departure, are set at a GIZ rate of 225 GHC. |
| Overnight allowance | 70 | Hotel accommodations will be provided for travel days, with an additional night covered for the arrival day. GIZ rates apply: 900 GHC in regional capitals and 650 GHC at the district level. |
| Domestic flights (round trip) | 26 | Round-trip domestic flights will be required between Accra (or the contractor’s origin) and the organizations' offices or implementation sites. |
| Car rental | 26 | Car rentals will be needed for all visits to implementation sites. The current market rate for car rentals is 2,000 GHC per day, including fuel. |

Other costs:

- Mobile Data. Much of the work of the contractor will require access to the internet and therefore mobile data. We assume monthly mobile data costs of 500 GHC for the full period of the assignment of 12 months resulting in a maximum of 6,000 GHC (reimbursable against evidence).

- Flexible remuneration. A budget of GHC 60,000 is foreseen for flexible remuneration. Please incorporate this budget into the price schedule. During implementation, flexible remuneration may be allocated to cover unforeseen expenses within existing budget lines. Written permission from GIZ must be obtained before using these funds.

- Ghana tax law applies (7.5% withholding tax).

# Inputs of GIZ or other actors

GIZ/REACH will provide the following:

- Dedicated contact person for the assignment.

- Review and feedback on reports as well as training material within 5 working days of submission.

- Provide contact details to focal persons at the various organizations.

# Requirements on the format of the tender

The structure of the tender must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted (not with zero) criteria in the assessment grid. The tender must be drawn up in English, legible (Arial, font size 11) and clearly formulated.

The complete tender must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be written in English, should be structured according to assessment grid criteria (e.g. general professional experience, specific professional experience, etc.), and should not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long.

Please calculate your financial bid based exactly on the parameters specified in Chapter 5 (Quantitative requirements). The contractor is not contractually entitled to use up the days, trips, or budgets in full. The number of days, trips, and the budgets will be contractually agreed upon as maximum limits. The specifications for pricing are defined in the price schedule. Financial offers should be categorized based on the tasks to be performed in Chapter 2 and other incidental cost as mentioned in this ToR.

# Annex

Annex 1: Annex 3a Financial Guidelines for Grant Recipients (https://www.giz.de/en/downloads/giz2024-en-annex-3a-financial-requirements-grant-recipients.pdf)

A knockout criterion indicates a mandatory characteristic. The bidder will be disqualified if this criterion is not met.