## Sheet1
Planned Time Schedule for Rehabilitation works in VTC Erbil Active section to be filled by the bidders
Program Migration for Development PN: 23.2165.1-161
NO. | Items
|  | Month | Month 1 |  |  |  | Month 2
|  | Week | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Mobilization | Planing | bar: Month 1 1
Active
2 | Office rehabilitation works | Planing | bar: Month 1 2 to Month 1 3
Active
3 | Stair case construction | Planing | bar: Month 1 2 to Month 1 3
Active
4 | Corridor works | Planing | bar: Month 1 2 to Month 1 3
Active
5 | Main entry door replacement | Planing | bar: Month 1 2 to Month 1 3
Active
6 | Toilets rehabilitation works - VTC building | Planing | bar: Month 1 4 to Month 2 2
Active
7 | Toilets rehabilitation works - Conference hall building | Planing | bar: Month 1 4 to Month 2 2
Active
8 | Site hand/take over | Planing | bar: Month 2 2
Active