## Sheet1
Planned Time Schedule for cabin construction works in Halabja Active section to be filled by the bidders
Program Migration for Development PN: 23.2165.1-161
NO. | Items
|  | Month | Month 1 |  |  |  | Month 2 |  |  |  | Month 3
|  | Week | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
| Mobilization | Planing | bar: Month 1 1
Active
| Excavation and foundation | Planing | bar: Month 1 2 to Month 1 4
Active
| Cabin construction (Steel frame, Panels, Kerby…etc) | Planing | bar: Month 2 1 to Month 2 3
Active
| Plumbing and Electircity | Planing | bar: Month 2 3
Active
| Flooring, doors, windows and site cleaning. | Planing | bar: Month 2 3 to Month 2 4
Active
| Site hand/take over | Planing | bar: Month 3 1
Active